## Slide 1: Beam Transport Modules Preliminary Design Review (WP12)
Dr Paul Aden
Project Manager
ESS PDR, Lund, 10th November 2015

## Slide 2: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  3 Test Chambers
  75 LWUs
  52 Beam pipe modules
  2 Differential pumping systems
  2 mobile installation cleanrooms
Notes: Over the next four years we have been asked to delivery …

## Slide 3: Scope of work update
Particle control only on 52/75 LWUs
  Upto HEBT
BPM work package
  Only electrical centre measurement, not on prototype
  BPMs Pickups are to be supplied on contract loan from DESY
Final decision on BPM design expected March 2016
Magnet designs still now finalised.
  Unknown completion date (Dec 15?)
  Working with space envelopes until then (not ideal)
Notes: Upto hebt

## Slide 4: Overview In/Out
In
  Girder design & procurement
  Chamber design (within given parameters) & procurement
  Vacuum design & procurement
  Survey & Alignment
  Particulate Control
Out
  BPM Procurement & Design
  BCM Design
  Bolt in diagnostics
  Magnet Design & Procurement
  Installation & Onsite testing

## Slide 5: Scope of Work
Technical Annex currently being complied.
Full Scope now available
  Full excluded / included list in STFC document tdl-1224-meng-spec-0005

## Slide 6: Schedule
BTM Assembly
2015 | 2016 | 2017 | 2018 | 2019 | 2020
Magnet Deliveries
Differential Pumping System 2
Installation Cleanrooms
Differential Pumping System 1
Elliptical Prototype
Spoke Prototype
BPM Deliveries
BTM Design
BP Assembly
LWU Assembly
20/08/19

## Slide 7: Final Design Reviews
Milestone | Date
Elliptical | June 2016
Spoke | June 2016
HEDP | July 2016
LEDP | July 2016
Cleanrooms | August 2016
Beam Pipe | August 2016

## Slide 8: Schedule Detail
Last LWU 20/08/19
First useful magnet delivery 5/5/17
Final Magnet Design not until December 15
  Therefore, no magnets on prototypes
Q7 magnets arriving first, these magnets however these LWUs do not require particle control.

## Slide 9: Elettra Delivery Plan
Current schedule suites magnet deliveries, do magnet deliveries suite ESS?

## Slide 10: BPMs
Last date for BPM design to be given to STFC, March 2016.
  For strip line full detailed design should be given
  Will allow re-design of chambers
  Will give time for manufacture of chambers
BPM Delivery
  BPMs should start arriving at STFC in August 2016
  Should be continuous supplied to STFC at a rate of 4 BPM pickups per week.
  No Delivery Schedule has been seen

## Slide 11: Summary
Prototype
  Build to start 10/2/16
Production Units
  PDR 10/11/15
  Beam pipe build to start 8/8/16
  LWU Build to Start 13/2/17 – dictated by magnet shipments
BPMs must have finalised design by March 16
Magnet Delivery schedule could be changed to improve LWU deliveries
Notes: Prototype 2 - FDR 14/7/16

## Slide 12: Mechanical Design

## Slide 13: Warm Linac Units

## Slide 14: Warm Linac Units
Aluminium slotted girder
One BPM per LWU
Semi–kinematic
girder adjustment
Pedestals
Quadrupole Magnets
Fiducials, laser tracker alignment
Built in lifting points
‘Particle Free’ Chamber
- ISO 5 or better

## Slide 15: Design Overview
Based on many years experience developing accelerator modules
Slotted girders allows for versatility
Optimised for ground vibrations
Fiducial mounts for survey and alignment
  ±50µm alignment to local girder network
Girder adjustment ±55mm
Magnet/Chamber adjustment ±15mm
Large space between pedestals for access/egress

## Slide 16: Chamber Design

## Slide 17: Material Selection
Tube & main chamber body; 316L
Tube to be seamless.
Tubes 3.2mm thickness, Magnetic permeability to be less than 1.005
Flanges 316LN
Bellows TBC
Either 316L or 321

## Slide 18: Chamber Stress
Current design does not exceed 80MPa.
Therefore if required the wall thickness on the tubes potentially could be reduced

## Slide 19: Chamber Deflection
Maximum chamber deflection is 0.14mm on box flanges.
Maximum of 50µm on fiducials – fiducial position to be re-assed

## Slide 20: Add New Schematic Here

## Slide 21: BPM
BPM design
  Current estimates based upon;
    Button BPMs
    Welded into the chamber
  Prototype must have flanged design
  Both types will fit in the space envelope
    (now that there is one BPM per LWU)

## Slide 22: BPM
Welded BPM | Flanged BPM
Pros: | Pros:
High reliability of the welded (STFC) | Flanged BPMs easier to clean/PC
Welded BPMs do not create additional leak point | Flanges easier to replace in-situ
Higher installation accuracy | 
Cons: | Cons:
Welded BPMs more difficult to particle count | Create many possible leak points
Can not be swapped out | Processing is more time consuming

## Slide 23: BPM
Prototype design uses DN 25
  To match existing BPM Pickups
DESY Proposed block to use DN 50
STFC Proposed block to use DN40
  European standard
  Needs discussion with DESY but may give smaller block.
Space available for stripline units is 175mm to still allow magnet / Chamber adjustment
  This needs to includes space for mounting & feedthroughs
Notes: (210 with zero adjustment)

## Slide 24: BCM Design
4 x BCMs. Flanged solutions are preferable.
Preferred Solution
Similar EMMA Design

## Slide 25: Design
Current design uses Knife Edge flanges.
  Are ESS bound to this?
  Can we look at other options?
  Prototype to use knife Edge
Bellows Design…

## Slide 26: Bellows

## Slide 27: Bellows Travel Requirements
Bellows Travel Required 85mm
35mm M8
Gate valve
VAT 48
LWU Side
Tapped Blanking Flange

## Slide 28: Bellows Travel Requirements
Bellows Travel Required 65mm
Bolt Extraction Direction
Slotted CF Flange
Tapped CF Flange
Gate valve
VAT 48

## Slide 29: Bellows constraints
Can be ‘bagged’ during installation
Currently in discussions with DESY to investigate possible use of KEK film on mobile cleanrooms.

## Slide 30: Bellows Design
Still in discussions with suppliers
Specifications maybe difficult to achieve
Slotted flanges would reduce the travel required by the bellows
Could non-standard width flanges be used?
Can the internal bellows ID be reduced?
  To say 85mm?
  What could the minimum be?
Are rotatable flanges required.
  Do they need mechanical fixings?
  How to prevent particle generation?

## Slide 31: Bellows Design
Any other methods to reduce bellows travel
  Capped LWUs rather than flanged.
  Capped gate valves?

## Slide 32: Survey and Alignment

## Slide 33: Survey & Alignment
4 x 6H7 Fiducial Mounts,
Will be machine post chamber assembly to ensure accuracy

## Slide 34: Survey & Alignment
4 x 6H7 Fiducial Mounting points at each corner of the girder.
4 x 6H7 Fiducial mounting points at each corner of the pedestal.

## Slide 35: Survey & Alignment
BPM Survey fiducials for reference to local girder network

## Slide 36: Prototype

## Slide 37: Prototype
Prototype to be one welded assembly
Three other dummy chambers to be three flanged units in different configurations, to improve particulate control

## Slide 38: Prototype
Reduce production series risk
Determine particle control procedure to be agreed
Producing three dummy chamber will allow for variation in design to be tested to determine best design to achieve
  Low particulate requirement
  Most efficient Particle control procedures
  Most fit for purpose design

## Slide 39: Schematic LWU Layouts

## Slide 40: Elliptical Requirements

## Slide 41: Elliptical Design
350mm
350mm
720mm
1932.4mm
150mm
256.2mm
256.2mm

## Slide 42: Elliptical

## Slide 43: Elliptical
5 Types to cover the 7 variations
Chamber Type 1

## Slide 44: Elliptical
Chamber Type 2 Covers:
Notes: Non-invasive Profile Monitor – such as ionization profile monitor

## Slide 45: Elliptical
Same basic Chamber design but with BPM at rear
Could be the same chamber if is made of three parts
Chamber Type 3 Covers:

## Slide 46: Elliptical
Chamber Type 4
Chamber Type 5

## Slide 47: Spoke LWUs

## Slide 48: Spoke Chambers
3 Types to cover the 8 variations
Chamber Type 1
FC Flange unknown

## Slide 49: Spoke
?
Chamber Type 2

## Slide 50: Spoke
Chamber Type 3

## Slide 51: LEDP
Elliptical Chamber Type 2

## Slide 52: Beam Pipe units
No Survey or alignment requirements
  Fiducials will be included.
No fine adjustment
Basic no adjustable framework
Central Pumping section with spare ports

## Slide 53: Girder Design

## Slide 54: LWU Girder

## Slide 55: Pedestals
450 mm
450 mm
710mm
Steel Box Section- hollow to allow for damping sand if needed
Mount for central support and wheels
No Grout. Kinematic can cope with floor unevenness Holes on floor etc…

## Slide 56: Ingress / Egress
700mm
850mm

## Slide 57: Adjustment
Individual item adjustment on three point kinematic mounts

## Slide 58: Adjustment
=/ 15mm – check later

## Slide 59: Vertical Adjustment
Vertical Adjustment on Semi-Kinematic mounts ± 50mm

## Slide 60: Adjustment
Slider Plate, Girder directly mounted to these steel plates

## Slide 61: Y & Z Adjustment
Adjusting Screws

## Slide 62: Semi Kinematic Adjustment
Lifting Points
Cone Adjusting Screw
Vee Adjusting Screw
Flat Adjusting Screw
Horizontal Movement Clamps
Girder
Y,Z Plate
Notes: At the request of ESS Survey and alignment group horizontal girder adjustment is above vertical adjustment

## Slide 63: Semi Kinematic Mounts
‘V’
Cone
Flat
M30 Tie Downs

## Slide 64: Adjustment
Slotted Girder allows for ‘unlimited’ ‘coarse’ on z Adjustment.
Mounting adjustment allows for ±15mm fine adjustment
Kinematic mounts allow for vertical adjustment ±25mm on a fine M24 nut.
Plus girder adjustment
At the request of ESS Survey and alignment group horizontal girder adjustment is above vertical adjustment

## Slide 65: Installation support/wheels

## Slide 66: Installation Supports
Fixes pedestals together to easy removal and replacement of girder whilst pedestals are not fixed to the floor
Lifting Points for Girder, Adjusted for CoG
Removable wheels

## Slide 67: ELI-NP Lifting Frame

## Slide 68: Shipment

## Slide 69: Delivery
From Scope Document:
All beam transport modules will be shipped DDP (Delivered, Duty Paid) from Daresbury Laboratory. STFC is responsible for loading the all the Beam Transport Modules onto a vehicle, for all export procedures and for onward transport to ESS. ESS will accept responsibility for BTMs after a visual inspection and pressure check, i.e. that the pressure still reads 1100mbar.

## Slide 70: Transport Method Option
Open plywood box with corner supports
Plywood bottom with timber base for reinforcement
Anti-Vibration Springs
between module and box base
1
2
3
Lifting Points required on 3.
Plywood lid
Module
Airide trailer for low road vibration transmission
Springs between girder and box base for shock loads
Quantity will depend on girder length & weight
Spring dampers

## Slide 71: Crates
Crates will be capable of being stacked two units high.
All crates will have tilt & shock watch detectors mounted on the sides.

## Slide 72: Production Management
All Beam Transport Modules will have serial numbers
All Items in the module will be similarly numbered
All Modules will have Quality Control documents which will follow the module through the build process
All BPMs should have serial numbers etched into them, the BPMs used on each module will be reordered in the modules Quality Control Log
Each Module will ship with it’s unique quality control log

## Slide 73: Outstanding Design Items
Bellows – availability / compromise
Rectangular flange design
BPM Decisions
  BPM Style – full detailed design required by March 16
  Flanged vs Welded
  Flange Size
  BPM Delivery Schedule
  Stripline everywhere?
H&V Corrector Design
Q5 Magnet Design
Dipole Magnet Design
Particulate Process agreement

## Slide 74: Other Options
Delivery without magnets?
Staff welcome to come to STFC to spend time building LWUs
Notes: BI to be installed in the tunnel.
Cleanroom times & delivery times.

## Slide 75: Thank You
ESS PDR, Paul Aden, 10-11-15