## IST Stave Progress
Updated | 2012-11-02
STAVE Numbers |  |  |  | Prep |  |  | Open Stave |  |  |  | Assembly |  |  |  | Bare Staves |  |  |  | Quality Assurance |  |  |  | Shipping
STAVE Starts | Hybrid Serial Number | Production Database Number | LBNL Serial Number | Received | Pictures | Masking | Co-Cured | Foam Bond | Honey-Comb | Close-Out Bond | Core Ground | Foam Machined | Tube Bonded | Stave Closed | Tube Swaged | Connector Holes | Ground Connection | Plasma Clean | Pressure Cycle Leak Result | In Survey | Survey Result | Finish Date | Boxed | Shipping Number | Comment
1 | IST-001 | Pre-Prod. | [12 empty] | n/a |  | n/a |  | n/a | n/a | n/a |  | x | Delivered | Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
2 | IST-002 | Pre-Prod. | [12 empty] | n/a |  | n/a |  | n/a | n/a | n/a |  | x | Delivered | Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
3 | IST-003 | Pre-Prod. | [12 empty] | n/a |  | n/a |  | n/a | n/a | n/a |  | x | Delivered | Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
4 | IST-004 | [13 empty] | * |  |  |  | * | * | * |  |  |  | Deliver without Swage or Survey
5 | IST-005 | [13 empty] | * |  |  |  | * | * | * |  |  |  | Deliver without Swage or Survey
6 | IST-006
7 | IST-007
8 | IST-008
9 | IST-009
10 | IST-010
11 | IST-011
12 | IST-012
13 | IST-013
14 | IST-014
15 | IST-015
16 | IST-016
17 | IST-017
18 | IST-018
19 | IST-019
20 | IST-020
21 | IST-021
22 | IST-022
23 | IST-023
24 | IST-024
25 | IST-025
26 | IST-026
27 | IST-027
28 | IST-028
29 | IST-029
30 | IST-030
31 | IST-031
32 | IST-032
33 | IST-033
34 | IST-034
35 | IST-035
36 | IST-036
37 | IST-037
38 | IST-038
39 | IST-039
40 | IST-040
41 | IST-041
42 | IST-042
43 | IST-043
44
45
[6 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 3 | Shipped
Ready to ship
[23 empty] | 3 | Total

## IST Ladder Integration
STAVE Numbers |  |  | SMT Loading |  |  | Shipping |  | Sensor and ASIC Loading | [6 empty] | Shipping |  | Assembly
STAVE Starts | Hybrid Serial Number | Production Database Number | Received | Location | Components Loaded | Boxed | Shipping Number | Received | Location | Sensors | APV | Wire Bond | Electrical Test | Encapsulate | Boxed | Shipping Number | Assembly Complete | Received At BNL | Electrical Test | Comment
1 | IST-001
2 | IST-002
3 | IST-003
4 | IST-004
5 | IST-005
6 | IST-006
7 | IST-007
8 | IST-008
9 | IST-009
10 | IST-010
11 | IST-011
12 | IST-012
13 | IST-013
14 | IST-014
15 | IST-015
16 | IST-016
17 | IST-017
18 | IST-018
19 | IST-019
20 | IST-020
21 | IST-021
22 | IST-022
23 | IST-023
24 | IST-024
25 | IST-025
26 | IST-026
27 | IST-027
28 | IST-028
29 | IST-029
30 | IST-030
31 | IST-031
32 | IST-032
33 | IST-033
34 | IST-034
35 | IST-035
36 | IST-036
37 | IST-037
38 | IST-038
39 | IST-039
40 | IST-040
41 | IST-041
42 | IST-042
43 | IST-043
44
45
|  |  | 0 |  |  | 0 | Shipped | 0 | [6 empty] | 0 | Shipped |  |  | 0
[7 empty] | Ready to ship | [8 empty] | Ready to ship
[6 empty] | 0 | Total | [7 empty] | 0 | Total