## SUMMARY
| BASE | [7 empty] | CONTINGENCY
Year | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 844 | 755 | 48 | 553.5 | 0 | 39174.5 |  | 2009 | 273 | 341 | 88 | 163 | 0 | 13227.5
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Contingency
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 107188 | 88335 | 6096 | 83025 | 0 | 39174.5 | 323818.5 | 2009 | 34671 | 39897 | 11176 | 24450 | 0 | 13227.5 | 123421.5
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 323818.5 | [6 empty] | Contingency | 123421.5
[14 empty] | Percent | 38.11%
| Pre-Production Base Cost | [7 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 0 | [6 empty] | Contingency | 0
[14 empty] | Percent | #DIV/0!
| Production Base Cost | [7 empty] | Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 844 | 755 | 48 | 553.5 | 0 | 39174.5 |  | 2009 | 273 | 341 | 88 | 163 | 0 | 13227.5
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 107188 | 88335 | 6096 | 83025 | 0 | 39174.5 | 323818.5 | 2009 | 34671 | 39897 | 11176 | 24450 | 0 | 13227.5 | 123421.5
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 323818.5 | [6 empty] | Contingency | 123421.5
[14 empty] | Percent | 38.11%

## Pre- and Production
Barrel Support Estimate | [14 empty] | TRACKING | [8 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | CMM | Eng Time | Des Time | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals
Material Batches | [21 empty] | Underage(-)
Thicker M55J | M55J | 1 | Order | 10000 | 10000 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 10300 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 2 | 0 | 10000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 534 | 1 | 534 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 55 | 27.5 | 0 | 8 | 0 | 1 | 0 | hours | 3258 | 3 | 3340.5 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 24 | 0 | 3 | 0 | 82.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 1800 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 2 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cloth CN60 | CN60 | 1 | Order | 6000 | 6000 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 6300 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 6000
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 234 | 1 | 234 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 55 | 27.5 | 0 | 8 | 0 | 1 | 0 | hours | 3258 | 3 | 3340.5 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 3 | 0 | 82.5
Test | N/A | 1 | Order | 1500 | 1500 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 1800 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 1500
Carbon Foam Core | Allcomp Densified | 2 | bdft | 600 | 1200 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 1500 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 2 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Pre-Production | Hysol 9320 | 1 | Order | 500 | 500 | 0 | 0 | 0 | 0.5 | 0 | hours | 75 | 1 | 575 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0.5 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Batches | Hysol 9320 | 1 | Order | 500 | 500 | 0 | 0 | 0 | 0.5 | 0 | hours | 150 | 2 | 1150 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 1 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables | Bagging | 1 | Order | 5000 | 5000 | 0 | 0 | 0 | 1 | 0 | hours | 150 | 1 | 5150 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 1 | 0 | 5000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Material Batches Subtotal | [11 empty] | 5067 | Base Labor | [10 empty] | 0 | 26 | 0 | 13.5 | 0 |  | 19282.5 | 24349.5 |  | 11674.5 | 0 | 26 | 0 | 7 | 0 |  | 7582.5
Layer Support Assemblies
Plate (for all parts + spares) | [12 empty] | 1
Plate Lamination | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 0 | 0 | hours | 1404 | 3 | 1569 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 12 | 0 | 0 | 0 | 165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim to Size (cuts all face sheets, both styles) | Batch | 0 | Waterjet | 80 | 0 | 8 | 4 | 0 | 4 | 0 | hours | 2084 | 1 | 2084 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 4 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Core | [12 empty] | 1
Rough thickness core | Batch | 0 | N/A | 0 | 0 | 32 | 8 | 0 | 1 | 0 | hours | 5150 | 1 | 5150 | B | PD | BPD2009 | [5 empty] | 2009 | 32 | 8 | 0 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim to shape (all styles) | Batch | 3 | Cutter | 80 | 240 | 16 | 8 | 0 | 2 | 0 | hours | 3268 | 1 | 3508 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 8 | 0 | 2 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface Parts | [12 empty] | 1
Inserts | CF PEEK | 0.03 | lb | 600 | 18 | 0.5 | 0 | 0 | 0.1 | 0 | hours | 9420 | 120 | 11580 | B | PD | BPD2009 | [5 empty] | 2009 | 60 | 0 | 0 | 12 | 0 | 2160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Inserts (contingency) | CF PEEK | 0.03 | lb | 600 | 18 | 0.5 | 0 | 0 | 0 | 0 | hours | 3175 | 50 | 4075 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 25 | 0 | 0 | 0 | 0 | 900
Stave Mounts | CF PEEK | 0.08 | lb | 600 | 48 | 1 | 0 | 0 | 0.1 | 0 | hours | 11360 | 80 | 15200 | B | PD | BPD2009 | [5 empty] | 2009 | 80 | 0 | 0 | 8 | 0 | 3840 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mounts (Contingency) | CF PEEK | 0.08 | lb | 600 | 48 | 1 | 0 | 0 | 0 | 0 | hours | 5080 | 40 | 7000 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 0 | 0 | 0 | 0 | 1920
Tooling | [10 empty] | Sum | 29198 | Sum
Base Plate (Layer 1) | Aluminum | 20 | lb | 8 | 160 | 24 | 4 | 0 | 8 | 0 | hours | 4716 | 1 | 4876 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 1) | Aluminum | 5 | lb | 8 | 40 | 8 | 2 | 0 | 0 | 0 | hours | 1250 | 1 | 1290 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 2 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 1) | Aluminum | 5 | lb | 8 | 40 | 16 | 0 | 0 | 2 | 0 | hours | 2332 | 1 | 2372 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 2 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mount Tooling (Layer 1) | Aluminum | 20 | lb | 8 | 160 | 24 | 8 | 0 | 8 | 0 | hours | 5184 | 1 | 5344 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 8 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Plate (Layer 2) | Aluminum | 10 | lb | 8 | 80 | 16 | 4 | 0 | 2 | 0 | hours | 2800 | 1 | 2880 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 4 | 0 | 2 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 2) | Aluminum | 5 | lb | 8 | 40 | 4 | 0 | 0 | 1 | 0 | hours | 658 | 1 | 698 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 0 | 0 | 1 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 2) | Aluminum | 5 | lb | 8 | 40 | 8 | 0 | 0 | 2 | 0 | hours | 1316 | 1 | 1356 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 0 | 0 | 2 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mount Tooling (Layer 2) | Aluminum | 5 | lb | 8 | 40 | 24 | 8 | 0 | 8 | 0 | hours | 5184 | 1 | 5224 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 8 | 0 | 8 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Plate (Layer 3) | Aluminum | 20 | lb | 8 | 160 | 24 | 4 | 0 | 8 | 0 | hours | 4716 | 1 | 4876 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 4 | 0 | 8 | 0 | 160
Caul Plate (Layer 3) | Aluminum | 5 | lb | 8 | 40 | 8 | 2 | 0 | 0 | 0 | hours | 1250 | 1 | 1290 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 2 | 0 | 0 | 0 | 40
Insert Location Plate (Layer 3) | Aluminum | 5 | lb | 8 | 40 | 16 | 0 | 0 | 2 | 0 | hours | 2332 | 1 | 2372 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 2 | 0 | 40
Stave Mount Tooling (Layer 3) | Aluminum | 20 | lb | 8 | 160 | 24 | 8 | 0 | 8 | 0 | hours | 5184 | 1 | 5344 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 8 | 0 | 8 | 0 | 160
Base Plate (Layer 4) | Aluminum | 40 | lb | 8 | 320 | 24 | 4 | 0 | 8 | 0 | hours | 4716 | 1 | 5036 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 4) | Aluminum | 10 | lb | 8 | 80 | 8 | 2 | 0 | 0 | 0 | hours | 1250 | 1 | 1330 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 2 | 0 | 0 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 4) | Aluminum | 5 | lb | 8 | 40 | 16 | 0 | 0 | 2 | 0 | hours | 2332 | 1 | 2372 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 2 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly | [10 empty] | Sum | 31738 | Sum
Layer 1 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 6976 | 4 | 6976 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 32 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 2 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 6976 | 4 | 6976 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 32 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 3 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 6976 | 4 | 6976 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 32 | 0 | 8 | 0 | 0
Layer 4 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 6976 | 4 | 6976 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 32 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 1 Stave Mounts | Batch | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 1 | 0 | hours | 4344 | 4 | 4344 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 32 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 2 Stave Mounts | Batch | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 1 | 0 | hours | 4344 | 4 | 4344 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 32 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 3 Stave Mounts | Batch | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 1 | 0 | hours | 4344 | 4 | 4344 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 4 | 0 | 0
Layer 1 Structure (contingency) | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 1 | 0 | hours | 1594 | 1 | 1594 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 8 | 0 | 1 | 0 | 0
Layer 2 Structure (contingency) | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 1 | 0 | hours | 1594 | 1 | 1594 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 8 | 0 | 1 | 0 | 0
Layer 4 Structure (contingency) | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 1744 | 1 | 1744 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 1 Stave Mounts (contingency) | Batch | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 1 | 0 | hours | 1086 | 1 | 1086 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 0
Layer 2 Stave Mounts (contingency) | Batch | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 1 | 0 | hours | 1086 | 1 | 1086 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 0
Parylene Coating (100% Production) | [10 empty] | Sum | 31360 | Sum
Batch | Order | 1 | Each | 300 | 300 | 0 | 4 | 0 | 0 | 0 | hours | 468 | 1 | 768 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 0 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Process/Shipping Container | Aluminum | 30 | Each | 8 | 240 | 8 | 8 | 0 | 0 | 0 | hours | 1952 | 1 | 2192 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 8 | 0 | 0 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping | Order | 1 | Each | 200 | 200 | 0 | 1 | 0 | 0 | 0 | hours | 117 | 1 | 317 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 200
Pixel Support Sub Total | [11 empty] | 98204 | Base Labor | [10 empty] | 428 | 244 | 0 | 102 | 0 |  | 7985 | 106189 |  | 41954 | 161 | 111 | 0 | 34 | 0 |  | 3420
Barrel Shell Components
Part Tooling
Half Shell
Welded Tube Assembly | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 24 | 0 | hours | 8680 | 1 | 9480 | B | PD | BPD2009 | [5 empty] | 2009 | 40 | 0 | 0 | 24 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Material CTE Study | Labor | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 16 | 0 | hours | 3844 | 1 | 3844 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 8 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 800 | 800 | 0 | 4 | 0 | 4 | 0 | hours | 1068 | 1 | 1868 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 4 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 0 | 0 | 24 | 0 | hours | 5632 | 1 | 5632 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 24 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 800 | 800 | 0 | 4 | 0 | 4 | 0 | hours | 1068 | 1 | 1868 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 800
Trim Fixture | Aluminum | 20 | lb | 8 | 160 | 24 | 0 | 0 | 24 | 0 | hours | 6648 | 1 | 6808 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 0 | 0 | 24 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Gusset Plate Tooling | [10 empty] | Sum | 20240 | Sum | 22000
Lamination Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 0 | 0 | 8 | 0 | hours | 3232 | 1 | 3552 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machining Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 0 | 0 | 8 | 0 | hours | 3232 | 1 | 3552 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Support Beam Tooling | [10 empty] | Sum | 6464 | Sum | 7104
Bottom Skin Tool | Aluminum | 20 | N/A | 8 | 160 | 16 | 4 | 0 | 8 | 0 | hours | 3700 | 1 | 3860 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 4 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Skin Tool | Aluminum | 30 | N/A | 8 | 240 | 24 | 4 | 0 | 16 | 0 | hours | 5916 | 1 | 6156 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 0 | 16 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Core Bond Tool | Aluminum | 20 | N/A | 8 | 160 | 24 | 4 | 0 | 16 | 0 | hours | 5916 | 1 | 6076 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 4 | 0 | 16 | 0 | 160
Machining Tool | Aluminum | 20 | N/A | 8 | 160 | 24 | 4 | 0 | 8 | 0 | hours | 4716 | 1 | 4876 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Transition Ring Tool | [10 empty] | Sum | 14332 | Sum | 10016
Lamination Tool | SS | 225 | lb | 12 | 2700 | 40 | 4 | 0 | 40 | 0 | hours | 11548 | 1 | 14248 | B | PD | BPD2009 | [5 empty] | 2009 | 40 | 4 | 0 | 40 | 0 | 2700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool Iteration | Labor | 0 | N/A | 0 | 0 | 24 | 4 | 8 | 24 | 0 | hours | 8132 | 1 | 8132 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 8 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool Iteration (Contingency) | Labor | 0 | N/A | 0 | 0 | 24 | 4 | 8 | 24 | 0 | hours | 8132 | 1 | 8132 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 4 | 8 | 24 | 0 | 0
Half Shell Production | [10 empty] | Sum | 19680 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 2136 | 1 | 2136 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Tube | Bagging | 12 | m^2 | 55 | 660 | 0 | 80 | 0 | 40 | 0 | hours | 15360 | 1 | 16020 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 80 | 0 | 40 | 0 | 660 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Tube | Bagging | 12 | m^2 | 55 | 660 | 0 | 60 | 0 | 8 | 0 | hours | 16440 | 2 | 17760 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 120 | 0 | 16 | 0 | 1320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Tube (Contingency) | Bagging | 12 | m^2 | 55 | 660 | 0 | 60 | 0 | 8 | 0 | hours | 8220 | 1 | 8880 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 60 | 0 | 8 | 0 | 660
Part Trim | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 3072 | 2 | 3072 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Trim (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 936 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 0
Gusset Plate Production | [10 empty] | Sum | 37008 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 4 | 0 | hours | 1068 | 1 | 1068 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Lamination | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 0 | 0 | hours | 1872 | 2 | 1982 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 0 | 0 | 110 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Lamination (contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 991 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 55
Part Machining | Labor | 0 | N/A | 0 | 0 | 16 | 0 | 0 | 2 | 0 | hours | 9328 | 4 | 9328 | B | PD | BPD2009 | [5 empty] | 2009 | 64 | 0 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Machining (Contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 0 | 0 | 0 | 0 | hours | 2032 | 1 | 2032 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0
Transition Ring Production | [10 empty] | Sum | 12268 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 8 | 0 | hours | 1668 | 1 | 1668 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Ring | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 8 | 0 | hours | 4272 | 2 | 4382 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 16 | 0 | 110 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Ring (contingency if re-tooled) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 8 | 8 | 0 | hours | 6304 | 2 | 6414 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 16 | 16 | 0 | 110
Production Ring | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 1 | 0 | hours | 4344 | 4 | 4564 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 32 | 0 | 4 | 0 | 220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Ring (Contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 1 | 0 | hours | 2172 | 2 | 2282 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 2 | 0 | 110
Support Beam Production | [10 empty] | Sum | 10284 | Sum
Base Laminate | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 2 | 0 | hours | 3072 | 4 | 3292 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Laminate (contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 0 | 0 | hours | 936 | 2 | 1046 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 110
Top Laminate | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 2 | 0 | hours | 3072 | 4 | 3292 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Laminate (contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 0 | 0 | hours | 936 | 2 | 1046 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 110
Core Bond | Bagging | 1 | m^2 | 55 | 55 | 4 | 4 | 0 | 2 | 0 | hours | 5104 | 4 | 5324 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 16 | 0 | 8 | 0 | 220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Core Bond (contingency) | Bagging | 1 | m^2 | 55 | 55 | 4 | 4 | 0 | 0 | 0 | hours | 1952 | 2 | 2062 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 8 | 0 | 0 | 0 | 110
Top Skin Bonding | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 4 | 0 | hours | 4272 | 4 | 4272 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Skin Bonding (contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 0 | 0 | hours | 936 | 2 | 936 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 0
Machined Assembly | Labor | 0 | N/A | 0 | 0 | 12 | 0 | 0 | 8 | 0 | hours | 10896 | 4 | 10896 | B | PD | BPD2009 | [5 empty] | 2009 | 48 | 0 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machined Assembly (contingency) | Labor | 0 | N/A | 0 | 0 | 12 | 0 | 0 | 0 | 0 | hours | 3048 | 2 | 3048 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0
Part Subtotal | [11 empty] | 83840 | Base Labor | [10 empty] | 356 | 392 | 8 | 364 | 0 |  | 8740 | 155432 |  | 51381 | 112 | 152 | 24 | 94 | 0 |  | 2225
[11 empty] | Sum | 26416 | Sum
Barrel Shell Assembly
Assembly Tooling | [12 empty] | 1
Base Plate | Aluminum | 100 | lb | 8 | 800 | 16 | 0 | 0 | 40 | 0 | hours | 8032 | 1 | 8832 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 40 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Arch Supports | Aluminum | 32 | lb | 8 | 256 | 20 | 0 | 0 | 0 | 0 | hours | 5080 | 2 | 5592 | B | PD | BPD2009 | [5 empty] | 2009 | 40 | 0 | 0 | 0 | 0 | 512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 2 | 0 | hours | 4124 | 1 | 4124 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 24 | 8 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Assembly | [10 empty] | Sum | 17236 | Sum
End Flange to Transition Ring Bond | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 3072 | 2 | 3072 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Support Beam bond | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 3072 | 2 | 3072 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Bond | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 3072 | 2 | 3072 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CMM Survey of Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 16 | 4 | 0 | hours | 6200 | 2 | 6200 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 32 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CMM Survey of Bonded Assembly with Pixel Mounts | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 16 | 4 | 0 | hours | 7136 | 2 | 7136 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 32 | 8 | 0 | 0
End Flange to Transition Ring Bond | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 1536 | 1 | 1536 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 4 | 0 | 0
Support Beam bond | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 1536 | 1 | 1536 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 4 | 0 | 0
Shell Bond | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 1536 | 1 | 1536 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 4 | 0 | 0
CMM Survey of Bonded Assembly | Contingency | 0 | N/A | 0 | 0 | 0 | 4 | 16 | 4 | 0 | hours | 3100 | 1 | 3100 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 16 | 4 | 0 | 0
CMM Survey of Bonded Assembly with Pixel Mounts | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 16 | 4 | 0 | hours | 3568 | 1 | 3568 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 16 | 4 | 0 | 0
Stave Assembly Subtotal | [11 empty] | 179344 | Base Labor | [10 empty] | 56 | 80 | 40 | 74 | 0 |  | 1312 | 33964 |  | 18412 | 0 | 52 | 64 | 28 | 0 |  | 0
[11 empty] | Sum | 32652 | Sum
Shipping (100% Production)
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 585 | 1 | 735 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 5 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 508 | 1 | 558 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 936 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 1500 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping Subtotal | [11 empty] | 2029 | Base Labor | [10 empty] | 4 | 13 | 0 | 0 | 0 |  | 1855 | 3884 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[22 empty] | 0 |  | 844 | 755 | 48 | 553.5 | 0 |  | 39174.5 |  |  |  | 273 | 341 | 88 | 163 | 0 |  | 13227.5
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost |  |  |  | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost
[29 empty] | Cost With Contingency | 447240 | 447240 |  | External Work Excluded…
[24 empty] | BASE | [9 empty] | CONTINGENCY
[23 empty] | Year | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[23 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2009 | 844 | 755 | 48 | 553.5 | 0 | 39174.5 |  |  |  | 2009 | 273 | 341 | 88 | 163 | 0 | 13227.5
[23 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Contingency
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[23 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2009 | 107188 | 88335 | 6096 | 83025 | 0 | 39174.5 | 323818.5 |  |  | 2009 | 34671 | 39897 | 11176 | 24450 | 0 | 13227.5 | 123421.5
[23 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 323818.5 | [8 empty] | Contingency | 123421.5
[39 empty] | Percent | 38.11%
[24 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPT | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Cost
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPT | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 0 | [8 empty] | Contingency | 0
[39 empty] | Percent | #DIV/0!
[24 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPD | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2009 | 844 | 755 | 48 | 553.5 | 0 | 39174.5 |  |  | CPD | 2009 | 273 | 341 | 88 | 163 | 0 | 13227.5
[17 empty] | BPD | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Cost
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPD | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2009 | 107188 | 88335 | 6096 | 83025 | 0 | 39174.5 | 323818.5 |  | CPD | 2009 | 34671 | 39897 | 11176 | 24450 | 0 | 13227.5 | 123421.5
[17 empty] | BPD | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 323818.5 | [8 empty] | Contingency | 123421.5
[39 empty] | Percent | 38.11%
[30 empty] | 323818.5 | checksum | [8 empty] | 123421.5 | checksum

## Rates
Shop | 127
CMM | 127
M_Tech | 117
Engineer | 150
Designer | 120
B
C