## SUMMARY
| BASE | [7 empty] | CONTINGENCY
Year | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 500 | 628 | 92 | 416 | 0 | 43492.5 |  | 2009 | 72 | 197 | 112 | 92 | 0 | 2225
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 174 | 0 | 0 | 0 | 0 | 5550 |  | Hytec | 31.6 | 0 | 0 | 0 | 0 | 804
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Contingency
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 63500 | 73476 | 11684 | 62400 | 0 | 43492.5 | 254552.5 | 2009 | 9144 | 23049 | 14224 | 13800 | 0 | 2225 | 62442
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 254552.5 | [6 empty] | Contingency | 62442
[14 empty] | Percent | 24.53%
| Pre-Production Base Cost | [7 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 0 | [6 empty] | Contingency | 0
[14 empty] | Percent | #DIV/0!
| Production Base Cost | [7 empty] | Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 500 | 628 | 92 | 416 | 0 | 43492.5 |  | 2009 | 72 | 197 | 112 | 92 | 0 | 2225
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 174 | 0 | 0 | 0 | 0 | 5550 |  | Hytec | 31.6 | 0 | 0 | 0 | 0 | 804
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 63500 | 73476 | 11684 | 62400 | 0 | 43492.5 | 254552.5 | 2009 | 9144 | 23049 | 14224 | 13800 | 0 | 2225 | 62442
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 254552.5 | [6 empty] | Contingency | 62442
[14 empty] | Percent | 24.53%

## Pre- and Production
Barrel Support Estimate | [14 empty] | TRACKING | [8 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | CMM | Eng Time | Des Time | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals
Material Batches | [21 empty] | Underage(-)
Thicker M55J | M55J | 1 | Order | 10000 | 10000 | 0 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 55 | 27.5 | 0 | 8 | 0 | 1 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cloth CN60 | CN60 | 1 | Order | 21000 | 21000 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 22200 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 8 | 0 | 21000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency | N/A | 0 | N/A | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 234 | 1 | 234 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 2 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 55 | 27.5 | 0 | 8 | 0 | 1 | 0 | hours | 3258 | 3 | 3340.5 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 24 | 0 | 3 | 0 | 82.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test | N/A | 1 | Order | 1500 | 1500 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 2700 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 8 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Carbon Foam Core | Allcomp Densified | 2 | bdft | 600 | 1200 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 2400 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 8 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Pre-Production | Hysol 9320 | 1 | Order | 500 | 500 | 0 | 0 | 0 | 0.5 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Batch | Hysol 9320 | 1 | Order | 500 | 500 | 0 | 0 | 0 | 1 | 0 | hours | 150 | 1 | 650 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 1 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables | Bagging | 1 | Order | 5000 | 5000 | 0 | 0 | 0 | 4 | 0 | hours | 600 | 1 | 5600 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 4 | 0 | 5000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Material Batches Subtotal | [11 empty] | 7842 | Base Labor | [10 empty] | 0 | 26 | 0 | 32 | 0 |  | 29282.5 | 37124.5 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Layer Support Assemblies (and dummy)
Plate (for all parts + spares) | [12 empty] | 1
Plate Lamination | Bagging | 1 | m^2 | 55 | 55 | 0 | 6 | 0 | 0 | 0 | hours | 2106 | 3 | 2271 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 18 | 0 | 0 | 0 | 165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim to Size (cuts all face sheets, both styles) | Batch | 0 | Waterjet | 80 | 0 | 16 | 4 | 0 | 4 | 0 | hours | 3100 | 1 | 3100 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 4 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Core | [12 empty] | 1
Rough thickness core | Batch | 0 | N/A | 0 | 0 | 32 | 8 | 0 | 1 | 0 | hours | 5150 | 1 | 5150 | B | PD | BPD2009 | [5 empty] | 2009 | 32 | 8 | 0 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim to shape (all styles) | Batch | 3 | Cutter | 80 | 240 | 16 | 8 | 0 | 2 | 0 | hours | 3268 | 1 | 3508 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 8 | 0 | 2 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface Parts | [12 empty] | 1
Inserts | CF PEEK | 0.03 | lb | 600 | 18 | 0.8 | 0 | 0 | 0 | 0 | hours | 5080 | 50 | 5980 | B | PD | BPDHytec | [5 empty] | Hytec | 40 | 0 | 0 | 0 | 0 | 900 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Inserts (LBNL Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 1200 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Inserts (contingency) | CF PEEK | 0.03 | lb | 600 | 18 | 0.8 | 0 | 0 | 0 | 0 | hours | 1219.2 | 12 | 1435.2 | C | PD | CPDHytec | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 9.6 | 0 | 0 | 0 | 0 | 216
Stave Mounts | CF PEEK | 0.08 | lb | 600 | 48 | 1 | 0 | 0 | 0 | 0 | hours | 10160 | 80 | 14000 | B | PD | BPDHytec | [5 empty] | Hytec | 80 | 0 | 0 | 0 | 0 | 3840 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mounts (LBNL Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 1200 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mounts (Contingency) | CF PEEK | 0.08 | lb | 600 | 48 | 1 | 0 | 0 | 0 | 0 | hours | 1270 | 10 | 1750 | C | PD | CPDHytec | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 10 | 0 | 0 | 0 | 0 | 480
Tooling | [10 empty] | Sum | 17640 | Sum
Base Plate (Layer 1) | Aluminum | 20 | lb | 8 | 160 | 24 | 4 | 0 | 8 | 0 | hours | 4716 | 1 | 4876 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 1) | Aluminum | 5 | lb | 8 | 40 | 8 | 2 | 0 | 0 | 0 | hours | 1250 | 1 | 1290 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 2 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 1) | Aluminum | 5 | lb | 8 | 40 | 16 | 0 | 0 | 8 | 0 | hours | 3232 | 1 | 3272 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 8 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mount Tooling (Layer 1) | Aluminum | 20 | lb | 8 | 160 | 24 | 8 | 0 | 8 | 0 | hours | 5184 | 1 | 5344 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 8 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Plate (Layer 2) | Aluminum | 10 | lb | 8 | 80 | 16 | 4 | 0 | 8 | 0 | hours | 3700 | 1 | 3780 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 4 | 0 | 8 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 2) | Aluminum | 5 | lb | 8 | 40 | 4 | 0 | 0 | 1 | 0 | hours | 658 | 1 | 698 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 0 | 0 | 1 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 2) | Aluminum | 5 | lb | 8 | 40 | 8 | 0 | 0 | 8 | 0 | hours | 2216 | 1 | 2256 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 0 | 0 | 8 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mount Tooling (Layer 2) | Aluminum | 5 | lb | 8 | 40 | 24 | 8 | 0 | 8 | 0 | hours | 5184 | 1 | 5224 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 8 | 0 | 8 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Plate (Layer 3) | Aluminum | 20 | lb | 8 | 160 | 24 | 4 | 0 | 8 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 3) | Aluminum | 5 | lb | 8 | 40 | 8 | 2 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 3) | Aluminum | 5 | lb | 8 | 40 | 16 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Mount Tooling (Layer 3) | Aluminum | 20 | lb | 8 | 160 | 24 | 8 | 0 | 8 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Plate (Layer 4) | Aluminum | 40 | lb | 8 | 320 | 24 | 4 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Caul Plate (Layer 4) | Aluminum | 10 | lb | 8 | 80 | 8 | 2 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insert Location Plate (Layer 4) | Aluminum | 5 | lb | 8 | 40 | 16 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly | [10 empty] | Sum | 26140 | Sum
Layer 1 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 10 | 0 | 2 | 0 | hours | 7912 | 4 | 7912 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 40 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 2 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 10 | 0 | 2 | 0 | hours | 7912 | 4 | 7912 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 40 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 3 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 4 Structure | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 1 Stave Mounts | Batch | 0 | N/A | 0 | 0 | 0 | 10 | 0 | 2 | 0 | hours | 5880 | 4 | 5880 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 40 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 2 Stave Mounts | Batch | 0 | N/A | 0 | 0 | 0 | 10 | 0 | 2 | 0 | hours | 5880 | 4 | 5880 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 40 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 3 Stave Mounts | Batch | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 1 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 1 Structure (contingency) | Batch | 0 | N/A | 0 | 0 | 4 | 12 | 0 | 2 | 0 | hours | 2212 | 1 | 2212 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 12 | 0 | 2 | 0 | 0
Layer 2 Structure (contingency) | Batch | 0 | N/A | 0 | 0 | 4 | 12 | 0 | 2 | 0 | hours | 2212 | 1 | 2212 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 12 | 0 | 2 | 0 | 0
Layer 4 Structure (contingency) | Batch | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layer 1 Stave Mounts (contingency) | Batch | 0 | N/A | 0 | 0 | 0 | 12 | 0 | 2 | 0 | hours | 1704 | 1 | 1704 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 12 | 0 | 2 | 0 | 0
Layer 2 Stave Mounts (contingency) | Batch | 0 | N/A | 0 | 0 | 0 | 12 | 0 | 2 | 0 | hours | 1704 | 1 | 1704 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 12 | 0 | 2 | 0 | 0
Parylene Coating (100% Production) | [10 empty] | Sum | 27584 | Sum
Batch | Order | 1 | Each | 300 | 300 | 0 | 4 | 0 | 0 | 0 | hours | 468 | 1 | 768 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 0 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Process/Shipping Container | Aluminum | 30 | Each | 8 | 240 | 8 | 8 | 0 | 0 | 0 | hours | 1952 | 1 | 2192 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 8 | 0 | 0 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping | Order | 1 | Each | 200 | 200 | 0 | 1 | 0 | 0 | 0 | hours | 117 | 1 | 317 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 200
Pixel Support Sub Total | [11 empty] | 87408 | Base Labor | [10 empty] | 348 | 236 | 0 | 104 | 0 |  | 6285 | 93693 |  | 11334.2 | 27.6 | 49 | 0 | 8 | 0 |  | 896
Barrel Shell Components
Part Tooling
Half Shell
Welded Tube Assembly | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 8 | 0 | hours | 6280 | 1 | 7080 | B | PD | BPD2009 | [5 empty] | 2009 | 40 | 0 | 0 | 8 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Material CTE Study | Labor | 0 | N/A | 0 | 0 | 4 | 8 | 0 | 16 | 0 | hours | 3844 | 1 | 3844 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 8 | 0 | 16 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 4 | 0 | hours | 1108 | 1 | 2308 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 0 | 0 | 4 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 24 | 0 | 0 | 24 | 0 | hours | 6648 | 1 | 6648 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 0 | 0 | 24 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 4 | 0 | hours | 1108 | 1 | 2308 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 4 | 0 | 1200
Trim Fixture | Aluminum | 20 | lb | 8 | 160 | 24 | 0 | 0 | 24 | 0 | hours | 6648 | 1 | 6808 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 0 | 0 | 24 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Gusset Plate Tooling | [10 empty] | Sum | 14036 | Sum | 16196
Lamination Tool | Aluminum | 40 | lb | 8 | 320 | 0 | 8 | 0 | 8 | 0 | hours | 2136 | 1 | 2456 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machining Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 0 | 0 | 8 | 0 | hours | 3232 | 1 | 3552 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Support Beam Tooling | [10 empty] | Sum | 5368 | Sum | 6008
Bottom Skin Tool | Aluminum | 20 | N/A | 8 | 160 | 16 | 4 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Skin Tool | Aluminum | 30 | N/A | 8 | 240 | 24 | 4 | 0 | 16 | 0 | hours | 5916 | 1 | 6156 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 4 | 0 | 16 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Core Bond Tool | Aluminum | 20 | N/A | 8 | 160 | 24 | 4 | 0 | 16 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machining Tool | Aluminum | 20 | N/A | 8 | 160 | 24 | 4 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Transition Ring Temp Layer 4 Support Tool | [10 empty] | Sum | 5916 | Sum | 6156
Lamination Tool | Aluminum | 120 | lb | 8 | 960 | 4 | 8 | 0 | 0 | 0 | hours | 1444 | 1 | 2404 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 8 | 0 | 0 | 0 | 960 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool Iteration | Labor | 0 | N/A | 0 | 0 | 24 | 4 | 8 | 24 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool Iteration (Contingency) | Labor | 0 | N/A | 0 | 0 | 24 | 4 | 8 | 24 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface Parts (Shell to Layer 4) | [10 empty] | Sum | 1444 | Sum
Shell To Layer 4 mounts | CF PEEK | 0.05 | lb | 600 | 30 | 2 | 0 | 0 | 0 | 0 | hours | 6858 | 27 | 7668 | B | PD | BPDHytec | [5 empty] | Hytec | 54 | 0 | 0 | 0 | 0 | 810 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(LBNL Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 1200 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mounts (contingency) | CF PEEK | 0.03 | lb | 600 | 18 | 2 | 0 | 0 | 0 | 0 | hours | 1524 | 6 | 1632 | C | PD | CPDHytec | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 12 | 0 | 0 | 0 | 0 | 108
Half Shell Production | [10 empty] | Sum | 8058 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 2136 | 1 | 2136 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Half Shell | Bagging | 6 | m^2 | 55 | 330 | 0 | 32 | 0 | 40 | 0 | hours | 9744 | 1 | 10074 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 32 | 0 | 40 | 0 | 330 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Half Shell | Bagging | 6 | m^2 | 55 | 330 | 0 | 32 | 0 | 8 | 0 | hours | 9888 | 2 | 10548 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 64 | 0 | 16 | 0 | 660 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Half Shell (Contingency) | Bagging | 12 | m^2 | 55 | 660 | 0 | 32 | 0 | 8 | 0 | hours | 4944 | 1 | 5604 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 8 | 0 | 660
Part Trim (Cutouts) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 3072 | 2 | 3072 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Trim (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 936 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 0
Gusset Plate Production | [10 empty] | Sum | 24840 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 4 | 0 | hours | 1068 | 1 | 1068 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Lamination | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 0 | 0 | hours | 1872 | 2 | 1982 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 0 | 0 | 110 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Lamination (contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 991 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 55
Part Machining | Labor | 0 | N/A | 0 | 0 | 12 | 0 | 0 | 2 | 0 | hours | 7296 | 4 | 7296 | B | PD | BPD2009 | [5 empty] | 2009 | 48 | 0 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Machining (Contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 0 | 0 | 2 | 0 | hours | 2332 | 1 | 2332 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 2 | 0 | 0
Transition Ring Temp Support Production | [10 empty] | Sum | 10236 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 8 | 0 | hours | 1668 | 1 | 1668 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 4 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Support | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 8 | 0 | hours | 2136 | 1 | 2191 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 8 | 0 | 55 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Ring (contingency if re-tooled) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 8 | 8 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Support | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 2 | 0 | hours | 4944 | 4 | 5164 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 32 | 0 | 8 | 0 | 220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Support (Contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 2 | 0 | hours | 1236 | 1 | 1291 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 2 | 0 | 55
Support Beam Production | [10 empty] | Sum | 8748 | Sum
Base Laminate | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Base Laminate (contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Laminate | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 2 | 0 | hours | 4944 | 4 | 5164 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 32 | 0 | 8 | 0 | 220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Laminate (contingency) | Bagging | 1 | m^2 | 55 | 55 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 991 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 55
Core Bond | Bagging | 1 | m^2 | 55 | 55 | 4 | 4 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Core Bond (contingency) | Bagging | 1 | m^2 | 55 | 55 | 4 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Skin Bonding | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 4 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Top Skin Bonding (contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machined Assembly | Labor | 0 | N/A | 0 | 0 | 10 | 0 | 0 | 4 | 0 | hours | 7480 | 4 | 7480 | B | PD | BPD2009 | [5 empty] | 2009 | 40 | 0 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machined Assembly (contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 0 | 0 | 4 | 0 | hours | 2632 | 1 | 2632 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 4 | 0 | 0
Part Subtotal | [11 empty] | 54112 | Base Labor | [10 empty] | 254 | 236 | 0 | 208 | 0 |  | 6405 | 97475 |  | 29209 | 76 | 72 | 0 | 60 | 0 |  | 2133
[11 empty] | Sum | 12424 | Sum
Barrel Shell Assembly
Assembly Tooling | [12 empty] | 1
Base Plate | Aluminum | 200 | lb | 12 | 2400 | 16 | 0 | 0 | 0 | 0 | hours | 2032 | 1 | 4432 | B | PD | BPD2009 | [5 empty] | 2009 | 16 | 0 | 0 | 0 | 0 | 2400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Arch Supports | Aluminum | 60 | lb | 8 | 480 | 24 | 0 | 0 | 0 | 0 | hours | 6096 | 2 | 7056 | B | PD | BPD2009 | [5 empty] | 2009 | 48 | 0 | 0 | 0 | 0 | 960 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Inserts (LBNL Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 12 | 8 | 0 | hours | 5532 | 1 | 5532 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 24 | 12 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Assembly | [10 empty] | Sum | 19660 | Sum
End Flange to Transition Ring Bond | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Support Beam bond | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Bond | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 8 | 0 | hours | 9888 | 2 | 9888 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 64 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CMM Survey of Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 40 | 4 | 0 | hours | 13232 | 2 | 13232 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 80 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CMM Survey of Bonded Assembly with Pixel Mounts | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 40 | 4 | 0 | hours | 15104 | 2 | 15104 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 80 | 8 | 0 | 0
End Flange to Transition Ring Bond | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Support Beam bond | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Bond | Contingency | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 8 | 0 | hours | 4944 | 1 | 4944 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 8 | 0 | 0
CMM Survey of Bonded Assembly | Contingency | 0 | N/A | 0 | 0 | 0 | 4 | 16 | 4 | 0 | hours | 3100 | 1 | 3100 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 16 | 4 | 0 | 0
CMM Survey of Bonded Assembly with Pixel Mounts | Contingency | 0 | N/A | 0 | 0 | 0 | 8 | 16 | 4 | 0 | hours | 3568 | 1 | 3568 | C | PD | CPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 16 | 4 | 0 | 0
Space Frame Assembly Subtotal | [11 empty] | 133850 | Base Labor | [10 empty] | 64 | 104 | 92 | 72 | 0 |  | 3360 | 46140 |  | 26716 | 0 | 76 | 112 | 24 | 0 |  | 0
[11 empty] | Sum | 42780 | Sum
Shipping (100% Production)
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 80 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 200 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 30 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 1170 | 2 | 2640 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 10 | 0 | 0 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 1016 | 2 | 2132 | B | PD | BPD2009 | [5 empty] | 2009 | 8 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 1872 | 2 | 3744 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 16 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 3000 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 3000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping Subtotal | [11 empty] | 4058 | Base Labor | [10 empty] | 8 | 26 | 0 | 0 | 0 |  | 3710 | 7768 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[22 empty] | 0 |  | 674 | 628 | 92 | 416 | 0 |  | 49042.5 |  |  |  | 103.6 | 197 | 112 | 92 | 0 |  | 3029
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost |  |  |  | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost
[29 empty] | Cost With Contingency | 349459.7 | 316994.5 |  | External Work Excluded…
[24 empty] | BASE | [9 empty] | CONTINGENCY
[23 empty] | Year | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[23 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2009 | 500 | 628 | 92 | 416 | 0 | 43492.5 |  |  |  | 2009 | 72 | 197 | 112 | 92 | 0 | 2225
[23 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | Hytec | 174 | 0 | 0 | 0 | 0 | 5550 |  |  |  | Hytec | 31.6 | 0 | 0 | 0 | 0 | 804
[23 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Contingency
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[23 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2009 | 63500 | 73476 | 11684 | 62400 | 0 | 43492.5 | 254552.5 |  |  | 2009 | 9144 | 23049 | 14224 | 13800 | 0 | 2225 | 62442
[23 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 254552.5 | [8 empty] | Contingency | 62442
[39 empty] | Percent | 24.53%
[24 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPT | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Cost
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPT | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 0 | [8 empty] | Contingency | 0
[39 empty] | Percent | #DIV/0!
[24 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPD | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2009 | 500 | 628 | 92 | 416 | 0 | 43492.5 |  |  | CPD | 2009 | 72 | 197 | 112 | 92 | 0 | 2225
[17 empty] | BPD | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | Hytec | 174 | 0 | 0 | 0 | 0 | 5550 |  |  | CPD | Hytec | 31.6 | 0 | 0 | 0 | 0 | 804
[17 empty] | BPD | [5 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Cost
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPD | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2009 | 63500 | 73476 | 11684 | 62400 | 0 | 43492.5 | 254552.5 |  | CPD | 2009 | 9144 | 23049 | 14224 | 13800 | 0 | 2225 | 62442
[17 empty] | BPD | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 254552.5 | [8 empty] | Contingency | 62442
[39 empty] | Percent | 24.53%
[30 empty] | 254552.5 | checksum | [8 empty] | 62442 | checksum

## Rates
|  |  | English | Metric | Quoted |  | Metric
Shop | 127 | Material | lb/in^3 | g/cc | Cost/Unit | Unit | Cost/Unit | Unit
CMM | 127 | Aluminum | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
M_Tech | 117 | MIC-6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
Engineer | 150 | 6061-T6 | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
Designer | 120 | 7075-T6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
|  | Titanium | 0.198 | 5.4855 | 15 | $/lb | 0.030992 | $/g
|  | 6Al4V | 0.198 | 5.4855 | 20 | $/lb | 0.041322 | $/g
|  | Steel | 0.298 | 8.256 | 3 | $/lb | 0.0061983 | $/g
|  | 304SS | 0.298 | 8.256 | 15 | $/lb | 0.030992 | $/g
|  | Carbon Fiber | 0.065 | 1.8008 | 100 | $/lb | 0.20661 | $/g
|  | M55J-UDT | 0.065 | 1.8008 | 800 | $/lb | 1.6529 | $/g
B |  | CN60-PW | 0.065 | 1.8008 | 500 | $/lb | 1.0331 | $/g
C |  | YSH80A-UDT | 0.065 | 1.8008 | 1200 | $/lb | 2.4793 | $/g
|  | Adhesive | 0.055 | 1.5238 | 400 | $/qt | 0.42283 | $/cc
|  | EA9396 | 0.055 | 1.5238 | 350 | $/qt | 0.36998 | $/cc
|  | EA9394 | 0.075 | 2.0779 | 450 | $/qt | 0.47569 | $/cc
|  | CF HoneyComb | 0.0017361 | 0.048099 | 600 | $/bdft | 0.25424 | $/cc
|  | Al HoneyComb | 0.0017361 | 0.048099 | 75 | $/bdft | 0.03178 | $/cc
|  | Nomex HC | 0.0023148 | 0.064131 | 100 | $/bdft | 0.042373 | $/cc
|  | PEEK | 0.055 | 1.5238 | 400 | $/lb | 0.82645 | $/g
|  | CF PEEK | 0.055 | 1.5238 | 600 | $/lb | 1.2397 | $/g

## Material Estimates
Material Estimates per component |  |  | Values used to estimate Size/Cost of Batch Orders--Does not report to Cost Summary
Item | Material | Descriptor | Quantity | CPT (microns) | Density (g/cc) | Finished Form | % Waste | Length (cm) | Diameter/Width (cm) | Thickness (cm) | Volume (cc) | Mass (g) | Pre-Preg Area (m^2) | Cost Per Unit | Choose Unit | Cost | Prototype Mass | Prototype Area | Prototype Composites
VTX Support Spaceframe | [19 empty] | /cc | Bulk | 1
Half Shell | [19 empty] | /g | Plate | 2
Tooling | [19 empty] | /m^2 | Round | 3
Mandrel | Steel | Pipe | 1 | n/a | 8.3 | Shell | 0% | 57 | 42 | 2 | 15041.9456 | 124848.1487 | #VALUE! | 0.006 | /g | 749.0889 | 0 | 0 | 0 |  | Shell | 4
Mandrel End Plates | Steel | Plate | 2 | n/a | 8.3 | Plate | 0% | 45 | 45 | 2 | 8100 | 67230 | #VALUE! | 0.006 | /g | 403.38 | 0 | 0 | 0
Shell
Shell Laminate | CN60 Cloth | Laminate | 1.5 | 330 | 1.8 | Shell | 30% | 40 | 42 | 0.16 | 1646.6972 | 2964.055 | 4.99 | 1.033 | /g | 3061.8688 | 0 | 0 | 0
Test Shell Laminate | CN60 Cloth | Test | 0.5 | 330 | 1.8 | Shell | 30% | 40 | 42 | 0.16 | 548.8991 | 988.0183 | 1.6633 | 1.033 | /g | 1020.6229 | 988.0183 | 1.6633 | 1020.6229
Support Beams
Tooling
Support Beam Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 100 | 15 | 4 | 6000 | 16200 | #VALUE! | 0.017 | /g | 275.4 | 0 | 0 | 0
Support Beam Machining Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 100 | 15 | 4 | 6000 | 16200 | #VALUE! | 0.017 | /g | 275.4 | 0 | 0 | 0
Components
Thick Laminate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Plate | 30% | 80 | 2.5 | 0.8 | 1040 | 1872 | 3.1515 | 1.033 | /g | 1933.776 | 0 | 0 | 0
Thick Laminate Test | CN60 Cloth | Test | 2 | 330 | 1.8 | Plate | 50% | 20 | 3 | 0.8 | 144 | 259.2 | 0.43636 | 1.033 | /g | 267.7536 | 259.2 | 0.43636 | 267.7536
End Flange
Tooling
Machine Fixturing | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 45 | 22 | 2 | 1980 | 5346 | #VALUE! | 0.017 | /g | 90.882 | 0 | 0 | 0
Lamination Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 45 | 22 | 2 | 1980 | 5346 | #VALUE! | 0.017 | /g | 90.882 | 0 | 0 | 0
Components
Half Plate Laminate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Shell | 60% | 0.3 | 35 | 7 | 1847.2565 | 3325.0617 | 5.5977 | 1.033 | /g | 3434.7887 | 0 | 0 | 0
Test Lamiante | CN60 Cloth | Test | 1 | 330 | 1.8 | Shell | 60% | 0.3 | 35 | 7 | 369.4513 | 665.0123 | 1.1195 | 1.033 | /g | 686.9577 | 665.0123 | 1.1195 | 686.9577
Gusset Plate
Tooling
Machine Fixturing | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 70 | 22 | 2 | 3080 | 8316 | #VALUE! | 0.017 | /g | 141.372 | 0 | 0 | 0
Lamination Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 70 | 22 | 2 | 3080 | 8316 | #VALUE! | 0.017 | /g | 141.372 | 0 | 0 | 0
Components
Gusset Plate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Shell | 30% | 39 | 16 | 0.396 | 5045.9507 | 9082.7113 | 15.2908 | 1.033 | /g | 9382.4408 | 0 | 0 | 0
Material Acceptance
CN60 Cloth
12" Test Panels | CN60 Cloth | Test | 5 | 330 | 1.8 | Plate | 30% | 30 | 30 | 0.1 | 585 | 1053 | 1.7727 | 1.033 | /g | 1087.749 | 1053 | 1.7727 | 1087.749
Assembly
Tooling
Bond Tool Base | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 110 | 57 | 5 | 31350 | 84645 | #VALUE! | 0.034 | /g | 2877.93 | 0 | 0 | 0
Bond Tool Arches | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 0% | 22 | 44 | 5 | 9680 | 26136 | #VALUE! | 0.017 | /g | 444.312 | 0 | 0 | 0
Survey/QA jig | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 110 | 57 | 2.5 | 15675 | 42322.5 | #VALUE! | 0.017 | /g | 719.4825 | 0 | 0 | 0
Components
Mount Blocks | CF PEEK | Blocks | 30 | n/a | 1.52 | Plate | 0% | 3 | 2 | 2 | 360 | 547.2 | #VALUE! | 1.24 | /g | 678.528 | 0 | 0 | 0
[15 empty] | Total | 27763.9869
|  | Mass (kg) | Area (m^2) | Cost
| Test Atticles | 6.5313 | 4.992 | 3063.0833
| Production | 37.982 | 29.03 | 17812.8743
| CN60 Cloth | 44.5133 | 34.022 | 20875.9575 | Total | 613.602
|  | Volume (cc) | Quarts | Cost
| EA9396 | 0 | 0 | 0
|  | Mass (kg) |  | Cost
| Aluminum | 468.783 |  | 5057.0325