## Barrel Mounts
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | ETC |  | Totals |  | Liens
WBS Barrel Mounts | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
4.2.2 Tooling |  |  | 1320 |  | 0 |  | 0 |  | 1320 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1320 | 25680
Eng | 110 | 117.7 |  | 0 | 0 | 0 | 0 | 12 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 78 | 82.68 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 10000
4.2.3 Fabrication |  |  | 3340 |  | 0 |  | 0 |  | 3340 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3340 | 43660
Eng | 110 | 117.7 |  | 0 | 0 | 0 | 0 | 2 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 78 | 82.68 |  | 0 | 0 | 0 | 0 | 40 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4.2.4 Material |  |  | 493 |  | 0 |  | 125 |  | 368 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 493 | 3507
Eng | 110 | 117.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 78 | 82.68 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 125 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 5153 |  | 0 |  | 125 |  | 5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5153 | 72847
|  |  | Budget |  | Percent Completion based on hours worked
4.2.2 Tooling |  |  | 27000 |  | 0%
4.2.3 Fabrication |  |  | 47000 |  | 0%
4.2.4 Material |  |  | 4000 |  | 0%
|  |  | 78000 | w/o Contingency
Progress as of end of Current Month
4.2.2 Tooling |  |  |  |  | Models complete for tooling. Ready to begin drawing process. 72 hour spent on engineering sub contract to develop models (part of Lien)--will be billed next month. $35k appears as lien on this account--will be split with 5.2.2
4.2.3 Fabrication |  |  |  |  | Have fabricated all M55J panels required to build Panel Assemblies.
4.2.4 Material |  |  |  |  | Carbon Foam for core materials is in hand. Will appear on next month's billing cycle.

## Space Frame
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | ETC |  | Totals |  | Liens
WBS Barrel Supports | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
5.2.2 Tooling |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 31000
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 25000
5.2.3 Fabrication |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 117000
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5.2.4 Material |  |  | 970 |  | 970 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 970 | 36530
Eng | 121.25 | 129.7375 |  | 8 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 24693
Totals |  |  | 970 |  | 970 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 970 | 184530
|  |  | Budget |  | Percent Completion based on hours worked
5.2.2 Tooling |  |  | 31000 |  | 0%
5.2.3 Fabrication |  |  | 117000 |  | 0%
5.2.4 Material |  |  | 37500 |  | 0% | [11 empty] | 100% |  | 100% |  | 100%
|  |  | 185500 | w/o Contingency
Progress as of end of Current Month
5.2.2 Tooling |  |  |  |  | Lien for $35k appears in 4.2.2. Will split ~$25k to this account for tracking purposes. No work started on this
5.2.3 Fabrication
5.2.4 Material |  |  |  |  | Material ordered, expect in May--will be billed after reciept. Appears as Lien in reports.