## Barrel Mounts
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | ETC |  | Totals |  | Liens
WBS Barrel Mounts | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
4.2.2 Tooling |  |  | 11565 |  | 0 |  | 0 |  | 1455 |  | 1940 |  | 8170 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11565 | 15435
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 12 | 1455 | 16 | 1940 | 8 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 7200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4.2.3 Fabrication |  |  | 18907.5 |  | 0 |  | 0 |  | 3922.5 |  | 6539 |  | 8446 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18907.5 | 28092.5
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 2 | 242.5 | 4 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 40 | 3680 | 24.5 | 2254 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 3800 |  | 3496 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4.2.4 Material |  |  | 6285 |  | 0 |  | 125 |  | 368 |  | 1068 |  | 4724 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6285 | -2285
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 4324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 125 | 0 | 368 | 0 | 0 | 4 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 1068 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 36757.5 |  | 0 |  | 125 |  | 5745.5 | 44.5 | 9547 | 108.5 | 21340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36757.5 | 41242.5
|  |  | Budget |  | Percent Completion based on hours worked
4.2.2 Tooling |  |  | 27000 |  | 0%
4.2.3 Fabrication |  |  | 47000 |  | 0%
4.2.4 Material |  |  | 4000 |  | 0%
|  |  | 78000 | w/o Contingency
Progress as of end of Current Month
4.2.2 Tooling |  |  |  |  | Billing for Engineering labor of April and May appears in this mont as a 'Procurement'. Design work is complete on tooling for barrel mounts. Fabrication remains
4.2.3 Fabrication |  |  |  |  | Production of all CF PEEK parts is concluded.
4.2.4 Material |  |  |  |  | CN60 Material Arrived. Test panels have been fabricated. Labor split between accoun 5.2.4, but material cost on 5.2.4. will split if desired. Rodne Post mis-charged 47hrs to RFNX424, will move next month or August depending on close of July to RFNX423.

## Space Frame
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | ETC |  | Totals |  | Liens
WBS Barrel Supports | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
5.2.2 Tooling |  |  | 184 |  | 0 |  | 0 |  | 0 |  | 0 |  | 184 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 184 | 30816
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 25000
5.2.3 Fabrication |  |  | 368 |  | 0 |  | 0 |  | 0 |  | 368 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 368 | 116632
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 368 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5.2.4 Material |  |  | 32654 |  | 970 |  | 0 |  | 0 |  | 0 |  | 31684 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 32654 | 4846
Eng | 121.25 | 129.7375 |  | 8 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 31500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 24693
Totals |  |  | 33206 |  | 970 |  | 0 |  | 0 | 0 | 368 | 4 | 31868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33206 | 152294
|  |  | Budget |  | Percent Completion based on hours worked
5.2.2 Tooling |  |  | 31000 |  | 0%
5.2.3 Fabrication |  |  | 117000 |  | 0%
5.2.4 Material |  |  | 37500 |  | 0% | [11 empty] | 100% |  | 100% |  | 100%
|  |  | 185500 | w/o Contingency
Progress as of end of Current Month
5.2.2 Tooling |  |  |  |  | Tom Johnson Mischarged to RFNX522--will likely re-map to RFNX422 or RFNX524.
5.2.3 Fabrication
5.2.4 Material |  |  |  |  | Material arrived in June. All charged to RFNX524, labor is for construction of Test Panel. Contract for material test issued, but not yet charged.

## R292A Summary
|  |  | February | March | April | May | June | July | August | September | October | November | December
WBS Barrel Mounts | Budget | YTD | Cost | Cost | Cost | Cost | Cost | Cost | Cost | Cost | Cost | HRS | Cost | EST | Reserve
4.2.2 Tooling | 27000 | 11565 | 0 | 0 | 1455 | 1940 | 8170 | 0 | 0 | 0 | 0 | 0 | 0 | 11565 | 15435
4.2.3 Fabrication | 47000 | 18907.5 | 0 | 0 | 3922.5 | 6539 | 8446 | 0 | 0 | 0 | 0 | 0 | 0 | 18907.5 | 28092.5
4.2.4 Material | 4000 | 6285 | 0 | 125 | 368 | 1068 | 4724 | 0 | 0 | 0 | 0 | 0 | 0 | 6285 | -2285
Totals | 78000 | 36757.5 | 0 | 125 | 5745.5 | 9547 | 21340 | 0 | 0 | 0 | 0 | 0 | 0 | 36757.5 | 41242.5
WBS Barrel Supports | Budget | YTD | Cost | Cost | Cost | Cost | Cost | Cost | Cost | Cost | Cost | HRS | Cost | EST | Reserve
5.2.2 Tooling | 31000 | 184 | 0 | 0 | 0 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 30816
5.2.3 Fabrication | 117000 | 368 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 116632
5.2.4 Material | 37500 | 32654 | 970 | 0 | 0 | 0 | 31684 | 0 | 0 | 0 | 0 | 0 | 0 | 32654 | 4846
Totals | 185500 | 33206 | 970 | 0 | 0 | 368 | 31868 | 0 | 0 | 0 | 0 | 0 | 0 | 33206 | 152294
R292A Total |  |  | 970 | 125 | 5745.5 | 9915 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 69963.5 | 193536.5