## Barrel Mounts
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | ETC |  | Totals |  | Liens
WBS Barrel Mounts | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
4.2.2 Tooling |  |  | 3395 |  | 0 |  | 0 |  | 1455 |  | 1940 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3395 | 23605
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 12 | 1455 | 16 | 1940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 10000
4.2.3 Fabrication |  |  | 10461.5 |  | 0 |  | 0 |  | 3922.5 |  | 6539 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10461.5 | 36538.5
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 2 | 242.5 | 4 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 40 | 3680 | 24.5 | 2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 3800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4.2.4 Material |  |  | 1561 |  | 0 |  | 125 |  | 368 |  | 1068 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1561 | 2439
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 125 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 1068 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 15417.5 |  | 0 |  | 125 |  | 5745.5 | 44.5 | 9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15417.5 | 62582.5
|  |  | Budget |  | Percent Completion based on hours worked
4.2.2 Tooling |  |  | 27000 |  | 0%
4.2.3 Fabrication |  |  | 47000 |  | 0%
4.2.4 Material |  |  | 4000 |  | 0%
|  |  | 78000 | w/o Contingency
Progress as of end of Current Month
4.2.2 Tooling |  |  |  |  | Drawing Process begun, nearly complete. 100hrs billed this month, but due to misunderstanding on Accounts Payable this and last month's billing will appear in June. $35k appears as lien on this account--will be split with 5.2.2
4.2.3 Fabrication |  |  |  |  | Have fabricated all M55J panels required to build Panel Assemblies. CF PEEK Material ordered for Stave mounts and Inserts (~$3.8k)
4.2.4 Material |  |  |  |  | Carbon Foam for core materials is in hand. Cost is $1068--machine to form will apper next month

## Space Frame
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | ETC |  | Totals |  | Liens
WBS Barrel Supports | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
5.2.2 Tooling |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 31000
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 25000
5.2.3 Fabrication |  |  | 368 |  | 0 |  | 0 |  | 0 |  | 368 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 368 | 116632
Eng | 121.25 | 129.7375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 368 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5.2.4 Material |  |  | 970 |  | 970 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 970 | 36530
Eng | 121.25 | 129.7375 |  | 8 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 92 | 97.52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 100 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 24693
Totals |  |  | 1338 |  | 970 |  | 0 |  | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338 | 184162
|  |  | Budget |  | Percent Completion based on hours worked
5.2.2 Tooling |  |  | 31000 |  | 0%
5.2.3 Fabrication |  |  | 117000 |  | 0%
5.2.4 Material |  |  | 37500 |  | 0% | [11 empty] | 100% |  | 100% |  | 100%
|  |  | 185500 | w/o Contingency
Progress as of end of Current Month
5.2.2 Tooling |  |  |  |  | Lien for $35k appears in 4.2.2. Will split ~$25k to this account for tracking purposes. No work started on this
5.2.3 Fabrication
5.2.4 Material |  |  |  |  | Material ordered, expect in May--will be billed after reciept. Appears as Lien in reports.