## Barrel Mounts
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March |  | April |  | May |  | ETC |  | Totals |  | Liens
WBS Barrel Mounts | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
4.2.2 Tooling |  |  | 34581.08 |  | 0 |  | 0 |  | 1488 |  | 1984 |  | 8192 |  | 496 |  | 8085.5 |  | 7905.5 |  | 3230.08 |  | 0 |  | 3200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 34581.08 | -7581.08
Eng | 124 | 138.88 |  | 0 | 0 | 0 | 0 | 12 | 1488 | 16 | 1984 | 8 | 992 | 4 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.5 | 7905.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 8085.5 | 0 | 0 | 28 | 3230.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 7200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4.2.3 Fabrication |  |  | 71898.24 |  | 0 |  | 0 |  | 4128 |  | 6672.5 |  | 13153.5 |  | 2987 |  | 1030 |  | 2231 |  | 7170.24 |  | 7000 |  | 12151 |  | 7788 |  | 6617 |  | 970 |  | 0 |  | 0 |  | 0 | 71898.24 | -24898.24
Eng | 124 | 138.88 |  | 0 | 0 | 0 | 0 | 2 | 248 | 4 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 |  | 0 | 0 | 0 | 0 | 40 | 3880 | 24.5 | 2376.5 | 47 | 4559 | 0 | 0 | 0 | 0 | 23 | 2231 | 66 | 7170.24 | 35 | 3395 | 91 | 8827 | 41 | 3977 | 62 | 6014 | 10 | 970 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 5098.5 | 29 | 2987 | 10 | 1030 | 0 | 0 | 0 | 0 | 35 | 3605 | 5 | 515 | 37 | 3811 | 1 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 3800 |  | 3496 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 825 |  | 0 |  | 500 |  | 0 |  | 0 |  | 0 |  | 0
4.2.4 Material |  |  | 1973 |  | 0 |  | 125 |  | 368 |  | 1068 |  | 412 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1973 | 2027
Eng | 124 | 138.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 97 | 108.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 103 | 115.36 |  | 0 | 0 | 0 | 125 | 0 | 368 | 0 | 0 | 4 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 1068 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 108452.32 |  | 0 |  | 125 |  | 5984 | 44.5 | 9724.5 | 108.5 | 21757.5 | 33 | 3483 | 88.5 | 9115.5 | 104.5 | 10136.5 | 94 | 10400.32 | 70 | 7000 | 112 | 15351 | 78 | 7788 | 63 | 6617 | 10 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 108452.32 | -30452.32
|  |  | Budget |  | Percent Completion based on hours worked
4.2.2 Tooling |  |  | 27000 |  | 0% |  | 0% |  | 5.511% |  | 12.86% |  | 43.2% |  | 45.04% |  | 74.98% |  | 104.3% |  | 116.2% |  | 116.2% |  | 128.1% |  | 128.1% |  | 128.1% |  | 128.1% |  | 128.1% |  | 128.1% |  | 128.1%
4.2.3 Fabrication |  |  | 47000 |  | 0% |  | 0% |  | 8.783% |  | 22.98% |  | 50.97% |  | 57.32% |  | 59.51% |  | 64.26% |  | 79.52% |  | 94.41% |  | 120.3% |  | 136.8% |  | 150.9% |  | 153% |  | 153% |  | 153% |  | 153%
4.2.4 Material |  |  | 4000 |  | 0% |  | 3.125% |  | 12.32% |  | 39.02% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33% |  | 49.33%
|  |  | 78000 | w/o Contingency
Progress as of end of Current Month
4.2.2 Tooling
4.2.3 Fabrication
4.2.4 Material

## Space Frame
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March |  | April |  | May |  | ETC |  | Totals |  | Liens
WBS Barrel Supports | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
5.2.2 Tooling |  |  | 19241.08 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3794 |  | 0 |  | 0 |  | 0 |  | 15447.08 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 19241.08 | 11758.92
Eng | 124 | 138.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2222.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 3600 |  | 0 |  | 0 |  | 0 |  | 13225 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
5.2.3 Fabrication |  |  | 97940 |  | 0 |  | 0 |  | 0 |  | 368 |  | 0 |  | 485 |  | 17917 |  | 10391 |  | 7000 |  | 3018 |  | 21169.5 |  | 7629 |  | 11429.5 |  | 12827.5 |  | 5705.5 |  | 0 |  | 0 | 97940 | 19060
Eng | 124 | 138.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 496 | 16 | 1984 | 32 | 3968 | 16 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 485 | 172.5 | 16732.5 | 105 | 10185 | 0 | 0 | 26 | 2522 | 55.5 | 5383.5 | 25 | 2425 | 45.5 | 4413.5 | 119.5 | 11591.5 | 3 | 291 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 | 1184.5 | 2 | 206 | 0 | 0 | 0 | 0 | 134 | 13802 | 12 | 1236 | 44 | 4532 | 12 | 1236 | 21.5 | 2214.5 | 0 | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 368 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7000 |  | 0 |  | 0 |  | 0 |  | 500 |  | 0 |  | 3200 |  | 0 |  | 0
5.2.4 Material |  |  | 33753 |  | 992 |  | 0 |  | 0 |  | 0 |  | 31694 |  | 1067 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 33753 | 3747
Eng | 124 | 138.88 |  | 8 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Tech | 97 | 108.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 194 | 11 | 1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shop | 103 | 115.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 31500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
Totals |  |  | 150934.08 |  | 992 |  | 0 |  | 0 | 0 | 368 | 4 | 35488 | 16 | 1552 | 184 | 17917 | 107 | 10391 | 16 | 22447.08 | 30 | 3018 | 205.5 | 21169.5 | 69 | 7629 | 105.5 | 11429.5 | 131.5 | 12827.5 | 24.5 | 5705.5 | 0 | 0 | 0 | 0 | 150934.08 | 34565.92
|  |  | Budget |  | Percent Completion based on hours worked
5.2.2 Tooling |  |  | 31000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 12.24% |  | 12.24% |  | 12.24% |  | 12.24% |  | 62.07% |  | 62.07% |  | 62.07% |  | 62.07% |  | 62.07% |  | 62.07% |  | 62.07% |  | 62.07%
5.2.3 Fabrication |  |  | 117000 |  | 0% |  | 0% |  | 0% |  | 0.3145% |  | 0.3145% |  | 0.7291% |  | 16.04% |  | 24.92% |  | 30.91% |  | 33.49% |  | 51.58% |  | 58.1% |  | 67.87% |  | 78.83% |  | 83.71% |  | 83.71%
5.2.4 Material |  |  | 37500 |  | 0% |  | 2.645% |  | 2.645% |  | 2.645% |  | 87.16% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01% |  | 90.01%
|  |  | 185500 | w/o Contingency
Progress as of end of Current Month
5.2.2 Tooling
5.2.3 Fabrication
5.2.4 Material

## R292A Summary
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March |  | April |  | May |  | ETC |  | Totals |  | Liens
WBS Barrel Mounts | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve | 0
4.2.2 Tooling |  |  | 34581.08 | 0 | 0 | 0 | 0 | 0 | 1488 | 0 | 1984 | 0 | 8192 | 0 | 496 | 0 | 8085.5 | 0 | 7905.5 | 0 | 3230.08 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34581.08 | -7581.08 | 0
Eng | 124 | 138.88 | 0 | 0 | 0 | 0 | 0 | 12 | 1488 | 16 | 1984 | 8 | 992 | 4 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.5 | 7905.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.5 | 8085.5 | 0 | 0 | 28 | 3230.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.3 Fabrication |  |  | 71898.24 | 0 | 0 | 0 | 0 | 0 | 4128 | 0 | 6672.5 | 0 | 13153.5 | 0 | 2987 | 0 | 1030 | 0 | 2231 | 0 | 7170.24 | 0 | 7000 | 0 | 12151 | 0 | 7788 | 0 | 6617 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 71898.24 | -24898.24 | 0
Eng | 124 | 138.88 | 0 | 0 | 0 | 0 | 0 | 2 | 248 | 4 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 | 0 | 0 | 0 | 0 | 0 | 40 | 3880 | 24.5 | 2376.5 | 47 | 4559 | 0 | 0 | 0 | 0 | 23 | 2231 | 66 | 7170.24 | 35 | 3395 | 91 | 8827 | 41 | 3977 | 62 | 6014 | 10 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.5 | 5098.5 | 29 | 2987 | 10 | 1030 | 0 | 0 | 0 | 0 | 35 | 3605 | 5 | 515 | 37 | 3811 | 1 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 3496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2.4 Material |  |  | 1973 | 0 | 0 | 0 | 125 | 0 | 368 | 0 | 1068 | 0 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1973 | 2027 | 0
Eng | 124 | 138.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 | 0 | 0 | 0 | 0 | 125 | 0 | 368 | 0 | 0 | 4 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  |  | 108452.32 | 0 | 0 | 0 | 125 | 0 | 5984 | 44.5 | 9724.5 | 108.5 | 21757.5 | 33 | 3483 | 88.5 | 9115.5 | 104.5 | 10136.5 | 94 | 10400.32 | 70 | 7000 | 112 | 15351 | 78 | 7788 | 63 | 6617 | 10 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 108452.32 | -30452.32 | 0
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March |  | April |  | May |  | ETC |  | Totals |  | Liens
WBS Barrel Supports | 09 rate | 10 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve | 0
5.2.2 Tooling |  |  | 19241.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15447.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19241.08 | 11758.92 | 0
Eng | 124 | 138.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2222.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.3 Fabrication |  |  | 97940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 485 | 0 | 17917 | 0 | 10391 | 0 | 7000 | 0 | 3018 | 0 | 21169.5 | 0 | 7629 | 0 | 11429.5 | 0 | 12827.5 | 0 | 5705.5 | 0 | 0 | 0 | 0 | 97940 | 19060 | 0
Eng | 124 | 138.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 496 | 16 | 1984 | 32 | 3968 | 16 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 485 | 172.5 | 16732.5 | 105 | 10185 | 0 | 0 | 26 | 2522 | 55.5 | 5383.5 | 25 | 2425 | 45.5 | 4413.5 | 119.5 | 11591.5 | 3 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 | 1184.5 | 2 | 206 | 0 | 0 | 0 | 0 | 134 | 13802 | 12 | 1236 | 44 | 4532 | 12 | 1236 | 21.5 | 2214.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.4 Material |  |  | 33753 | 0 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31694 | 0 | 1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33753 | 3747 | 0
Eng | 124 | 138.88 | 0 | 8 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech | 97 | 108.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 194 | 11 | 1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 103 | 115.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  |  | 150934.08 | 0 | 992 | 0 | 0 | 0 | 0 | 0 | 368 | 4 | 35488 | 16 | 1552 | 184 | 17917 | 107 | 10391 | 16 | 22447.08 | 30 | 3018 | 205.5 | 21169.5 | 69 | 7629 | 105.5 | 11429.5 | 131.5 | 12827.5 | 24.5 | 5705.5 | 0 | 0 | 0 | 0 | 150934.08 | 34565.92 | 0
|  |  |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March |  | April |  | May |  | ETC |  | Totals
|  |  |  | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | EST | Reserve
R292A Totals (Estimated in Report) |  |  | 259386.4 | 0 | 992 | 0 | 125 | 0 | 5984 | 44.5 | 10092.5 | 112.5 | 57245.5 | 49 | 5035 | 272.5 | 27032.5 | 211.5 | 20527.5 | 110 | 32847.4 | 100 | 10018 | 317.5 | 36520.5 | 147 | 15417 | 168.5 | 18046.5 | 141.5 | 13797.5 | 24.5 | 5705.5 | 0 | 0 | 0 | 0 | 259386.4 | 4113.6
R292 Actuals in Cost Database |  |  | 255933 |  | 969 |  | 112 |  | 4867 |  | 9539 |  | 53144 |  | 3985 |  | 30310 |  | 20774 |  | 32852 |  | 9976 |  | 36792 |  | 16440 |  | 18148 |  | 12692 |  | 5333 |  | 0
Deviation |  |  | 3453.4 |  | 23 |  | 13 |  | 1117 |  | 553.5 |  | 4101.5 |  | 1050 |  | -3277.5 |  | -246.5 |  | -4.6 |  | 42 |  | -271.5 |  | -1023 |  | -101.5 |  | 1105.5 |  | 372.5 |  | 0
3453.4
-4924.6