## Sheet1
|  |  |  | July |  | August |  | September |  | October |  | November |  | December |  | ETC |  | Totals
WBS Pixel Staves | 08 rate | 09 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | ETC | Reserve
2.3.2 Tooling |  |  | 25550.78 |  | 0 |  | 2528 |  | 4455 |  | 5008.5 |  | 10582.8 |  | 2976.48 |  | 7174.08 | 32724.86 | 2275.14
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 | 24 | 4057.44 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984.32 | 24 | 2976.48 | 32 | 3968.64
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 | 37.5 | 5008.5 | 34 | 4541.04 |  | 0 | 24 | 3205.44
Procurement |  |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  |  | 46655.08 |  | 0 |  | 1264 |  | 7231 |  | 7067 |  | 8099.46 |  | 22993.62 |  | 57752 | 104407.08 | -21407.08
Eng | 158 | 169.06 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 | 8 | 1352.48 | 40 | 6762.4
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 51 | 5967 | 50 | 6201 | 61 | 7565.22 | 58 | 7193.16 | 360 | 44647.2
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 534.24 | 95.5 | 12754.98 | 40 | 5342.4
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 866 |  | 0 |  | 1693 |  | 1000
2.3.4 Material |  |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0 |  | 0 | 15238 | -238
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0 |  | 0
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 87443.86 |  | 117 |  | 15984 |  | 14615 | 87.5 | 12075.5 | 139 | 18682.26 | 185.5 | 25970.1 | 496 | 64926.08 | 152369.94 | -19369.94
|  |  | Budgeted |  | Percent Completion based on hours worked
2.3.2 Tooling |  |  | $35k |  | 0% |  | 0% |  | 15% |  | 30%
2.3.3 Fabrication |  |  | $83k |  | 0% |  | 0% |  | 8% |  | 12%
2.3.4 Material |  |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% |  | 100%
Progress as of end of October
2.3.2 Tooling |  |  |  |  | Bowed tool successful. Had commissioned 4 additional tools, blanks for which were machined prior to understanding lower production rate required by RIKEN (finish machining completed on only first unit). Now have two omega tools. Assembly tooling for previous mount block design also completed. Work for assembly tooling needs to be re-done to accomodate new block design--representing overshot in tooling budget...
2.3.3 Fabrication |  |  |  |  | Unfortunately, all PEEK mount blocks were machined to improper mount positions prior to information from RIKEN that mounts had to be shifted by 1mm (includes 16hrs in Jan). 40 additional hrs required to machine new mount blocks to modified dimensions which is included in ETC (Estimate to Complete).
2.3.4 Material |  |  |  |  | Complete.