## Sheet1
|  |  |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | ETC |  | Totals
WBS Pixel Staves | 08 rate | 09 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | ETC | Reserve
2.3.2 Tooling |  |  | 27039.02 |  | 0 |  | 2528 |  | 4455 |  | 5008.5 |  | 10582.8 |  | 2976.48 |  | 0 |  | 1488.24 |  | 1488.24 | 28527.26 | 6472.74
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 | 24 | 4057.44 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984.32 | 24 | 2976.48 | 0 | 0 | 12 | 1488.24 | 12 | 1488.24
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 | 37.5 | 5008.5 | 34 | 4541.04 |  | 0 |  | 0 |  | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  |  | 68869.34 |  | 0 |  | 1264 |  | 7231 |  | 7067 |  | 8099.46 |  | 22993.62 |  | 6952.46 |  | 15261.8 |  | 50617.68 | 119487.02 | -36487.02
Eng | 158 | 169.06 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 | 8 | 1352.48 | 8 | 1352.48 | 8 | 1352.48 | 28 | 4733.68
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 51 | 5967 | 50 | 6201 | 61 | 7565.22 | 58 | 7193.16 | 29 | 3596.58 | 96 | 11905.92 | 272 | 33733.44
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 534.24 | 95.5 | 12754.98 | 15 | 2003.4 | 15 | 2003.4 | 76 | 10150.56
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 866 |  | 0 |  | 1693 |  | 0 |  | 0 |  | 2000
2.3.4 Material |  |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15238 | -238
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 111146.36 |  | 117 |  | 15984 |  | 14615 | 87.5 | 12075.5 | 139 | 18682.26 | 185.5 | 25970.1 | 52 | 6952.46 | 131 | 16750.04 | 388 | 52105.92 | 163252.28 | -30252.28
|  |  | Budgeted |  | Percent Completion based on hours worked | [14 empty] | Omega | 14
2.3.2 Tooling |  |  | $35k |  | 0% |  | 0% |  | 15% |  | 30% |  |  | 30% | [5 empty] | Bare Stave | 15
2.3.3 Fabrication |  |  | $83k |  | 0% |  | 0% |  | 8% |  | 12% |  |  | 12% | [5 empty] | W/Blocks | 0
2.3.4 Material |  |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% | 100% | 100% |  | 100% |  | 100%
Progress as of end of October
2.3.2 Tooling |  |  |  |  | Tooling for Survey is complete--only remaining tooling are fixtures etc for batch pressure cycling and leak check
2.3.3 Fabrication |  |  |  |  | Note ETC is only an estimate in this spreadsheet which uses average rates for shops/people. More accurate spreadsheet will accompany this.
2.3.4 Material |  |  |  |  | Complete.