## Sheet1
|  |  |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | ETC |  | Totals
WBS Pixel Staves | 08 rate | 09 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | ETC | Reserve
2.3.2 Tooling |  |  | 25550.78 |  | 0 |  | 2528 |  | 4455 |  | 5008.5 |  | 10582.8 |  | 2976.48 |  | 0 |  | 7174.08 | 32724.86 | 2275.14
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 | 24 | 4057.44 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984.32 | 24 | 2976.48 | 0 | 0 | 32 | 3968.64
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 | 37.5 | 5008.5 | 34 | 4541.04 |  | 0 |  | 0 | 24 | 3205.44
Procurement |  |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  |  | 53607.54 |  | 0 |  | 1264 |  | 7231 |  | 7067 |  | 8099.46 |  | 22993.62 |  | 6952.46 |  | 50818.62 | 104426.16 | -21426.16
Eng | 158 | 169.06 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 | 8 | 1352.48 | 8 | 1352.48 | 32 | 5409.92
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 51 | 5967 | 50 | 6201 | 61 | 7565.22 | 58 | 7193.16 | 29 | 3596.58 | 315 | 39066.3
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 534.24 | 95.5 | 12754.98 | 15 | 2003.4 | 40 | 5342.4
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 866 |  | 0 |  | 1693 |  | 0 |  | 1000
2.3.4 Material |  |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15238 | -238
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 94396.32 |  | 117 |  | 15984 |  | 14615 | 87.5 | 12075.5 | 139 | 18682.26 | 185.5 | 25970.1 | 52 | 6952.46 | 443 | 57992.7 | 152389.02 | -19389.02
|  |  | Budgeted |  | Percent Completion based on hours worked | [12 empty] | Omega | 20
2.3.2 Tooling |  |  | $35k |  | 0% |  | 0% |  | 15% |  | 30% |  |  | 30% |  |  |  | Bare Stave | 5
2.3.3 Fabrication |  |  | $83k |  | 0% |  | 0% |  | 8% |  | 12% |  |  | 12% |  |  |  | W/Blocks | 0
2.3.4 Material |  |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% | 100% | 100% |  | 100%
Progress as of end of October
2.3.2 Tooling |  |  |  |  | Stave assembly tooling 'complete' (assuming first article compatibility with RIKEN module mount tooling). Only remaining tooling is Stave Survey Tool.
2.3.3 Fabrication |  |  |  |  | Remaining shop time and procurement is to re-fabricate PEEK Blocks. Below ETC are the number of parts/assemblies complete. For work complete to date, ETC is tracking 'well' with hours--i.e. still $19.4k in the hole.
2.3.4 Material |  |  |  |  | Complete.