## Sheet1
|  |  |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March |  | April |  | May |  | June |  | ETC |  | Totals
WBS Pixel Staves | 08 rate | 09 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | ETC | Reserve
2.3.2 Tooling |  |  | 28031.18 |  | 0 |  | 2528 |  | 4455 |  | 5008.5 |  | 10582.8 |  | 2976.48 |  | 0 |  | 1488.24 |  | 992.16 |  | 0 |  | 0 |  | 0 |  | 0 | 28031.18 | 6968.82
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 | 24 | 4057.44 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984.32 | 24 | 2976.48 | 0 | 0 | 12 | 1488.24 | 8 | 992.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 | 37.5 | 5008.5 | 34 | 4541.04 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  |  | 110771.59 |  | 0 |  | 1264 |  | 7231 |  | 7067 |  | 8099.46 |  | 22993.62 |  | 6952.46 |  | 15261.8 |  | 20298.92 |  | 4669.83 |  | 11219.04 |  | 5714.46 |  | 8699.65 | 119471.24 | -35671.24
Eng | 158 | 169.06 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 | 8 | 1352.48 | 8 | 1352.48 | 8 | 1352.48 | 8 | 1352.48 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1352.48
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 51 | 5967 | 50 | 6201 | 61 | 7565.22 | 58 | 7193.16 | 29 | 3596.58 | 96 | 11905.92 | 128 | 15874.56 | 35.5 | 4402.71 | 84 | 10417.68 | 45 | 5580.9 | 34.5 | 4278.69
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 534.24 | 95.5 | 12754.98 | 15 | 2003.4 | 15 | 2003.4 | 23 | 3071.88 | 2 | 267.12 | 6 | 801.36 | 1 | 133.56 | 8 | 1068.48
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 866 |  | 0 |  | 1693 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2000
2.3.4 Material |  |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15238 | -238
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 154040.77 |  | 117 |  | 15984 |  | 14615 | 87.5 | 12075.5 | 139 | 18682.26 | 185.5 | 25970.1 | 52 | 6952.46 | 131 | 16750.04 | 167 | 21291.08 | 37.5 | 4669.83 | 90 | 11219.04 | 46 | 5714.46 | 50.5 | 8699.65 | 162740.42 | -28940.42
|  |  | Budgeted |  | Percent Completion based on hours worked | [22 empty] | Omega | 49
2.3.2 Tooling |  |  | $35k |  | 0% |  | 0% |  | 15% |  | 30% |  |  | 30% | [13 empty] | Bare Stave | 48
2.3.3 Fabrication |  |  | $83k |  | 0% |  | 0% |  | 8% |  | 12% |  |  | 12% | [13 empty] | W/Blocks | 47
2.3.4 Material |  |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% | 100% | 100% |  | 100% |  |  |  | 100% |  | 100% |  | 100% |  | 100%
Progress as of end of October
2.3.2 Tooling
2.3.3 Fabrication |  |  |  |  | 22 Staves have shipped. 2 Staves have failed leak check, and 2 additional have failed after re-work. All stave fabrication is complete, only survey and potential re-work of some staves is required. CMM shop is down until end of June/first wk July for upgrade of HVAC in Building 77. Remaining survey work will occur when CMM is brought back online after access to room is granted. ETC Value under $13.5k indicates that work to complete should be under estimate.
2.3.4 Material |  |  |  |  | Complete.