## Sheet1
|  |  |  | July |  | August |  | September |  | October |  | November |  | December |  | ETC |  | Totals
WBS Pixel Staves | 08 rate | 09 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | ETC | Reserve
2.3.2 Tooling |  |  | 22574.3 |  | 0 |  | 2528 |  | 4455 |  | 5008.5 |  | 10582.8 |  | 0 |  | 9311.04 | 31885.34 | 3114.66
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 | 24 | 4057.44 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1984.32 |  | 0 | 32 | 3968.64
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 | 37.5 | 5008.5 | 34 | 4541.04 |  | 0 | 40 | 5342.4
Procurement |  |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  |  | 23661.46 |  | 0 |  | 1264 |  | 7231 |  | 7067 |  | 8099.46 |  | 0 |  | 56752 | 80413.46 | 2586.54
Eng | 158 | 169.06 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 |  | 0 | 40 | 6762.4
Tech | 117 | 124.02 |  | 0 | 0 | 0 | 0 | 51 | 5967 | 50 | 6201 | 61 | 7565.22 |  | 0 | 360 | 44647.2
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 534.24 |  | 0 | 40 | 5342.4
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 866 |  | 0 |  | 0 |  | 0
2.3.4 Material |  |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0 |  | 0 | 15238 | -238
Eng | 158 | 169.06 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 124.02 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0 |  | 0
Shop | 126 | 133.56 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0 |  | 0
Totals |  |  | 61473.76 |  | 117 |  | 15984 |  | 14615 | 87.5 | 12075.5 | 139 | 18682.26 | 0 | 0 | 512 | 66063.04 | 127536.8 | 5463.2
|  |  | Budgeted |  | Percent Completion based on hours worked
2.3.2 Tooling |  |  | $35k |  | 0% |  | 0% |  | 15% |  | 30%
2.3.3 Fabrication |  |  | $83k |  | 0% |  | 0% |  | 8% |  | 12%
2.3.4 Material |  |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% |  | 100%
Progress as of end of October
2.3.2 Tooling |  |  |  |  | Have generated 'bowed' tool which can yeild flat omega parts. Have held off on full production qty of tooling to save cost versus schedule, to be discussed at LBNL during Riken visit--more tooling can allow production to go faster
2.3.3 Fabrication |  |  |  |  | Have spent some contingencency here to produce several trial omega samples to generate sufficient statistics to determine curvature. Stave assemblies with acceptable flatness have been produced (1 complete 4 partial--without mount blocks) by end of Nov. Hose barbs need to be re-fabricated. Initial five stave samples will be with non conforming barbs for use by RIKEN for procedural testing.
2.3.4 Material |  |  |  |  | Complete.