## Sheet1
|  |  |  | July |  | August |  | September |  | October |  | November |  | December
WBS Pixel Staves | 08 rate | 09 rate | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost
2.3.2 Tooling |  |  | 12108.995 |  | 0 |  | 2528 |  | 4455 |  | 5125.995 |  | 0 |  | 0
Eng | 158 | 164.32 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 |  | 0 |  | 0
Tech | 117 | 122.85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 37.5 | 4606.875 |  | 0 |  | 0
Shop | 126 | 129.78 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 | 4 | 519.12 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  |  | 15503.5 |  | 0 |  | 1264 |  | 7231 |  | 7008.5 |  | 0 |  | 0
Eng | 158 | 164.32 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 |  | 0
Tech | 117 | 122.85 |  | 0 | 0 | 0 | 0 | 51 | 5967 | 50 | 6142.5 |  | 0 |  | 0
Shop | 126 | 129.78 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 0 |  | 0 |  | 866 |  | 0 |  | 0
2.3.4 Material |  |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0
Eng | 158 | 164.32 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0
Tech | 117 | 122.85 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0
Shop | 126 | 129.78 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0
Totals |  |  | 42850.495 |  | 117 |  | 15984 |  | 14615 |  | 12134.495 |  | 0 |  | 0
|  |  | Budgeted |  | Percent Completion based on hours worked
2.3.2 Tooling |  |  | $35k |  | 0% |  | 0% |  | 15% |  | 30%
2.3.3 Fabrication |  |  | $83k |  | 0% |  | 0% |  | 8% |  | 12%
2.3.4 Material |  |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% |  | 100%
Progress as of end of October
2.3.2 Tooling |  |  |  |  | Omega tool delayed. Spent some contingency on accelerated Aluminum single part tool (not costed--will appear in Nov. Inadequate contingency model for omega tool--did not include re-machining to account for bowed part, may exceed tooling budget--hope to recover with simpler Assembly tooling
2.3.3 Fabrication |  |  |  |  | All Thermal tiles complete and within spec. 50hrs of tech time spent on Omega tool qualification fabricating sample parts to tune in laminate properties and to determine inherent bow of part. This will have to come from contingency--try to recover some in accelerated assembly.
2.3.4 Material |  |  |  |  | Material order complete but all contingency spent on additional material qualification--resin content of cheaper material necessitated additional bleed studies and complicates fabrication of Omega in particular--excessive bow is main consequence.