## PHENIX Stave Progress
STAVE Numbers |  |  |  | Parts |  | Bare Staves |  | Bare Staves |  |  | Quality Assurance |  |  |  | Shipping
STAVE Number | Production Number Original | Production Number Final | Serial Number | Tile | Omega | Bad Barb | Good Barb | Shifted Blocks | Good Blocks | Ground Wire | Pressure Cycle Leak Result | In Survey | Survey Result | Finish Date | Boxed | Shipping Number | Comment
1 | [13 empty] | Dec |  | Non Production | First Batch of 5 Staves--so-called 'December Staves', wrong barbs, low tolerance on holes. 1 with R Pak, 1 with Atsushi, 3 at LBNL
2 | [13 empty] | Dec |  | Non Production
3 | [13 empty] | Dec |  | Non Production
4 | [13 empty] | Dec |  | Non Production
5 | [13 empty] | Dec |  | Non Production
6 | [13 empty] | Jan |  | Non Production | Stave w/1mm Shifted Blocks 'January Stave'
7 |  |  | 102342 | [10 empty] | Feb |  | Non Production | Stave w original Blocks (low Tolerance holes) for test--now not considered part of production…
8 | 1 | 25 | 102202 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | Apr |  |  | Ready To Be Shipped
9 | 2 | 7 | 102242 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | Apr | x | ShipDoc# B34643
10 | 3 |  | 102259 | x | x | N/A | x | N/A | N/A | N/A | N/A | N/A | N/A | March
11 | 4 |  | 102264 | x | x | N/A | x | N/A | x | x | 9.2e-10 | x | x | June |  |  | Rework
12 | 5 |  | 102290 | x | x | N/A | x | N/A | x | x | 1.4e-09 | x |  | Apr |  |  | Out of tolerance
13 | 6 |  | 102299 | x | x | N/A | x | N/A | x | x | 1.6e-09 | x |  | Apr |  |  | Out of tolerance
14 | 7 | 8 | 102316 | x | x | N/A | x | N/A | x | x | 2.2e-09 | x | x | Apr | x | ShipDoc# B34643
15 | 8 | 2 | 102333 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | Apr | x | ShipDoc# B34094 | 2009-05-01
16 |  |  | 102342 | x | x | N/A | x | N/A | x | N/A | N/A | N/A | N/A | Feb |  |  | Stave w original Blocks (low Tolerance holes) for test--now not considered part of production…
17 | 9 | 6 | 102359 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | Apr | x | ShipDoc# B34094 | 2009-05-01
18 |  | 26 | 102368 | x | x | N/A | x | N/A | x | x | 1.4e-09 | x | x | June |  |  | Ready To Be Shipped
19 | 10 | 5 | 102377 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | Apr | x | ShipDoc# B34094 | 2009-05-01
20 | 11 | 4 | 102397 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | Apr | x | ShipDoc# B34094 | 2009-05-01
21 | 12 |  | 102411 | x | x | N/A | x | N/A | x | N/A | N/A | N/A | N/A | March
22 | 13 | 3 | 102424 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | Apr | x | ShipDoc# B34094 | 2009-05-01
23 | 14 | 9 | 102433 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | May | x | ShipDoc# B34643
24 | 15 | 10 | 102442 | x | x | N/A | x | N/A | x | x | 8.73e-10 | x | x | May | x | ShipDoc# B34643
25 | 16 | 11 | 102451 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | May | x | ShipDoc# B34643
26 | 17 | 12 | 102460 | x | x | N/A | x | N/A | x | x | 9.1e-10 | x | x | May | x | ShipDoc# B34643
27 | 18 | 13 | 102469 | x | x | N/A | x | N/A | x | x | 1.1e-09 | x | x | May | x | ShipDoc# B34643
28 | 19 | 14 | 102478 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | May | x | ShipDoc# B34643
29 | 20 | 15 | 102487 | x | x | N/A | x | N/A | x | x | 7.4e-10 | x | x | May | x | ShipDoc# B34643
30 | 21 | 27 | 102498 | x | x | N/A | x | N/A | x | x | 1e-09 | x | x | June |  |  | Ready To Be Shipped
31 | 22 | 16 | 102507 | x | x | N/A | x | N/A | x | x | 8.5e-10 | x | x | May | x | ShipDoc# B34643
32 | 23 | 17 | 102516 | x | x | N/A | x | N/A | x | x | 9.8e-10 | x | x | May | x | ShipDoc# B34643
33 | 24 | 18 | 102525 | x | x | N/A | x | N/A | x | x | 1e-09 | x | x | May | x | ShipDoc# B34643
34 | 25 |  | 102534 | x | x | N/A | x | N/A | x | x | 1e-09 | x | x | May |  |  | Rework
35 |  | 28 | 102543 | x | x | N/A | x | N/A | x | x | 1.5e-09 | x | x | June |  |  | Ready To Be Shipped
36 | 26 | 19 | 102552 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | April | x | ShipDoc# B34643
37 | 27 | 20 | 102570 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | April | x | ShipDoc# B34643
38 | 28 | 21 | 102579 | x | x | N/A | x | N/A | x | x | 1e-09 | x | x | April | x | ShipDoc# B34643
39 | 29 | 29 | 102588 | x | x | N/A | x | N/A | x | x | 1e-09 | x | x | June |  |  | Ready To Be Shipped
40 | 30 | 22 | 102597 | x | x | N/A | x | N/A | x | x | 1.2e-09 | x | x | April | x | ShipDoc# B34643
41 | 31 | 30 | 102606 | x | x | N/A | x | N/A | x | x | 1.5e-09 | x | x | June |  |  | Ready To Be Shipped
42 | 32 |  | 102615 | x | x | N/A | x | N/A | x | x | 1.9e-09 | x | x | June |  |  | Rework
43 |  | 23 | 102624 | x | x | N/A | x | N/A | x | x | 2.7e-09 | x | x | April | x | ShipDoc# B34643
44 | 33 |  | 102633 | x | x | N/A | x | N/A | x |  | Fail | [5 empty] | Will Recheck--no visible holes under microscope. Leaky Stave
45 | 34 | 31 | 102642 | x | x | N/A | x | N/A | x | x | 1.5e-09 | x | x | June |  |  | Ready To Be Shipped
46 | 35 | 32 | 102651 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | June |  |  | Ready To Be Shipped
47 | 36 | 33 | 102660 | x | x | N/A | x | N/A | x | x | 1.5e-09 | x | x | June |  |  | Ready To Be Shipped
48 | 37 | 34 | 102669 | x | x | N/A | x | N/A | x | x | 1.5e-09 | x | x | June |  |  | Ready To Be Shipped
49 | 38 | 35 | 102678 | x | x | N/A | x | N/A | x | x | 1.4e-09 | x | x | June |  |  | Ready To Be Shipped
50 | 39 |  | 102687 | x | x | N/A | x | N/A | x |  | Fail | [5 empty] | Will Recheck--no visible holes under microscope. Leaky Stave
51 |  | 36 | 102696 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | June |  |  | Ready To Be Shipped
52 |  |  | 102705 | x | x | N/A | x | N/A | x | x | 1.6e-09 | x | x | June |  |  | Rework
53 |  | 38 | 102723 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | June |  |  | Ready To Be Shipped - Omega has unusually high twist--use only if required.
54 | 40 | 39 | 102732 | x | x | N/A | x | N/A | x | x | 1.3e-09 | x | x | June |  |  | Ready To Be Shipped
55 |  | 37 | 102714 | x | x | N/A | x | N/A | x | x | 1.6e-09 | x | x | June |  |  | Ready To Be Shipped
56 | 41 | 24 | 102741 | x | x | N/A | x | N/A | x | x | 1.5e-09 | x | x | June |  |  | Ready To Be Shipped
57 | 42
58 | 43 | [15 empty] | At this point--need to make another batch of Thermal Planes…
|  |  |  | 49 | 49 |  | 49 |  | 48 |  | 44 | 44 | 42 |  | 22 | Shipped
[15 empty] | 15 | Ready to ship
[15 empty] | 4 | Rework Required
[15 empty] | 41 | Total