## Sheet1
|  |  | July |  | August |  | September |  | October |  | November |  | December
WBS Pixel Staves |  | YTD | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost | HRS | Cost
2.3.2 Tooling |  | 6983 |  | 0 |  | 2528 |  | 4455 |  | 0 |  | 0 |  | 0
Eng | 158 |  | 0 | 0 | 16 | 2528 | 8 | 1264 |  | 0 |  | 0 |  | 0
Tech | 117 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Shop | 126 |  | 0 | 0 | 0 | 0 | 14.5 | 1827 |  | 0 |  | 0 |  | 0
Procurement |  |  |  | 0 |  | 0 |  | 1364 |  | 0 |  | 0 |  | 0
2.3.3 Fabrication |  | 8495 |  | 0 |  | 1264 |  | 7231 |  | 0 |  | 0 |  | 0
Eng | 158 |  | 0 | 0 | 8 | 1264 | 8 | 1264 |  | 0 |  | 0 |  | 0
Tech | 117 |  | 0 | 0 | 0 | 0 | 51 | 5967 |  | 0 |  | 0 |  | 0
Shop | 126 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2.3.4 Material |  | 15238 |  | 117 |  | 12192 |  | 2929 |  | 0 |  | 0 |  | 0
Eng | 158 |  | 0 | 0 | 16 | 2528 | 0 | 0 |  | 0 |  | 0 |  | 0
Tech | 117 |  | 1 | 117 | 32 | 3744 | 12 | 1404 |  | 0 |  | 0 |  | 0
Shop | 126 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Procurement |  |  |  | 0 |  | 5920 |  | 1525 |  | 0 |  | 0 |  | 0
Totals |  | 30716 |  | 117 |  | 15984 |  | 14615 |  | 0 |  | 0 |  | 0
|  | Budgeted |  | Percent Completion based on hours worked
2.3.2 Tooling |  | $35k |  | 0% |  | 0% |  | 15%
2.3.3 Fabrication |  | $83k |  | 0% |  | 0% |  | 8%
2.3.4 Material |  | $15k |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% |  | 100%
Progress as of end of September
2.3.2 Tooling |  |  |  | Shops worked an additional 25hrs in Sept after fiscal close on 19-Sept. Actual progess closer to 30%. Omega Tool delayed by ~2wks from original schedule. Will begin tracking after reciept of tool (tool warps during machining)
2.3.3 Fabrication |  |  |  | Composite Plate for Thermal Tile complete, 4 tiles cut in preparation for first assemblies
2.3.4 Material |  |  |  | All work for material acquisition and testing is complete--lien for material testing cleared in September