## Rates
Shop | 135
CMM | 136
M_Tech | 127
Engineer | 150
Designer | 85
B
C

## Pre- and Production
PHENIX Stave Estimate to Complete | [14 empty] | TRACKING | [8 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | CMM | Eng Time | Des Time | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Orders | Base or Contingency | Protot or Production | Sum Logic Code | UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals
Material Batches | [21 empty] | Underage(-)
Hysol Adhesive | Hysol 9396 | 1 | Order | 327 | 327 | 0 | 0.5 | 0 | 0 | 0 | hours | 63.5 | 1 | 390.5 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0.5 | 0 | 0 | 0 | 327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Silver Epoxy | Epotek | 1 | Order | 500 | 500 | 0 | 0.5 | 0 | 0 | 0 | hours | 63.5 | 1 | 563.5 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0.5 | 0 | 0 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Batches Subtotal | [11 empty] | 127 | Base Labor | [10 empty] | 0 | 1 | 0 | 0 | 0 |  | 827 | 954 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Thermal Tiles
Pre-Productions | [12 empty] | 0
Plate Lamination | Bagging | 0.5 | m^2 | 55 | 27.5 | 0 | 4 | 0 | 0.8 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2008 | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim to Size (makes 24 pieces) | Batch | 1 | Cutter | 80 | 80 | 0 | 3 | 0 | 0.6 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2008 | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | C | PT | CPT2008 | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production | [12 empty] | 0
Plate Lamination | Bagging | 0.5 | m^2 | 55 | 27.5 | 0 | 4 | 0 | 0.8 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2008 | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim to Size (makes 24 pieces/Batch) | Batch | 1 | Cutter | 80 | 80 | 0 | 5 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2008 | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Thermal Tile Subtotal | [11 empty] | 0 | Base Labor | [10 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
OMEGA
Production Parts
Cut materials and kit | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 762 | 3 | 762 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 6 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Layup | Bagging | 0.25 | m^2 | 55 | 13.75 | 0 | 2 | 0 | 0 | 0 | hours | 7112 | 28 | 7497 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 56 | 0 | 0 | 0 | 385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OMEGA Subtotal | [11 empty] | 7874 | Base Labor | [10 empty] | 0 | 62 | 0 | 0 | 0 |  | 385 | 8259 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
STAVE Assembly
Tooling
Production Tooling | [12 empty] | 1
Stave Survey Fixture | Aluminum | 10 | lb | 8 | 80 | 0 | 8 | 0 | 0 | 0 | hours | 1016 | 1 | 1096 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 0 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Sum | 1016 | Sum
Production Assemblies (100%Production) | [12 empty] | 1
Omega to Tile Bond | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 6604 | 26 | 6604 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 52 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mount Block | Labor | 0 | N/A | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | hours | 3240 | 40 | 3240 | B | PD | BPD2009 | [5 empty] | 2009 | 24 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mount Block Bond | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 10160 | 40 | 10160 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 80 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pressure/Leak QA | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 6580 | 5 | 6580 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 40 | 0 | 10 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Survey | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0.4 | 0 | hours | 7840 | 40 | 7840 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 40 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Assemblies (+ 2 contingency) | [10 empty] | Sum | 34424 | Sum
Omega to Tile Bond | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 1016 | 4 | 1016 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mount Block Bond | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 1016 | 4 | 1016 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pressure/Leak QA | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 1016 | 1 | 1016 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stave Survey | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0.4 | 0 | hours | 784 | 4 | 784 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 4 | 1.6 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Sum | 3832 | Sum
Stave Assembly Subtotal | [11 empty] | 39272 | Base Labor | [10 empty] | 24 | 204 | 44 | 27.6 | 0 |  | 80 | 39352 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Shipping (25% Production)
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 540 | 1 | 590 | B | PD | BPD2009 | [5 empty] | 2009 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 1016 | 4 | 1016 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 200 | 200 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 800 | B | PD | BPD2009 | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 800 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping Subtotal | [11 empty] | 1556 | Base Labor |  |  |  |  | FY05 | [5 empty] | 4 | 8 | 0 | 0 | 0 |  | 850 | 2406 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[22 empty] | 0 |  | 28 | 275 | 44 | 27.6 | 0 |  | 2142 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost |  |  |  | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost
[29 empty] | Cost With Contingency | 50971 | 50971 |  | External Work Excluded…
[24 empty] | BASE | [9 empty] | CONTINGENCY
[23 empty] | Year | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[23 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 374.6 | [8 empty] | 2009 | 28 | 275 | 44 | 27.6 | 0 | 2142 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Contingency
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[23 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2009 | 3780 | 34925 | 5984 | 4140 | 0 | 2142 | 50971 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 50971 | [8 empty] | Contingency | 0
[39 empty] | Percent | 0%
[24 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPT | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Cost
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPT | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 0 | [8 empty] | Contingency | 0
[39 empty] | Percent | #DIV/0!
[24 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[24 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPD | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2008 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2009 | 28 | 275 | 44 | 27.6 | 0 | 2142 |  |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | Hytec | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | LANL | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | LANL | 0 | 0 | 0 | 0 | 0 | 0
[24 empty] | LBNL Cost | [9 empty] | LBNL Cost
[24 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPD | [5 empty] | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2009 | 3780 | 34925 | 5984 | 4140 | 0 | 2142 | 50971 |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[29 empty] | Base Cost | 50971 | [8 empty] | Contingency | 0
[39 empty] | Percent | 0%
[30 empty] | 50971 | checksum | [8 empty] | 0 | checksum

## SUMMARY
| BASE | [7 empty] | CONTINGENCY
Year | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 28 | 275 | 44 | 27.6 | 0 | 2142 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Contingency
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 3780 | 34925 | 5984 | 4140 | 0 | 2142 | 50971 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 50971 | [6 empty] | Contingency | 0 | 50971
[14 empty] | Percent | 0%
| Pre-Production Base Cost | [7 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 0 | [6 empty] | Contingency | 0
[14 empty] | Percent | #DIV/0!
| Production Base Cost | [7 empty] | Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2008 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2008 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 28 | 275 | 44 | 27.6 | 0 | 2142 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Hytec | 0 | 0 | 0 | 0 | 0 | 0 |  | Hytec | 0 | 0 | 0 | 0 | 0 | 0
LANL | 0 | 0 | 0 | 0 | 0 | 0 |  | LANL | 0 | 0 | 0 | 0 | 0 | 0
| LBNL Cost | [7 empty] | LBNL Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | 3780 | 34925 | 5984 | 4140 | 0 | 2142 | 50971 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 50971 | [6 empty] | Contingency | 0
[6 empty] | Spent 02/09 | 20503 | [6 empty] | Percent | 0%
[6 empty] | ETC | 30468