## WBS in Estimate
This table drives values in a lookup table in the Pre- and Production Sheet, columns U and V. It is 'copied' into that sheet at the bottom, see notes there to understand how to modify this. 'Inserting' rows does not work, only adding, so must modify whole table--5 rows are available for additions...
WBS | Description
1.5.4 | Infrastructure
1.5.4.1 | Cables
1.5.4.2 | Dry Gas Services
1.5.4.3 | Hall Modifications and Integrated Safety
1.5.4.3.1 | Clean Room Modification
1.5.4.3.2 | External Clean Tent
1.5.4.3.3 | Shield Wall Pass-through

## SUMMARY
| BASE | [9 empty] | CONTINGENCY | [8 empty] | Total Effort (Base + Contingency) (Hours)
| Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0.5 | 50 | 20 | 84.5 | 56 | 2200 |  |  |  | 2011 | 0 | 16 | 0 | 4 | 0 | 400 |  |  | 2011 | 0.5 | 66 | 20 | 88.5 | 56 | 2600
2012 | 0 | 24 | 0 | 84 | 0 | 35000 |  |  |  | 2012 | 0 | 32 | 0 | 112 | 0 | 10000 |  |  | 2012 | 0 | 56 | 0 | 196 | 0 | 45000
2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 10000
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 12 | 200 | 16 | 164 | 0 | 0 |  |  |  | STAR | 12 | 208 | 4 | 136 | 8 | 1000 |  |  | STAR | 24 | 408 | 20 | 300 | 8 | 1000
| Project Estimated Cost | [9 empty] | Project Estimated Contingency
| Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals | V0.2 | Delta |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals | V0.2 | Delta |  | FY | V0.2 | V0.3 | Delta
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2010 | 0 | 0 | 0
2011 | 63 | 4916.34 | 0 | 10281 | 0 | 2200 | 17460.34 | 17460.34 | 0 | 2011 | 0 | 1872 | 0 | 600 | 0 | 400 | 2872 | 2872 | 0 |  | 2011 | 20332.34 | 20332.34 | 0
2012 | 0 | 2808 | 0 | 12600 | 0 | 35000 | 50408 | 0 | 50408 | 2012 | 0 | 3744 | 0 | 4800 | 0 | 10000 | 18544 | 0 | 18544 |  | 2012 | 0 | 68952 | 68952
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 2013 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 1 | 9999 |  | 2013 | 2 | 10000 | 9998
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013 | 0 | 0 | 0
[6 empty] | Base Cost | 67868.34 | [8 empty] | Contingency | 31416 |  |  |  | Total | 20334.34 | 99284.34 | 78950
[16 empty] | Percent | 46.29%
| Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0.5 | 8 | 0 | 0.5 | 0 | 600 |  |  |  | 2011 | 0 | 16 | 0 | 4 | 0 | 400
2012 | 0 | 24 | 0 | 84 | 0 | 35000 |  |  |  | 2012 | 0 | 32 | 0 | 32 | 0 | 10000
2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 10000
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 8 | 136 | 0 | 60 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 63 | 936 | 0 | 75 | 0 | 600 | 1674 |  |  | 2011 | 0 | 1872 | 0 | 600 | 0 | 400 | 2872
2012 | 0 | 2808 | 0 | 12600 | 0 | 35000 | 50408 |  |  | 2012 | 0 | 3744 | 0 | 4800 | 0 | 10000 | 18544
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 52082 | [8 empty] | Contingency | 31416
[16 empty] | Percent | 60.32%
| Production Base Cost | [9 empty] | Production Contingency Cost
| Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0 | 42 | 20 | 84 | 56 | 1600 |  |  |  | 2011 | 0 | 0 | 0 | 0 | 0 | 0
2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2012 | 0 | 0 | 0 | 80 | 0 | 0
2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 4 | 64 | 16 | 104 | 0 | 0 |  |  |  | STAR | 12 | 208 | 4 | 136 | 8 | 1000
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0 | 3980.34 | 0 | 10206 | 0 | 1600 | 15786.34 |  |  | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 15786.34 | [8 empty] | Contingency | 0
[16 empty] | Percent | 0%

## Pre- and Production
[17 empty] | (HIDE) |  |  |  | (HIDE AS REQUIRED)
Infrastructure (1.5.4) | [14 empty] | TRACKING | [11 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | PostDoc (cont) | Eng Time | Engineer (cont) | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | Sum Logic Code | WBS | WBS Descriptor | PO/UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | PostDoc (cont) | Engineering | Engineer (cont) | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | PostDoc (cont) | Engineering | Engineer (cont) | Materials Sub Totals | Materials Totals
Cables | [24 empty] | Underage(-)
shroud bias cable | [12 empty] | 1 | [11 empty] | Underage(-)
shroud bias cable design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 40 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
connectors specify | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 8 | hours | 972 | 1 | 972 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 0 | 0 | 8 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
prototype construction | N/A | 1 | N/A | 600 | 600 | 0.5 | 8 | 0 | 0.5 | 0 | hours | 1074 | 1 | 1674 | B | PT | BPT2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0.5 | 8 | 0 | 0.5 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cable Fabrication | N/A | 1 | N/A | 1000 | 1000 | 0 | 8 | 16 | 8 | 8 | hours | 1730.16 | 1 | 2730.16 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 8 | 16 | 8 | 8 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 100 | 100 | 0 | 2 | 4 | 4 | 0 | hours | 675.54 | 1 | 775.54 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 2 | 4 | 4 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 16 | 8 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPDSTAR | B1.5.4.1STAR | 1.5.4.1 | Cables | [5 empty] | STAR | 0 | 16 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 8 | 8 | 4 | 8 | 8 | hours | 2546.64 | 1 | 3046.64 | C | PD | CPDSTAR | C1.5.4.1STAR | 1.5.4.1 | Cables | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 8 | 4 | 8 | 8 | 500
Environ Monitor and Rad monitor cables | [10 empty] | Sum | 11800.02 | Base Labor
Cable design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 1944 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 0 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
prototype construction | N/A | 1 | N/A | 400 | 400 | 0 | 16 | 0 | 4 | 0 | hours | 2472 | 1 | 2872 | C | PT | CPT2011 | C1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 4 | 0 | 400
Acceptance testing | N/A | 1 | N/A | 100 | 100 | 0 | 8 | 0 | 4 | 0 | hours | 1244.16 | 1 | 1344.16 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 8 | 0 | 4 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cable Fabrication | N/A | 1 | N/A | 0 | 400 | 0 | 16 | 0 | 0 | 0 | hours | 1516.32 | 1 | 1916.32 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 16 | 0 | 0 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
acceptance testing | N/A | 1 | N/A | 0 | 0 | 0 | 8 | 0 | 4 | 0 | hours | 1244.16 | 1 | 1244.16 | B | PD | BPD2011 | B1.5.4.12011 | 1.5.4.1 | Cables | [5 empty] | 2011 | 0 | 8 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 16 | 8 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPDSTAR | B1.5.4.1STAR | 1.5.4.1 | Cables | [5 empty] | STAR | 0 | 16 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 2230.16 | C | PD | CPDSTAR | C1.5.4.1STAR | 1.5.4.1 | Cables | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 8 | 0 | 500
[11 empty] | Sum | 8436.96 | Base Labor
Cables Subtotal | [11 empty] | 20236.98 | Base Labor | [13 empty] | 0.5 | 82 | 36 | 100.5 | 56 |  | 2200 | 22232.92 |  | 7679.12 | 8 | 32 | 4 | 20 | 8 |  | 1400
Dry Gas Services
Design interface to plant (Engineering) | [12 empty] | 1
engineering design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
spec size, insulation, material | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
heat exchanger upgrade (contingency) | N/A | 0 | N/A | 0 | 0 | 0 | 60 | 0 | 0 | 0 | hours | 5686.2 | 1 | 5686.2 | C | PD | CPDSTAR | C1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 60 | 0 | 0 | 0 | 0
plant upgrade (contingency) | N/A | 0 | N/A | 0 | 0 | 0 | 120 | 0 | 80 | 0 | hours | 21092.4 | 1 | 21092.4 | C | PD | CPDSTAR | C1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 80 | 0 | 0
heat exchanger upgrade (contingency) | N/A | 6000 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | C | PD | CPD2012 | C1.5.4.22012 | 1.5.4.2 | Dry Gas Services | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
plant upgrade (contingency) | N/A | 15000 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | C | PD | CPD2012 | C1.5.4.22012 | 1.5.4.2 | Dry Gas Services | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 80 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPDSTAR | C1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Interface Ducting | [10 empty] | Sum | 9720 | Base Labor
ducting prototype section | N/A | 1 | N/A | 0 | 0 | 8 | 24 | 0 | 4 | 0 | hours | 4416 | 1 | 4416 | B | PT | BPTSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 8 | 24 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 2136 | 1 | 2136 | B | PT | BPTSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
production ducting procure | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 972 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
flange passthrough | N/A | 1 | N/A | 0 | 0 | 4 | 8 | 0 | 0 | 0 | hours | 1166.4 | 1 | 1166.4 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 4 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 4 | 12 | 0 | 0 | 0 | hours | 1545.48 | 1 | 1545.48 | C | PD | CPDSTAR | C1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 12 | 0 | 0 | 0 | 0
External Ducting | [10 empty] | Sum | 10964.88 | Base Labor
engineering design (contingency) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ducting prototype section | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPTSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPTSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
production ducting procure | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.2STAR | 1.5.4.2 | Dry Gas Services | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Sum | 0 | Base Labor
Cooling Services Subtotal | [11 empty] | 20684.88 | Base Labor | [13 empty] | 12.5 | 146 | 36 | 200.5 | 56 |  | 0 | 39472.92 |  | 49183.2 | 12 | 224 | 4 | 220 | 8 |  | 0
Hall modification and Integrated Safety
Clean Room Modfication
sprinkler install Contributed Labor | N/A | 1 | N/A | 0 | 0 | 0 | 80 | 0 | 24 | 0 | hours | 12960 | 1 | 12960 | B | PT | BPTSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 80 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
sprinkler install Purchase | N/A | 1 | N/A | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 10000 | B | PT | BPT2012 | B1.5.4.32012 | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 10000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPTSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPTSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 10000 | C | PT | CPT2013 | C1.5.4.32013 | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10000
External Clean Tent | [10 empty] | Sum | 12960 | Sum
specify | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 9000 | 1 | 9000 | B | PT | BPT2012 | B1.5.4.32012 | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | 2012 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
procure | N/A | 1 | N/A | 0 | 0 | 0 | 8 | 0 | 16 | 0 | hours | 3336 | 1 | 3336 | B | PT | BPTSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 8 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 3072 | 1 | 3072 | B | PT | BPTSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
procure | N/A | 1 | N/A | 20000 | 20000 | 0 | 8 | 0 | 16 | 0 | hours | 3336 | 1 | 23336 | B | PT | BPT2012 | B1.5.4.32012 | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | 2012 | 0 | 8 | 0 | 16 | 0 | 20000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 5000 | 5000 | 0 | 16 | 0 | 8 | 0 | hours | 3072 | 1 | 8072 | B | PT | BPT2012 | B1.5.4.32012 | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | 2012 | 0 | 16 | 0 | 8 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 10000 | 10000 | 0 | 32 | 0 | 32 | 0 | hours | 8544 | 1 | 18544 | C | PT | CPT2012 | C1.5.4.32012 | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 32 | 0 | 10000
Shield Wall Pass-thru | [10 empty] | Sum | 21816 | Sum
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
xxx | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 3 | 0 | C | PD | CPDSTAR | C1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | C | PD | CPDSTAR | C1.5.4.3STAR | 1.5.4.3 | Hall Modifications and Integrated Safety | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Level Subtotal | [11 empty] | 34776 | Base Labor | [13 empty] | 0 | 128 | 0 | 132 | 0 |  | 35000 | 63168.56 |  | 26920.64 | 0 | 32 | 0 | 32 | 0 |  | 20000
[11 empty] | Sum | #REF! | Sum
[25 empty] | 0 |  | 12.5 | 274 | 36 | 332.5 | 56 |  | 37200 |  |  |  | 12 | 256 | 4 | 252 | 8 |  | 21400
[27 empty] | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) |  | M&S Cost |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) |  | M&S Cost
[26 empty] | Checksum | #REF! | #REF! | #REF! | #REF! | #REF! |  | 37200 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | 21400 | Checksum
[32 empty] | Cost With Contingency | #REF! | 99284.34 |  | Contributed Labor Excluded…
Description | WBS | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009
Infrastructure | 1.5.4 | <-- Copy Down from this Cell both columns A and B to update WBS list | [11 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | BASE | [9 empty] | CONTINGENCY
Cables | 1.5.4.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
Dry Gas Services | 1.5.4.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
Hall Modifications and Integrated Safety | 1.5.4.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Clean Room Modification | 1.5.4.3.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2011 | 0.5 | 50 | 20 | 84.5 | 56 | 2200 |  |  |  | 2011 | 0 | 16 | 0 | 4 | 0 | 400
External Clean Tent | 1.5.4.3.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 0 | 24 | 0 | 84 | 0 | 35000 |  |  |  | 2012 | 0 | 32 | 0 | 112 | 0 | 10000
Shield Wall Pass-through | 1.5.4.3.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 10000
[26 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | STAR | 12 | 200 | 16 | 164 | 0 | 0 |  |  |  | STAR | 12 | 208 | 4 | 136 | 8 | 1000
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Project Estimated Cost | [9 empty] | Project Estimated Contingency
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2011 | 63 | 4916.34 | 0 | 10281 | 0 | 2200 | 17460.34 |  |  | 2011 | 0 | 1872 | 0 | 600 | 0 | 400 | 2872
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 0 | 2808 | 0 | 12600 | 0 | 35000 | 50408 |  |  | 2012 | 0 | 3744 | 0 | 4800 | 0 | 10000 | 18544
[26 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [8 empty] | Base Cost | 67868.34 | [8 empty] | Contingency | 31416
[14 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [18 empty] | Percent | 46.29%
[33 empty] | 67868.34 | checksum | [8 empty] | 31416 | checksum
|  | IF need to copy below this line to contain WBS, need to update Data Validation for cells in column "U" (WBS) AND 'Look Up' vectors for Column "V" (Descriptor) | [24 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
[27 empty] | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
[17 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2011 | 0.5 | 8 | 0 | 0.5 | 0 | 600 |  |  | CPT | 2011 | 0 | 16 | 0 | 4 | 0 | 400
[17 empty] | BPT | [8 empty] | 2012 | 0 | 24 | 0 | 84 | 0 | 35000 |  |  | CPT | 2012 | 0 | 32 | 0 | 32 | 0 | 10000
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 10000
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | STAR | 8 | 136 | 0 | 60 | 0 | 0 |  |  | CPT | STAR | 0 | 0 | 0 | 0 | 0 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
[17 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2011 | 63 | 936 | 0 | 75 | 0 | 600 | 1674 |  | CPT | 2011 | 0 | 1872 | 0 | 600 | 0 | 400 | 2872
[17 empty] | BPT | [8 empty] | 2012 | 0 | 2808 | 0 | 12600 | 0 | 35000 | 50408 |  | CPT | 2012 | 0 | 3744 | 0 | 4800 | 0 | 10000 | 18544
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 52082 | [8 empty] | Contingency | 31416
[42 empty] | Percent | 60.32%
[27 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[27 empty] | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 0 | 42 | 20 | 84 | 56 | 1600 |  |  | CPD | 2011 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2012 | 0 | 0 | 0 | 80 | 0 | 0
[17 empty] | BPD | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2013 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | STAR | 4 | 64 | 16 | 104 | 0 | 0 |  |  | CPD | STAR | 12 | 208 | 4 | 136 | 8 | 1000
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 0 | 3980.34 | 0 | 10206 | 0 | 1600 | 15786.34 |  | CPD | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 15786.34 | [8 empty] | Contingency | 0
[42 empty] | Percent | 0%

## Rates
Values below used only for reference--not linked to data in sheet estimate…
| Construction | R&D |  | English | Metric | Quoted |  | Metric
Shop | 102.06 | 126 | Material | lb/in^3 | g/cc | Cost/Unit | Unit | Cost/Unit | Unit
CMM | 0 | 0 | Aluminum | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
M_Tech | 94.77 | 117 | MIC-6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
Engineer | 121.5 | 150 | 6061-T6 | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
DES | 0 | 0 | 7075-T6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
|  |  | Titanium | 0.198 | 5.4855 | 15 | $/lb | 0.030992 | $/g
Construction Rate does not have full Burden--currently ~81% (below) of Full Burden at LBNL (R&D Rate) |  |  | 6Al4V | 0.198 | 5.4855 | 20 | $/lb | 0.041322 | $/g
|  |  | Steel | 0.298 | 8.256 | 3 | $/lb | 0.0061983 | $/g
|  |  | 304SS | 0.298 | 8.256 | 15 | $/lb | 0.030992 | $/g
|  |  | Carbon Fiber | 0.065 | 1.8008 | 100 | $/lb | 0.20661 | $/g
Differential | 81% |  | M55J-UDT | 0.065 | 1.8008 | 800 | $/lb | 1.6529 | $/g
Change This to change burden rate… |  |  | CN60-PW | 0.065 | 1.8008 | 500 | $/lb | 1.0331 | $/g
|  |  | YSH80A-UDT | 0.065 | 1.8008 | 1200 | $/lb | 2.4793 | $/g
|  |  | Adhesive | 0.055 | 1.5238 | 400 | $/qt | 0.42283 | $/cc
|  |  | EA9396 | 0.055 | 1.5238 | 350 | $/qt | 0.36998 | $/cc
|  |  | EA9394 | 0.075 | 2.0779 | 450 | $/qt | 0.47569 | $/cc
|  |  | CF HoneyComb | 0.0017361 | 0.048099 | 600 | $/bdft | 0.25424 | $/cc
|  |  | Al HoneyComb | 0.0017361 | 0.048099 | 75 | $/bdft | 0.03178 | $/cc
|  |  | Nomex HC | 0.0023148 | 0.064131 | 100 | $/bdft | 0.042373 | $/cc
|  |  | PEEK | 0.055 | 1.5238 | 400 | $/lb | 0.82645 | $/g
|  |  | CF PEEK | 0.055 | 1.5238 | 600 | $/lb | 1.2397 | $/g

## Material Estimates
Material Estimates per component |  |  | Values used to estimate Size/Cost of Batch Orders--Does not report to Cost Summary
Item | Material | Descriptor | Quantity | CPT (microns) | Density (g/cc) | Finished Form | % Waste | Length (cm) | Diameter/Width (cm) | Thickness (cm) | Volume (cc) | Mass (g) | Pre-Preg Area (m^2) | Cost Per Unit | Choose Unit | Cost | Prototype Mass | Prototype Area | Prototype Composites
Material Volumes | [19 empty] | /cc | Bulk | 1
D-Tube | [19 empty] | /g | Plate | 2
Tooling | [19 empty] | /m^2 | Round | 3
Mandrel | Steel | Pipe | 1 | n/a | 8.3 | Shell | 0% | 60 | 20 | 1.5 | 5654.8668 | 46935.3942 | #VALUE! | 0.006 | /g | 281.6124 | 0 | 0 | 0 |  | Shell | 4
Mandrel End Plates | Steel | Plate | 1 | n/a | 8.3 | Plate | 0% | 60 | 25 | 3 | 4500 | 37350 | #VALUE! | 0.006 | /g | 224.1 | 0 | 0 | 0
D-Tube Bond Tool
Tooling
Support Beam Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 100 | 30 | 3 | 9000 | 24300 | #VALUE! | 0.017 | /g | 413.1 | 0 | 0 | 0
Support Beam Machining Tool | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 0% | 30 | 15 | 5 | 4500 | 12150 | #VALUE! | 0.017 | /g | 206.55 | 0 | 0 | 0
Components | [11 empty] | 80.2863
Thick Laminate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Plate | 30% | 80 | 2.5 | 0.8 | 1040 | 1872 | 3.1515 | 1.033 | /g | 1933.776 | 0 | 0 | 0
Thick Laminate Test | CN60 Cloth | Test | 2 | 330 | 1.8 | Plate | 50% | 20 | 3 | 0.8 | 144 | 259.2 | 0.43636 | 1.033 | /g | 267.7536 | 259.2 | 0.43636 | 267.7536
Insertion Test Bed
Support Components
Item Bars | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 250 | 7.5 | 7.5 | 73125 | 197437.5 | #VALUE! | 0.017 | /g | 3356.4375 | 0 | 0 | 0
Station Plates | Aluminum | Plate | 3 | n/a | 2.7 | Plate | 30% | 50 | 50 | 5 | 48750 | 131625 | #VALUE! | 0.017 | /g | 2237.625 | 0 | 0 | 0
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Iteration | [11 empty] | 840.7764 |  |  |  | 6489.1125
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Prototype | [11 empty] | 115.9692 |  |  |  | 895.05
Cart Rail Rider prototype | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Low Mass Cart | [11 empty] | 154.6256 |  |  |  | 1193.4
Cart Rail Rider | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Tooling | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 60 | 30 | 5 | 11700 | 31590 | 35.4545 | 0.017 | /g | 537.03 | 0 | 0 | 0