## WBS in Estimate
This table drives values in a lookup table in the Pre- and Production Sheet, columns U and V. It is 'copied' into that sheet at the bottom, see notes there to understand how to modify this. 'Inserting' rows does not work, only adding, so must modify whole table--5 rows are available for additions...
WBS | Description
1.5 | Integration and Global Supports
1.5.1 | Mechanics
1.5.1.1 | Inner Detector Support (IDS)
1.5.1.1.1 | West Support Cylinder Interface
1.5.1.1.2 | East Support Cylinder (ESC)
1.5.1.1.3 | Outer Support Cylinder (OSC)
1.5.1.1.4 | E-Field Shroud (EFS)
1.5.1.2 | Middle Support Cylinder (MSC)
1.5.1.2.1 | Pixel Insertion Tube
1.5.1.2.2 | Bulkhead Extension
1.5.1.2.3 | Transition Plate
1.5.1.2.4 | Pixel Support Tube
1.5.1.3 | Beam Pipe Mechanics
1.5.1.3.1 | Beam Pipe Model
1.5.1.3.2 | Internal Support (Low Mass)
1.5.1.3.3 | Alternate Beam Pipe Support
1.5.1.3.4 | External Beam Pipe Support
1.5.1.3.5 | Bake Out Equipment
1.5.2 | Electronics | Not In Estimate
1.5.2.1 | Detector Grounding/EMI Control | Not In Estimate
1.5.2.2 | Environmental Control | Not In Estimate
1.5.2.3 | Shroud Bias | Not In Estimate
1.5.3 | Assembly
1.5.3.1 | MSC Assembly
1.5.3.2 | IDS Assembly
1.5.4 | Integration Infrastructure | Not In Estimate
1.5.4.1 | Cables | Not In Estimate
1.5.4.2 | Dry Gas Services | Not In Estimate
1.5.4.3 | Hall Modifications and Safety | Not In Estimate
1.5.4.3.1 | Clean Room Modifications | Not In Estimate
1.5.4.3.2 | External Clean Tent | Not In Estimate
1.5.4.3.3 | Shield Wall Pass Thru | Not In Estimate
1.5.5 | Installation

## WBS Summary
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
WBS | Description | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
1.5 | Integration and Global Supports | 16 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420 | 0 | 1.5 | 13492 |  |  | 68
1.5.1 | Mechanics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.1 |  | 10343 |  | 0
1.5.1.1 | Inner Detector Support (IDS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.1.1 |  |  | 4577 | 0 | 640780 | 822927.5
1.5.1.1.1 | West Support Cylinder Interface | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.1.1.1 |  |  |  | 0
1.5.1.1.2 | East Support Cylinder (ESC) | 136 | 8 | 508 | 420 | 16 | 8 | 120 | 61 | 0 | 0 | 108660 | 11272.5 | 1.5.1.1.2 |  |  |  | 1277
1.5.1.1.3 | Outer Support Cylinder (OSC) | 346 | 76 | 1204 | 556 | 96 | 24 | 866 | 132 | 0 | 0 | 54455 | 7760 | 1.5.1.1.3 |  |  |  | 3300
1.5.1.1.4 | E-Field Shroud (EFS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.1.1.4 |  |  |  | 0
1.5.1.2 | Middle Support Cylinder (MSC) | 16 | 4 | 94 | 59 | 0 | 0 | 20 | 31 | 0 | 0 | 91555 | 111792.5 | 1.5.1.2 |  |  | 3590 | 224 | 502600 | 747977.5
1.5.1.2.1 | Pixel Insertion Tube | 192 | 64 | 620 | 476 | 24 | 16 | 188 | 108 | 0 | 0 | 11460 | 6640 | 1.5.1.2.1 |  |  |  | 1688
1.5.1.2.2 | Bulkhead Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.1.2.2 |  |  |  | 0
1.5.1.2.3 | Transition Plate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.1.2.3 |  |  |  | 0
1.5.1.2.4 | Pixel Support Tube | 142 | 68 | 624 | 332 | 0 | 0 | 460 | 52 | 0 | 0 | 16170 | 7760 | 1.5.1.2.4 |  |  |  | 1678
1.5.1.3 | Beam Pipe Mechanics | 8 | 0 | 112 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 800 | 0 | 1.5.1.3 |  |  | 2176 | 284 | 304640 | 345710
1.5.1.3.1 | Beam Pipe Model | 24 | 0 | 80 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 1800 | 0 | 1.5.1.3.1 |  |  |  | 176
1.5.1.3.2 | Internal Support (Low Mass) | 32 | 88 | 136 | 32 | 0 | 0 | 152 | 48 | 0 | 0 | 7930 | 4010 | 1.5.1.3.2 |  |  |  | 488
1.5.1.3.3 | Alternate Beam Pipe Support | 0 | 8 | 0 | 76 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 1300 | 1.5.1.3.3 |  |  |  | 160
1.5.1.3.4 | External Beam Pipe Support | 0 | 0 | 76 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 1300 | 0 | 1.5.1.3.4 |  |  |  | 196
1.5.1.3.5 | Bake Out Equipment | 8 | 0 | 124 | 80 | 0 | 0 | 460 | 200 | 0 | 0 | 1000 | 0 | 1.5.1.3.5 |  |  |  | 872
1.5.2 | Electronics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.2 |  |  |  | 0
1.5.2.1 | Detector Grounding/EMI Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.2.1 |  |  |  | 0
1.5.2.2 | Environmental Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.2.2 |  |  |  | 0
1.5.2.3 | Shroud Bias | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.2.3 |  |  |  | 0
1.5.3 | Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3 |  | 2513 |  | 0
1.5.3.1 | MSC Assembly | 32 | 40 | 590 | 20 | 0 | 0 | 340 | 40 | 0 | 0 | 16110 | 1600 | 1.5.3.1 |  |  | 1062 | 1062 | 148680 | 166390
1.5.3.2 | IDS Assembly | 44 | 60 | 871 | 20 | 0 | 0 | 416 | 40 | 0 | 0 | 24565 | 1600 | 1.5.3.2 |  |  | 1451 | 1451 | 203140 | 229305
1.5.4 | Integration Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4 |  |  |  | 0
1.5.4.1 | Cables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.1 |  |  |  | 0
1.5.4.2 | Dry Gas Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.2 |  |  |  | 0
1.5.4.3 | Hall Modifications and Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.3 |  |  |  | 0
1.5.4.3.1 | Clean Room Modifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.3.1 |  |  |  | 0
1.5.4.3.2 | External Clean Tent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.3.2 |  |  |  | 0
1.5.4.3.3 | Shield Wall Pass Thru | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4.3.3 |  |  |  | 0
1.5.5 | Installation | 0 | 80 | 300 | 0 | 0 | 0 | 140 | 48 | 0 | 0 | 0 | 1600 | 1.5.5 |  | 568 |  | 568 | 0
| Hours | 996 | 496 | 5391 | 2071 | 136 | 48 | 3518 | 836 | 0 | 0 | 343225 | 155335
| FTE | 0.57907 | 0.28837 | 3.1343 | 1.2041 | 0.07907 | 0.027907 | 2.0453 | 0.48605 | 0 | 0
| Cost Approx | 101651.76 | 50621.76 | 510905.07 | 196268.67 | 8.0699 | 4898.88 | 427437 | 101574 | 0 | 0

## WBS Summary by Year
2009
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 16 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420 | 0
2010
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0
| 1.5.1.1.3 | 58 | 0 | 260 | 0 | 0 | 0 | 498 | 0 | 0 | 0 | 38075 | 0
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 24 | 0 | 8 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 320 | 0
| 1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 82 | 0 | 271 | 0 | 0 | 0 | 758 | 0 | 0 | 0 | 42895 | 0
2011
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 132 | 8 | 464 | 406 | 16 | 8 | 102 | 52 | 0 | 0 | 16390 | 2940
| 1.5.1.1.3 | 278 | 72 | 492 | 152 | 24 | 0 | 240 | 24 | 0 | 0 | 12530 | 5030
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13500 | 0
| 1.5.1.2.1 | 4 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 420 | 0
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 66 | 44 | 256 | 16 | 0 | 0 | 240 | 0 | 0 | 0 | 9190 | 1520
| 1.5.1.3 | 8 | 0 | 72 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 800 | 0
| 1.5.1.3.1 | 24 | 0 | 80 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 1800 | 0
| 1.5.1.3.2 | 32 | 88 | 68 | 32 | 0 | 0 | 120 | 48 | 0 | 0 | 7430 | 4010
| 1.5.1.3.3 | 0 | 8 | 0 | 76 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 1300
| 1.5.1.3.4 | 0 | 0 | 36 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 1300 | 0
| 1.5.1.3.5 | 8 | 0 | 84 | 80 | 0 | 0 | 364 | 200 | 0 | 0 | 1000 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0
| 1.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 40 | 0 | 0 | 0 | 0
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 552 | 220 | 1599 | 762 | 40 | 8 | 1434 | 408 | 0 | 0 | 64360 | 14800
2012
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 4 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855 | 0
| 1.5.1.1.3 | 10 | 4 | 244 | 108 | 24 | 0 | 64 | 28 | 0 | 0 | 3850 | 420
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 8 | 0 | 61 | 46 | 0 | 0 | 20 | 31 | 0 | 0 | 74345 | 109937.5
| 1.5.1.2.1 | 178 | 62 | 364 | 246 | 16 | 8 | 116 | 74 | 0 | 0 | 7690 | 4120
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 52 | 22 | 224 | 158 | 0 | 0 | 76 | 26 | 0 | 0 | 4350 | 3720
| 1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.2 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 32 | 40 | 350 | 20 | 0 | 0 | 124 | 40 | 0 | 0 | 16110 | 1600
| 1.5.3.2 | 44 | 60 | 447 | 20 | 0 | 0 | 128 | 0 | 0 | 0 | 24565 | 1600
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.5 | 0 | 80 | 80 | 0 | 0 | 0 | 40 | 48 | 0 | 0 | 0 | 1600
|  | 328 | 268 | 1815 | 598 | 40 | 8 | 568 | 247 | 0 | 0 | 132765 | 122997.5
2013
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.3 | 0 | 0 | 208 | 296 | 48 | 24 | 64 | 80 | 0 | 0 | 0 | 2310
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 8 | 4 | 26 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 3710 | 1855
| 1.5.1.2.1 | 10 | 2 | 216 | 230 | 8 | 8 | 32 | 34 | 0 | 0 | 3350 | 2520
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 0 | 2 | 136 | 158 | 0 | 0 | 24 | 26 | 0 | 0 | 2310 | 2520
| 1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
| 1.5.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.2 | 0 | 0 | 160 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 18 | 8 | 750 | 697 | 56 | 32 | 168 | 140 | 0 | 0 | 9870 | 9205
CONT
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STAR
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0
| 1.5.1.3.4 | 0 | 0 | 40 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0
| 1.5.1.3.5 | 0 | 0 | 40 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
| 1.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.3.1 | 0 | 0 | 160 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0
| 1.5.3.2 | 0 | 0 | 264 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0
| 1.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.4.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5.5 | 0 | 0 | 180 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 684 | 0 | 0 | 0 | 496 | 32 | 0 | 0 | 0 | 0

## SUMMARY
| BASE | [9 empty] | CONTINGENCY
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  | FY | SHOP V0.4 | SHOP V0.5 | DELTA
2009 | 16 | 52 | 0 | 0 | 0 | 7420 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0
2010 | 82 | 271 | 0 | 758 | 0 | 42895 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2010 | 10332 | 10332 | 0
2011 | 552 | 1627 | 40 | 1452 | 0 | 150275 |  |  |  | 2011 | 220 | 762 | 8 | 408 | 0 | 14800 |  |  |  | 2011 | 155539.44 | 82056.24 | -73483.2
2012 | 328 | 1815 | 40 | 568 | 0 | 132765 |  |  |  | 2012 | 268 | 612 | 8 | 256 | 0 | 131330 |  |  |  | 2012 | 16941.96 | 9593.64 | -7348.32
2013 | 18 | 750 | 56 | 168 | 0 | 9870 |  |  |  | 2013 | 8 | 697 | 32 | 140 | 0 | 9205 |  |  |  | 2013 | 0 | 0 | 0
2014 | 0 | 192 | 0 | 76 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 182813.4 | 101981.88 | -80831.52
STAR | 0 | 684 | 0 | 496 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 32 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Contingency
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals | Plan B | Delta |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals | Plan B | Delta | FY | Plan B | V0.5 | DELTA
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0
2010 | 10332 | 31707 | 0 | 108570 | 0 | 42895 | 193504 | 93634 | 99870 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 93634 | 193504 | 99870
2011 | 56337.12 | 151537.23 | 4082.4 | 174231 | 0 | 64360 | 450547.75 | 690509.39 | -239961.64 | 2011 | 22453.2 | 72214.74 | 816.48 | 49572 | 0 | 14800 | 159856.42 | 180557.42 | -20701 | 2011 | 871066.81 | 610404.17 | -260662.64
2012 | 33475.68 | 172007.55 | 4082.4 | 69012 | 0 | 132765 | 411342.63 | 236218.17 | 175124.46 | 2012 | 27352.08 | 56672.46 | 816.48 | 30010.5 | 0 | 122997.5 | 237849.02 | 237341.06 | 507.96 | 2012 | 473559.23 | 649191.65 | 175632.42
2013 | 1837.08 | 71077.5 | 5715.36 | 20412 | 0 | 9870 | 108911.94 | 65283.8 | 43628.14 | 2013 | 816.48 | 66054.69 | 3265.92 | 17010 | 0 | 9205 | 96352.09 | 76159.05 | 20193.04 | 2013 | 141442.85 | 205264.03 | 63821.18
2014 | 0 | 19595.52 | 0 | 7756.56 | 0 | 0 | 27352.08 | 6123.6 | 21228.48 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 6123.6 | 27352.08 | 21228.48
[6 empty] | Base Cost | 1191658.4 | 1091768.96 | 99889.44 | [6 empty] | Contingency | 494057.53 | 494057.53 | 0 |  | 1585826.49 | 1685715.93 | 99889.44
[16 empty] | Percent | 41.46%
| Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 82 | 271 | 0 | 578 | 0 | 42895 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2011 | 0 | 0 | 0 | 0 | 0 | 0
2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2012 | 0 | 0 | 0 | 0 | 0 | 0
2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 10332 | 31707 | 0 | 86700 | 0 | 42895 | 171634 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 171634 | [8 empty] | Contingency | 0
[16 empty] | Percent | 0%
| Production Base Cost | [9 empty] | Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 180 | 0 | 0 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 552 | 1599 | 40 | 1434 | 0 | 64360 |  |  |  | 2011 | 220 | 762 | 8 | 408 | 0 | 14800
2012 | 328 | 1815 | 40 | 568 | 0 | 132765 |  |  |  | 2012 | 268 | 598 | 8 | 247 | 0 | 122997.5
2013 | 18 | 750 | 56 | 168 | 0 | 9870 |  |  |  | 2013 | 8 | 697 | 32 | 140 | 0 | 9205
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 684 | 0 | 496 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 32 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 0 | 0 | 21870 | 0 | 0 | 21870 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 56337.12 | 151537.23 | 4082.4 | 174231 | 0 | 64360 | 450547.75 |  |  | 2011 | 22453.2 | 72214.74 | 816.48 | 49572 | 0 | 14800 | 159856.42
2012 | 33475.68 | 172007.55 | 4082.4 | 69012 | 0 | 132765 | 411342.63 |  |  | 2012 | 27352.08 | 56672.46 | 816.48 | 30010.5 | 0 | 122997.5 | 237849.02
2013 | 1837.08 | 71077.5 | 5715.36 | 20412 | 0 | 9870 | 108911.94 |  |  | 2013 | 816.48 | 66054.69 | 3265.92 | 17010 | 0 | 9205 | 96352.09
2014 | 0 | 19595.52 | 0 | 7756.56 | 0 | 0 | 27352.08 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 1020024.4 | [8 empty] | Contingency | 494057.53
[16 empty] | Percent | 48.44%

## Pre- and Production
[17 empty] | (HIDE) |  |  |  | (HIDE AS REQUIRED)
HFT Integration Estimate (1.5) | [14 empty] | TRACKING | [11 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | CMM | Eng Time | Des Time | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | Sum Logic Code | WBS | WBS Descriptor | PO/UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals
Composite Material Batches | [24 empty] | Underage(-)
OSC Flange qualification | CN60 | 10 | m^2 | 400 | 4000 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 4300 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 2 | 0 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 1 | N/A | 400 | 400 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 400 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 534 | 1 | 534 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 1086 | 1 | 1138.5 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 1068 | 1 | 2568 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSC Shell qualification | YSH80A | 34 | m^2 | 500 | 17000 | 0 | 0 | 0 | 2 | 0 | hours | 300 | 1 | 17300 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 2 | 0 | 17000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 3.4 | N/A | 500 | 1700 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1700 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 1700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 534 | 1 | 534 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 1086 | 1 | 1138.5 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 1068 | 1 | 2568 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CN60 Batch (ESC, OSC, MSC PT and MSC) | CN60 | 29 | m^2 | 400 | 11600 | 0 | 0 | 0 | 2 | 0 | hours | 243 | 1 | 11843 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 2 | 0 | 11600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 2.9 | N/A | 400 | 1160 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1160 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 1160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
YSH80 Batch (ESC, OSC, MSC PT and MSC) | YSH80A | 143 | m^2 | 500 | 71500 | 0 | 0 | 0 | 4 | 0 | hours | 486 | 1 | 71986 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 4 | 0 | 71500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 14.3 | N/A | 500 | 7150 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 7150 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 7150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CN60 Batch (OSC, MSC PT and MSC) Contingency | CN60 | 12 | m^2 | 400 | 4800 | 0 | 0 | 0 | 2 | 0 | hours | 243 | 1 | 5043 | C | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 4800
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Order Contingency (+10% Areal) | N/A | 1.2 | N/A | 400 | 480 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 480 | C | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 480
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | C | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 2 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | C | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 52.5
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | C | PD | 1.5.1.1.1 | 1.5.1.1.1 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 1500
YSH80 Batch (OSC, MSC PT and MSC) Contingency | YSH80A | 85 | m^2 | 500 | 42500 | 0 | 0 | 0 | 4 | 0 | hours | 486 | 1 | 42986 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 4 | 0 | 42500
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Order Contingency (+10% Areal) | N/A | 8.5 | N/A | 500 | 4250 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 4250 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4250
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 2 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 52.5
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 1500
CN60 Batch (OSC, MSC) | CN60 | 12 | m^2 | 400 | 4800 | 0 | 0 | 0 | 2 | 0 | hours | 243 | 1 | 5043 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 2 | 0 | 4800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 1.2 | N/A | 400 | 480 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 480 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 480 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
YSH80 Batch (OSC, MSC) | YSH80A | 85 | m^2 | 500 | 42500 | 0 | 0 | 0 | 4 | 0 | hours | 486 | 1 | 42986 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 4 | 0 | 42500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 8.5 | N/A | 500 | 4250 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 4250 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 4250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CN60 Batch (OSC, MSC) Contingency | CN60 | 12 | m^2 | 400 | 4800 | 0 | 0 | 0 | 2 | 0 | hours | 243 | 1 | 5043 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 4800
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Order Contingency (+10% Areal) | N/A | 1.2 | N/A | 400 | 480 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 480 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 480
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 2 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 52.5
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 1500
YSH80 Batch (OSC, MSC) Contingency | YSH80A | 85 | m^2 | 500 | 42500 | 0 | 0 | 0 | 4 | 0 | hours | 486 | 1 | 42986 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 4 | 0 | 42500
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Order Contingency (+10% Areal) | N/A | 8.5 | N/A | 500 | 4250 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 4250 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4250
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 2 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 52.5
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 1500
Hysol Adhesive Pre-Production | Hysol 9396 | 3 | Order | 500 | 1500 | 0 | 1 | 0 | 0 | 0 | hours | 351 | 3 | 4851 | B | PT | BPT2010 | B1.5.1.1.22010 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2010 | 0 | 3 | 0 | 0 | 0 | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Production | Hysol 9396 | 5 | Order | 500 | 2500 | 0 | 1 | 0 | 0 | 0 | hours | 284.31 | 3 | 7784.31 | B | PD | BPD2011 | B1.5.1.22011 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2011 | 0 | 3 | 0 | 0 | 0 | 7500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Production | Hysol 9396 | 5 | Order | 500 | 2500 | 0 | 1 | 0 | 0 | 0 | hours | 284.31 | 3 | 7784.31 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 3 | 0 | 0 | 0 | 7500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables Base 2011 | Expendable | 1 | Order | 6000 | 6000 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 6379.08 | B | PD | BPD2011 | B1.5.1.22011 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2011 | 0 | 4 | 0 | 0 | 0 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables Base 2012 | Expendable | 1 | Order | 5000 | 5000 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 5379.08 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 4 | 0 | 0 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables Contingency | Expendable | 1 | Order | 2000 | 2000 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 2379.08 | C | PD | CPD2012 | C1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 0 | 0 | 2000
Material Batches Subtotal | [11 empty] | 17820.9 | Base Labor | [13 empty] | 0 | 101 | 0 | 58 | 0 |  | 215355 | 231973.77 |  | 128816.2 | 0 | 60 | 0 | 40 | 0 |  | 118270
East Support Cylinder | [12 empty] | .
Shell Laminate | [12 empty] | .
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 24 | 0 | 8 | 0 | hours | 3246.48 | 1 | 3246.48 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 200 | 0 | 24 | 0 | hours | 21870 | 1 | 24180 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 200 | 0 | 24 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 24 | 0 | 8 | 0 | hours | 3246.48 | 1 | 3246.48 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 200 | 0 | 24 | 0 | hours | 21870 | 1 | 24180 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 200 | 0 | 24 | 0 | 2310
Flange Laminates | [10 empty] | Sum | 25116.48 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Conical Tranistion Plate Laminates | [10 empty] | Sum | 4928.04 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cone Laminate | Bagging | 1 | N/A | 105 | 105 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2379.48 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 0 | 0 | 0 | 105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Large Flange Base | Bagging | 2 | N/A | 105 | 210 | 4 | 16 | 0 | 1 | 0 | hours | 2046.06 | 1 | 2256.06 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 4 | 16 | 0 | 1 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Small Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 1083.78 | 1 | 1188.78 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 2 | 8 | 0 | 1 | 0 | 105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Cone Laminate | Bagging | 1 | N/A | 105 | 105 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2379.48 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 105
Large Flange Base | Bagging | 2 | N/A | 105 | 210 | 4 | 16 | 0 | 1 | 0 | hours | 2046.06 | 1 | 2256.06 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 16 | 0 | 1 | 0 | 210
Small Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 1083.78 | 1 | 1188.78 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 1 | 0 | 105
Interface Parts | [10 empty] | Sum | 7892.64 | Base Labor
Termination Flange | Aluminum | 200 | lb | 8 | 1600 | 40 | 0 | 0 | 0 | 0 | hours | 4082.4 | 1 | 5682.4 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 40 | 0 | 0 | 0 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Threaded Inserts | Aluminum | 0.1 | lb | 8 | 0.8 | 0.2 | 0 | 0 | 0 | 0 | hours | 1020.6 | 50 | 1060.6 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 10 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Tool Modifications (from WSC) | [10 empty] | Sum | 5103 | Base Labor
Clocking Plates Modification (Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 2916 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Clocking Plates Modification | Labor | 0 | N/A | 0 | 0 | 40 | 8 | 0 | 0 | 0 | hours | 4840.56 | 1 | 4840.56 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 40 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cone Plate Modification (Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 1944 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cone Plate Modification | Labor | 0 | N/A | 0 | 0 | 32 | 8 | 0 | 0 | 0 | hours | 4024.08 | 1 | 4024.08 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 32 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly/Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 4 | 0 | hours | 3576.96 | 1 | 3576.96 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 8 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ESC Assembly | [10 empty] | Sum | 17301.6 | Base Labor
Cone Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ESC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | B | PD | BPD2011 | B1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 24 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cone Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
ESC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | C | PD | CPD2011 | C1.5.1.1.22011 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 8 | 8 | 0 | 0
ESC Sub Total | [11 empty] | 71228.16 | Base Labor | [13 empty] | 132 | 464 | 16 | 100 | 0 |  | 4790 | 76018.16 |  | 49367.58 | 8 | 406 | 8 | 52 | 0 |  | 2940
[11 empty] | Sum | 10886.4 | Base Labor
Outer Support Cylinder | [12 empty] | .
Tooling OSC Prototype (MSC PIT Tool Development) | [12 empty] | .
Shell Prototype Tool | [12 empty] | .
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 160 | 0 | hours | 24000 | 1 | 24000 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Material CTE Study | Labor | 0 | N/A | 0 | 0 | 2 | 8 | 0 | 0 | 0 | hours | 1188 | 1 | 1188 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 2 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Fabrication | Labor | 0 | N/A | 0 | 0 | 24 | 8 | 0 | 0 | 0 | hours | 3960 | 1 | 3960 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 24 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 504 | 1 | 1704 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 4 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 8 | 0 | 0 | 0 | hours | 2391.12 | 1 | 2391.12 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 8 | 0 | 0 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1200
Shell Production Tool (same as MSC PIT) | [10 empty] | Sum | 29652 | Sum | 0
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Fabrication | Labor | 0 | N/A | 0 | 0 | 60 | 8 | 0 | 0 | 0 | hours | 6881.76 | 1 | 6881.76 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 60 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 4 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 24 | 0 | 0 | 0 | 0 | hours | 2449.44 | 1 | 2449.44 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 0 | 0 | 0 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1200
Flange Tooling | [10 empty] | Sum | 12150 | Sum | 30852
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 18000 | 1 | 18000 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool | Aluminum | 40 | lb | 8 | 320 | 24 | 8 | 0 | 0 | 0 | hours | 3960 | 1 | 4280 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 24 | 8 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool (Contingency) | Aluminum | 40 | lb | 8 | 320 | 24 | 8 | 0 | 0 | 0 | hours | 3207.6 | 1 | 3527.6 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 8 | 0 | 0 | 0 | 320
Bond Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 16 | 0 | 0 | 0 | hours | 3149.28 | 1 | 3469.28 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 16 | 16 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 16 | 0 | 0 | 0 | hours | 3149.28 | 1 | 3469.28 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 16 | 16 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Laminate Prototype | [10 empty] | Sum | 28258.56 | Sum
Engineering Oversight | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 18000 | 1 | 18000 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 2808 | 3 | 2808 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 48 | 0 | 0 | 0 | hours | 16848 | 3 | 23778 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 144 | 0 | 0 | 0 | 6930 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Laminate 2011 (Inintial Install) | [10 empty] | Sum | 37656 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 120 | 0 | 16 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | C | PD | CPD2011 | C1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 16 | 0 | 2310
Shell Laminate 2012 for SSD | [10 empty] | Sum | 15804.72 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 120 | 0 | 16 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 16 | 0 | 2310
Flange Laminates Prototype | [10 empty] | Sum | 15804.72 | Base Labor
Engineering Oversight | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 936 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 1872 | 2 | 2082 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 0 | 16 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 2376 | 2 | 2586 | B | PT | BPT2010 | B1.5.1.1.32010 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2010 | 4 | 16 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Laminates 2011 (Initial Install) | [10 empty] | Sum | 11184 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Flange Laminates 2012 for SSD | [10 empty] | Sum | 4928.04 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Interface Parts | [10 empty] | Sum | #REF! | Base Labor
Hardware | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 1137.24 | 3 | 2637.24 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 12 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Threaded Inserts | Aluminum | 0.1 | lb | 8 | 0.8 | 0.2 | 0 | 0 | 0 | 0 | hours | 1020.6 | 50 | 1060.6 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 10 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Tool (not shared with MSC) | [10 empty] | Sum | 2157.84 | Base Labor
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Clocking Plates MFG | Aluminum | 400 | lb | 8 | 3200 | 60 | 16 | 0 | 0 | 0 | hours | 7639.92 | 1 | 10839.92 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 60 | 16 | 0 | 0 | 0 | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Space Bars | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 0 | 0 | hours | 4082.4 | 1 | 4882.4 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 40 | 0 | 0 | 0 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly/Survey | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 8 | 8 | 0 | hours | 5579.28 | 1 | 5579.28 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 40 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSC Assembly | [10 empty] | Sum | 24591.6 | Base Labor
Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 16 | 0 | hours | 5734.8 | 1 | 5734.8 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 40 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 8 | 0 | hours | 6492.96 | 2 | 6492.96 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 48 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSC Assembly and Survey 2011 | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 24 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 16 | 0 | hours | 5734.8 | 1 | 5734.8 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 16 | 0 | 0
Termination Flange Assembly Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 8 | 0 | hours | 3246.48 | 1 | 3246.48 | C | PD | CPD2012 | C1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 8 | 0 | 0
Bonded Assembly 2013 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 16 | 0 | hours | 5734.8 | 1 | 5734.8 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 40 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 4548.96 | 2 | 4548.96 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 48 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
OSC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 24 | 8 | 0 | hours | 5695.92 | 1 | 5695.92 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 24 | 24 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly 2013 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 16 | 0 | hours | 5734.8 | 1 | 5734.8 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 16 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
OSC Sub Total | [11 empty] | 162523.92 | Base Labor | [13 empty] | 272 | 916 | 40 | 672 | 0 |  | 18350 | 218650.04 |  | 67568.76 | 76 | 460 | 0 | 92 | 0 |  | 5040
Middle Support Cylinder (PST Portion) | [12 empty] | .
Tooling PST (PIT shared w/OSC) | [12 empty] | .
Shell Prototype Tool | [12 empty] | .
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Material CTE Study | Labor | 0 | N/A | 0 | 0 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 962.28 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 2 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Fabrication | Labor | 0 | N/A | 0 | 0 | 24 | 8 | 0 | 0 | 0 | hours | 3207.6 | 1 | 3207.6 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 24 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 4 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 8 | 0 | 0 | 0 | hours | 2391.12 | 1 | 2391.12 | C | PD | CPD2011 | C1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 8 | 0 | 0 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | C | PD | CPD2011 | C1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1200
Shell Production Tool PST | [10 empty] | Sum | 14298.12 | Sum | 0
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Fabrication | Labor | 0 | N/A | 0 | 0 | 40 | 8 | 0 | 0 | 0 | hours | 4840.56 | 1 | 4840.56 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 40 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 4 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 16 | 0 | 0 | 0 | 0 | hours | 1632.96 | 1 | 1632.96 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1200
Flange Tooling | [10 empty] | Sum | 10108.8 | Sum | 15498.12
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 18000 | 1 | 18000 | B | PT | BPT2010 | B1.5.1.2.42010 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2010 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool | Aluminum | 40 | lb | 8 | 320 | 24 | 8 | 0 | 0 | 0 | hours | 3960 | 1 | 4280 | B | PT | BPT2010 | B1.5.1.2.42010 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2010 | 24 | 8 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool (Contingency) | Aluminum | 40 | lb | 8 | 320 | 24 | 8 | 0 | 0 | 0 | hours | 3207.6 | 1 | 3527.6 | C | PD | CPD2011 | C1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 8 | 0 | 0 | 0 | 320
Bond Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 16 | 0 | 0 | 0 | hours | 3149.28 | 1 | 3469.28 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 16 | 16 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Trim Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 16 | 0 | 0 | 0 | hours | 3149.28 | 1 | 3469.28 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 16 | 16 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Laminate Prototype PST | [10 empty] | Sum | 28258.56 | Sum
Engineering Oversight | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 2274.48 | 3 | 2274.48 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 48 | 0 | 0 | 0 | hours | 13646.88 | 3 | 20576.88 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 144 | 0 | 0 | 0 | 6930 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Laminate 2011 PST (Engineering Run) | [10 empty] | Sum | 30501.36 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 120 | 0 | 16 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 16 | 0 | 2310
Shell Laminate 2012 for IST | [10 empty] | Sum | 15804.72 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2013 | B1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | B | PD | BPD2013 | B1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 120 | 0 | 16 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2013 | C1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | C | PD | CPD2013 | C1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 16 | 0 | 2310
Flange Laminates Prototype | [10 empty] | Sum | 15804.72 | Base Labor
Engineering Oversight | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 1516.32 | 2 | 1726.32 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 0 | 16 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 1924.56 | 2 | 2134.56 | B | PD | BPD2011 | B1.5.1.2.42011 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2011 | 4 | 16 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Laminates 2011 (Initial Install) | [10 empty] | Sum | 9059.04 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2012 | C1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Flange Laminates 2012 for SSD | [10 empty] | Sum | 4928.04 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2012 | B1.5.1.2.42012 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2012 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2013 | C1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2013 | C1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2013 | C1.5.1.2.42013 | 1.5.1.2.4 | Pixel Support Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Interface Parts | [10 empty] | Sum | 4928.04 | Base Labor
Hardware | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 1137.24 | 3 | 2637.24 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 12 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Threaded Inserts | Aluminum | 0.1 | lb | 8 | 0.8 | 0.2 | 0 | 0 | 0 | 0 | hours | 1020.6 | 50 | 1060.6 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 10 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Tool | [10 empty] | Sum | 2157.84 | Base Labor
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Clocking Plates MFG | Aluminum | 200 | lb | 8 | 1600 | 40 | 16 | 0 | 0 | 0 | hours | 5598.72 | 1 | 7198.72 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 40 | 16 | 0 | 0 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Space Bars | Steel | 100 | lb | 4 | 400 | 24 | 0 | 0 | 0 | 0 | hours | 2449.44 | 1 | 2849.44 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 24 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly/Survey | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 8 | 16 | 0 | hours | 6551.28 | 1 | 6551.28 | B | PD | BPD2011 | B1.5.1.1.32011 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2011 | 0 | 40 | 8 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PST Assembly 2011 | [10 empty] | Sum | 24319.44 | Base Labor
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 0 | 0 | hours | 6181.92 | 2 | 6181.92 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 48 | 16 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PIT Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 0 | 0 | hours | 3090.96 | 1 | 3090.96 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 24 | 8 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pixel Mount Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2012 | B1.5.1.1.32012 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2012 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PST Assembly 2012 | [10 empty] | Sum | 16407.36 | Base Labor
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 0 | 0 | hours | 6181.92 | 2 | 6181.92 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 48 | 16 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PIT Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 0 | 0 | hours | 3090.96 | 1 | 3090.96 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 24 | 8 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pixel Mount Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2013 | B1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PST Assembly Contingency | [10 empty] | Sum | 16407.36 | Base Labor
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 0 | 0 | hours | 6181.92 | 2 | 6181.92 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 16 | 0 | 0 | 0
PIT Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 0 | 0 | hours | 3090.96 | 1 | 3090.96 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 8 | 0 | 0 | 0
Pixel Mount Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2013 | C1.5.1.1.32013 | 1.5.1.1.3 | Outer Support Cylinder (OSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
PST Sub Total | [11 empty] | 192983.4 | Base Labor | [13 empty] | 216 | 884 | 56 | 636 | 0 |  | 19710 | 208521 |  | 68889.08 | 68 | 428 | 24 | 92 | 0 |  | 7760
Middle Support Cylinder (PIT Portion) | [10 empty] | Sum | 0 | Base Labor
Shell Laminate 2011 PIT (Engineering Run) | [12 empty] | .
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 120 | 0 | 16 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 16 | 0 | 2310
Shell Laminate 2012 for IST | [10 empty] | Sum | 15804.72 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 16 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 120 | 0 | 16 | 0 | 2310 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 2488.32 | 1 | 2488.32 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 8 | 0 | 0
Shell Lamination | Bagging | 22 | N/A | 105 | 2310 | 0 | 120 | 0 | 16 | 0 | hours | 13316.4 | 1 | 15626.4 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 16 | 0 | 2310
Flange Laminates Prototype | [10 empty] | Sum | 15804.72 | Base Labor
Engineering Oversight | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.5.1.2.12011 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2011 | B1.5.1.2.12011 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2011 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 1516.32 | 2 | 1726.32 | B | PD | BPD2011 | B1.5.1.2.12011 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2011 | 0 | 16 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 1924.56 | 2 | 2134.56 | B | PD | BPD2011 | B1.5.1.2.12011 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2011 | 4 | 16 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Laminates 2011 (Initial Install) | [10 empty] | Sum | 9059.04 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Flange Laminates 2012 for SSD | [10 empty] | Sum | 4928.04 | Base Labor
Ply Trim and Kit | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 1 | 0 | hours | 1759.32 | 2 | 1969.32 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Base | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 1 | 0 | hours | 2167.56 | 2 | 2377.56 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 4 | 16 | 0 | 2 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 2 | 0 | hours | 811.62 | 1 | 811.62 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6 | 0 | 2 | 0 | 0
Flange Contingency | Bagging | 1 | N/A | 105 | 105 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 863.16 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 105
Flange Base Contingnency | Bagging | 1 | N/A | 105 | 105 | 2 | 8 | 0 | 0 | 0 | hours | 962.28 | 1 | 1067.28 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 8 | 0 | 0 | 0 | 105
Transition Plate (Aluminum) 2011 | [10 empty] | Sum | 4928.04 | Base Labor
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Fabrication | Aluminum | 200 | lb | 8 | 1600 | 60 | 16 | 0 | 0 | 0 | hours | 7639.92 | 1 | 9239.92 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 60 | 16 | 0 | 0 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Fabrication Contingency | Aluminum | 200 | lb | 8 | 1600 | 60 | 16 | 0 | 0 | 0 | hours | 7639.92 | 1 | 9239.92 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 60 | 16 | 0 | 0 | 0 | 1600
Transition Plate (2012) | [10 empty] | Sum | 12499.92 | Base Labor
Part Fabrication | Aluminum | 200 | lb | 8 | 1600 | 60 | 16 | 0 | 0 | 0 | hours | 7639.92 | 1 | 9239.92 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 60 | 16 | 0 | 0 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface Parts | [10 empty] | Sum | 7639.92 | Base Labor
Hardware | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 879.08 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 4 | 0 | 0 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 758.16 | 2 | 1758.16 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 8 | 0 | 0 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Threaded Inserts | Aluminum | 0.1 | lb | 8 | 0.8 | 0.2 | 0 | 0 | 0 | 0 | hours | 1020.6 | 50 | 1060.6 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 10 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Threaded Inserts | Aluminum | 0.1 | lb | 8 | 0.8 | 0.2 | 0 | 0 | 0 | 0 | hours | 1020.6 | 50 | 1060.6 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 10 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Tool | [10 empty] | Sum | 3178.44 | Base Labor
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 2916 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Space Bars | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 0 | 0 | hours | 4082.4 | 1 | 4882.4 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 40 | 0 | 0 | 0 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly/Survey | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 8 | 8 | 0 | hours | 5579.28 | 1 | 5579.28 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 40 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly 2011 | [10 empty] | Sum | 12577.68 | Base Labor
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | B | PD | BPD2012 | B1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 24 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
MSC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | C | PD | CPD2012 | C1.5.1.2.12012 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 8 | 8 | 0 | 0
MSC Assembly 2012 | [10 empty] | Sum | 8611.92 | Base Labor
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | B | PD | BPD2013 | B1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 24 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Termination Flange Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
Flange Bonded Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2274.48 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 0
MSC Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | C | PD | CPD2013 | C1.5.1.2.12013 | 1.5.1.2.1 | Pixel Insertion Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 8 | 8 | 0 | 0
MSC PIT Sub Total | [11 empty] | 103644.36 | Base Labor | [13 empty] | 192 | 620 | 24 | 188 | 0 |  | 11460 | 115104.36 |  | 73037.32 | 64 | 476 | 16 | 108 | 0 |  | 6640
[11 empty] | Sum | 8611.92 | Base Labor
Beam Pipe Mechanics | [10 empty] | Sum | 0 | Base Labor
Beam Pipe Model | [12 empty] | .
Design Engineering for Fabrication | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPDSTAR | B1.5.1.3STAR | 1.5.1.3 | Beam Pipe Mechanics | [5 empty] | STAR | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Prototypes, Conflat | Contract | 1 | N/A | 5000 | 5000 | 0 | 0 | 0 | 24 | 0 | hours | 0 | 0 | 0 | B | PD | BPDSTAR | B1.5.1.3.1STAR | 1.5.1.3.1 | Beam Pipe Model | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Flange Prototypes, Helicoflex | Contract | 1 | N/A | 5000 | 5000 | 0 | 0 | 0 | 24 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.5.1.3.12010 | 1.5.1.3.1 | Beam Pipe Model | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Engineering for Beam Pipe Mockup | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | B | PD | BPD2010 | B1.5.1.3.12010 | 1.5.1.3.1 | Beam Pipe Model | [5 empty] | 2010 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Beam Pipe Mockup | Aluminum | 150 | lb | 8 | 1200 | 12 | 40 | 0 | 6 | 0 | hours | 5744.52 | 1 | 6944.52 | B | PD | BPD2011 | B1.5.1.3.12011 | 1.5.1.3.1 | Beam Pipe Model | [5 empty] | 2011 | 12 | 40 | 0 | 6 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Supports for Mockup in ITB | Aluminum | 75 | lb | 8 | 600 | 12 | 40 | 0 | 6 | 0 | hours | 5744.52 | 1 | 6344.52 | B | PD | BPD2011 | B1.5.1.3.12011 | 1.5.1.3.1 | Beam Pipe Model | [5 empty] | 2011 | 12 | 40 | 0 | 6 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Alternate Beam Pipe Supports | [10 empty] | Sum | 33359.04 | Base Labor
Integration into STAR | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 32 | 0 | hours | 3888 | 1 | 3888 | C | PD | CPDSTAR | C1.5.1.3.3STAR | 1.5.1.3.3 | Alternate Beam Pipe Support | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 32 | 0 | 0
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2011 | C1.5.1.3.32011 | 1.5.1.3.3 | Alternate Beam Pipe Support | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Part Fabrication | Aluminum | 100 | lb | 8 | 800 | 8 | 40 | 0 | 4 | 0 | hours | 5093.28 | 1 | 5893.28 | C | PD | CPD2011 | C1.5.1.3.32011 | 1.5.1.3.3 | Alternate Beam Pipe Support | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 40 | 0 | 4 | 0 | 800
Hardware | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 879.08 | C | PD | CPD2011 | C1.5.1.3.32011 | 1.5.1.3.3 | Alternate Beam Pipe Support | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 0 | 0 | 500
Installation | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3032.64 | 1 | 3032.64 | C | PD | CPD2011 | C1.5.1.3.32011 | 1.5.1.3.3 | Alternate Beam Pipe Support | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 0 | 0 | 0
Internal Beam Pipe Supports (Low Mass) | [10 empty] | Sum | 0 | Base Labor
Integration into STAR | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 32 | 0 | hours | 3888 | 1 | 3888 | B | PD | BPDSTAR | B1.5.1.3.2STAR | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | STAR | 0 | 0 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Engineering Collars | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Collar Prototypes | Vespel | 2 | lb | 600 | 1200 | 8 | 8 | 0 | 4 | 0 | hours | 4121.28 | 2 | 6521.28 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 16 | 16 | 0 | 8 | 0 | 2400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Collar Production | Vespel | 2 | lb | 600 | 1200 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 3 | 3600 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 3600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Collar Production Contingency | Vespel | 2 | lb | 600 | 1200 | 24 | 0 | 0 | 12 | 0 | hours | 11722.32 | 3 | 15322.32 | C | PD | CPD2011 | C1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 72 | 0 | 0 | 36 | 0 | 3600
Sliding Support Prototypes | Aluminum | 15 | lb | 8 | 120 | 8 | 8 | 0 | 4 | 0 | hours | 2060.64 | 1 | 2180.64 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 8 | 8 | 0 | 4 | 0 | 120 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sliding Support Production | Aluminum | 25 | lb | 8 | 200 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 200 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sliding Support Production Contingency | Aluminum | 25 | lb | 8 | 200 | 16 | 0 | 0 | 8 | 0 | hours | 2604.96 | 1 | 2804.96 | C | PD | CPD2011 | C1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 8 | 0 | 200
Design Engineering Fixed Support Tool | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Fixed Support Tool | Aluminum | 50 | lb | 8 | 400 | 8 | 8 | 0 | 4 | 0 | hours | 2060.64 | 1 | 2460.64 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 8 | 8 | 0 | 4 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Fixed Support Production | Bagging | 1 | m^2 | 105 | 105 | 0 | 16 | 0 | 2 | 0 | hours | 3518.64 | 2 | 3728.64 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 32 | 0 | 4 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Fixed Support Production Contingency | Bagging | 1 | m^2 | 105 | 105 | 0 | 16 | 0 | 2 | 0 | hours | 3518.64 | 2 | 3728.64 | C | PD | CPD2011 | C1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 4 | 0 | 210
Hardware 2011 | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 879.08 | B | PD | BPD2011 | B1.5.1.3.22011 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2011 | 0 | 4 | 0 | 0 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware 2013 | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 879.08 | B | PD | BPD2013 | B1.5.1.3.22013 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2013 | 0 | 4 | 0 | 0 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation 2011 | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3032.64 | 1 | 3032.64 | B | PD | BPD2012 | B1.5.1.3.22012 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2012 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation 2013 | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3032.64 | 1 | 3032.64 | B | PD | BPD2014 | B1.5.1.3.22014 | 1.5.1.3.2 | Internal Support (Low Mass) | [5 empty] | 2014 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
External Beam Pipe Supports | [10 empty] | Sum | 34622.64 | Base Labor
Integration into STAR | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | B | PD | BPDSTAR | B1.5.1.3.4STAR | 1.5.1.3.4 | External Beam Pipe Support | [5 empty] | STAR | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.5.1.3.42011 | 1.5.1.3.4 | External Beam Pipe Support | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
I-Beam Modification | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 20 | 0 | hours | 6220.8 | 1 | 6220.8 | B | PD | BPDSTAR | B1.5.1.3.4STAR | 1.5.1.3.4 | External Beam Pipe Support | [5 empty] | STAR | 0 | 40 | 0 | 20 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Part Fabrication (Temp Supports) | Aluminum | 100 | lb | 8 | 800 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 800 | B | PD | BPD2011 | B1.5.1.3.42011 | 1.5.1.3.4 | External Beam Pipe Support | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 500 | 500 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 879.08 | B | PD | BPD2011 | B1.5.1.3.42011 | 1.5.1.3.4 | External Beam Pipe Support | [5 empty] | 2011 | 0 | 4 | 0 | 0 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3032.64 | 1 | 3032.64 | B | PD | BPD2011 | B1.5.1.3.42011 | 1.5.1.3.4 | External Beam Pipe Support | [5 empty] | 2011 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Tool (Beam Pipe Support during Assembly) | [10 empty] | Sum | 21782.52 | Base Labor
Design Engineering | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 2916 | B | PD | BPD2011 | B1.5.1.32011 | 1.5.1.3 | Beam Pipe Mechanics | [5 empty] | 2011 | 0 | 0 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Support Beams | Steel | 50 | lb | 4 | 200 | 2 | 8 | 0 | 1 | 0 | hours | 4335.12 | 4 | 5135.12 | B | PD | BPD2011 | B1.5.1.32011 | 1.5.1.3 | Beam Pipe Mechanics | [5 empty] | 2011 | 8 | 32 | 0 | 4 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly 2012 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 8 | 0 | hours | 4762.8 | 1 | 4762.8 | B | PD | BPD2011 | B1.5.1.32011 | 1.5.1.3 | Beam Pipe Mechanics | [5 empty] | 2011 | 0 | 40 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly 2013 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 8 | 0 | hours | 4762.8 | 1 | 4762.8 | B | PD | BPD2014 | B1.5.1.32014 | 1.5.1.3 | Beam Pipe Mechanics | [5 empty] | 2014 | 0 | 40 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insertable Bake Out Jacket | [10 empty] | Sum | 16776.72 | Base Labor
Bake Out Jacket Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bake Out Jacket Design Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 60 | 0 | 0
Carraige Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Heating Elements | Contract | 1 | Order | 5000 | 5000 | 0 | 0 | 0 | 24 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Heating Elements Contingency | Contract | 1 | Order | 5000 | 5000 | 0 | 0 | 0 | 24 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2012 | C1.5.1.3.52012 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Materials/Structure | Insulation | 1 | Order | 1500 | 1500 | 32 | 0 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Materials/Structure Contingency | Insulation | 1 | Order | 1500 | 1500 | 32 | 0 | 0 | 8 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2012 | C1.5.1.3.52012 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Assembly Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 8 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2012 | C1.5.1.3.52012 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Carraige Components | Aluminum | 150 | lb | 8 | 1200 | 40 | 40 | 0 | 16 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 1000 | 1000 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Carraige Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 16 | 0 | hours | 5734.8 | 1 | 5734.8 | B | PD | BPDSTAR | B1.5.1.3.5STAR | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | STAR | 0 | 40 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Integrated Bake Out Jackets | [10 empty] | Sum | 25174.8 | Base Labor
Mid Section Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | B | PD | BPD2010 | B1.5.1.3.52010 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2010 | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mid Section Design Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Extension Jacket Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Extension Jacket Design Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 60 | 0 | 0
Heating Elements Large Cylindrical | Contract | 1 | Each | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Heating Elements Large Cylindrical Contingency | Contract | 1 | Each | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Heating Elements Large Conical | Contract | 1 | Each | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Heating Elements Large Cylindrical Contingency | Contract | 1 | Each | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Materials | Insulation | 1 | Order | 2500 | 2500 | 0 | 0 | 0 | 8 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Assembly (CERN) | Contract | 0 | N/A | 15000 | 0 | 0 | 0 | 0 | 20 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Jacket Assembly (CERN) Contingency | Contract | 0 | N/A | 15000 | 0 | 0 | 0 | 0 | 20 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 2000 | 2000 | 0 | 8 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bake Out Test | [10 empty] | Sum | 24300 | Base Labor
Test Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Technical Support | Labor | 0 | N/A | 0 | 0 | 0 | 80 | 0 | 0 | 0 | hours | 7581.6 | 1 | 7581.6 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 80 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Technical Support Contingency | Labor | 0 | N/A | 0 | 0 | 0 | 80 | 0 | 0 | 0 | hours | 7581.6 | 1 | 7581.6 | C | PD | CPD2011 | C1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 80 | 0 | 0 | 0 | 0
Support Equipment Fabrication | Labor | 0 | N/A | 0 | 0 | 8 | 0 | 0 | 4 | 0 | hours | 1302.48 | 1 | 1302.48 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 8 | 0 | 0 | 4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 1000 | 1000 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 1379.08 | B | PD | BPD2011 | B1.5.1.3.52011 | 1.5.1.3.5 | Bake Out Equipment | [5 empty] | 2011 | 0 | 4 | 0 | 0 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Beam Pipe Sub Total | [11 empty] | 174998.88 | Base Labor | [13 empty] | 72 | 528 | 0 | 968 | 0 |  | 12830 | 187828.88 |  | 72290.52 | 96 | 188 | 0 | 324 | 0 |  | 5310
Assembly of Global Supports | [10 empty] | Sum | 18983.16 | Base Labor
MSC Assembly | [12 empty] | .
MSC Assembly Tool Design | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPD2011 | B1.5.3.12011 | 1.5.3.1 | MSC Assembly | [5 empty] | 2011 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly Tool Design Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2012 | C1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
MSC Tooling Fabrication | Aluminum | 800 | lb | 8 | 6400 | 24 | 40 | 0 | 12 | 0 | hours | 7698.24 | 1 | 14098.24 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 24 | 40 | 0 | 12 | 0 | 6400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Tooling Fabrication Contingency | Aluminum | 200 | lb | 8 | 1600 | 40 | 20 | 0 | 0 | 0 | hours | 5977.8 | 1 | 7577.8 | C | PD | CPD2012 | C1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 20 | 0 | 0 | 0 | 1600
MSC Tooling Assembly (LBL) | Labor | 1 | N/A | 5000 | 5000 | 0 | 80 | 0 | 24 | 0 | hours | 10497.6 | 1 | 15497.6 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 80 | 0 | 24 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 1000 | 1000 | 0 | 4 | 0 | 0 | 0 | hours | 379.08 | 1 | 1379.08 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 4 | 0 | 0 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly (LBL) 2011 | Labor | 0 | N/A | 0 | 0 | 0 | 120 | 0 | 40 | 0 | hours | 16232.4 | 1 | 16232.4 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 120 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Tooling Assembly (BNL w/LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Tooling Assembly (BNL w/STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPDSTAR | B1.5.3.1STAR | 1.5.3.1 | MSC Assembly | [5 empty] | STAR | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly (at BNL, LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly (at BNL, STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 0 | 0 | hours | 3790.8 | 1 | 3790.8 | B | PD | BPDSTAR | B1.5.3.1STAR | 1.5.3.1 | MSC Assembly | [5 empty] | STAR | 0 | 40 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Tooling Assembly (BNL w/LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPD2014 | B1.5.3.12014 | 1.5.3.1 | MSC Assembly | [5 empty] | 2014 | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Tooling Assembly (BNL w/STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPDSTAR | B1.5.3.1STAR | 1.5.3.1 | MSC Assembly | [5 empty] | STAR | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly (at BNL, LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPD2014 | B1.5.3.12014 | 1.5.3.1 | MSC Assembly | [5 empty] | 2014 | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly (at BNL, STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 0 | 0 | hours | 3790.8 | 1 | 3790.8 | B | PD | BPDSTAR | B1.5.3.1STAR | 1.5.3.1 | MSC Assembly | [5 empty] | STAR | 0 | 40 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Inner Detector Support Assembly | [10 empty] | Sum | 97209.72 | Base Labor
Integration into STAR Assembly Hall | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 32 | 0 | hours | 3888 | 1 | 3888 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 0 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly Tool Design | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPD2011 | B1.5.3.22011 | 1.5.3.2 | IDS Assembly | [5 empty] | 2011 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly Tool Design Contingency | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2011 | C1.5.3.22011 | 1.5.3.2 | IDS Assembly | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
IDS Tooling Fabrication | Aluminum | 1500 | lb | 8 | 12000 | 32 | 40 | 0 | 16 | 0 | hours | 9000.72 | 1 | 21000.72 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 32 | 40 | 0 | 16 | 0 | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Tooling Fabrication Contingency | Aluminum | 200 | lb | 8 | 1600 | 60 | 20 | 0 | 0 | 0 | hours | 8019 | 1 | 9619 | C | PD | CPD2012 | C1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 60 | 20 | 0 | 0 | 0 | 1600
IDS Tooling Assembly (LBL) | Labor | 1 | N/A | 5000 | 5000 | 0 | 80 | 0 | 24 | 0 | hours | 10497.6 | 1 | 15497.6 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 80 | 0 | 24 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Order | 1 | N/A | 2000 | 2000 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 2758.16 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 0 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly (LBL) 2011 | Labor | 0 | N/A | 0 | 0 | 0 | 120 | 0 | 40 | 0 | hours | 16232.4 | 1 | 16232.4 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 120 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Tooling Assembly (BNL w/LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Tooling Assembly (BNL w/STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly (at BNL, LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 120 | 0 | 24 | 0 | hours | 14288.4 | 1 | 14288.4 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 120 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly (at BNL, STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 0 | 0 | hours | 3790.8 | 1 | 3790.8 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 40 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Tooling Assembly (BNL w/LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPD2013 | B1.5.3.22013 | 1.5.3.2 | IDS Assembly | [5 empty] | 2013 | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Tooling Assembly (BNL w/STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 24 | 0 | hours | 6706.8 | 1 | 6706.8 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 40 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly (at BNL, LBL Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 120 | 0 | 24 | 0 | hours | 14288.4 | 1 | 14288.4 | B | PD | BPD2013 | B1.5.3.22013 | 1.5.3.2 | IDS Assembly | [5 empty] | 2013 | 0 | 120 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly (at BNL, STAR Labor) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 0 | 0 | hours | 3790.8 | 1 | 3790.8 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 40 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Sub Total | [11 empty] | 215152.2 | Base Labor | [13 empty] | 56 | 1292 | 0 | 716 | 0 |  | 31400 | 246552.2 |  | 26916.8 | 100 | 40 | 0 | 80 | 0 |  | 3200
Installation | [10 empty] | Sum | 49572 | Base Labor
Insertion into STAR of IDS | [12 empty] | .
Lift Fixture modification design | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPDSTAR | B1.5.5STAR | 1.5.5 | Installation | [5 empty] | STAR | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lift Fixture modification contingency | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 24 | 0 | hours | 6998.4 | 1 | 7798.4 | C | PD | CPD2012 | C1.5.52012 | 1.5.5 | Installation | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 0 | 0 | 24 | 0 | 800
Cradle modification design | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPDSTAR | B1.5.5STAR | 1.5.5 | Installation | [5 empty] | STAR | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cradle modification contingency | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 24 | 0 | hours | 6998.4 | 1 | 7798.4 | C | PD | CPD2012 | C1.5.52012 | 1.5.5 | Installation | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 0 | 0 | 24 | 0 | 800
Technical Support LBNL 2012 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 20 | 0 | hours | 6220.8 | 1 | 6220.8 | B | PD | BPD2012 | B1.5.52012 | 1.5.5 | Installation | [5 empty] | 2012 | 0 | 40 | 0 | 20 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Technical Support STAR 2012 | Labor | 0 | N/A | 0 | 0 | 0 | 60 | 0 | 0 | 0 | hours | 5686.2 | 1 | 5686.2 | B | PD | BPDSTAR | B1.5.5STAR | 1.5.5 | Installation | [5 empty] | STAR | 0 | 60 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Technical Support LBNL 2013 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 20 | 0 | hours | 6220.8 | 1 | 6220.8 | B | PD | BPD2012 | B1.5.52012 | 1.5.5 | Installation | [5 empty] | 2012 | 0 | 40 | 0 | 20 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Technical Support STAR 2013 | Labor | 0 | N/A | 0 | 0 | 0 | 60 | 0 | 0 | 0 | hours | 5686.2 | 1 | 5686.2 | B | PD | BPDSTAR | B1.5.5STAR | 1.5.5 | Installation | [5 empty] | STAR | 0 | 60 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Technical Support LBNL 2014 | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 20 | 0 | hours | 6220.8 | 1 | 6220.8 | B | PD | BPD2014 | B1.5.52014 | 1.5.5 | Installation | [5 empty] | 2014 | 0 | 40 | 0 | 20 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Technical Support STAR 2014 | Labor | 0 | N/A | 0 | 0 | 0 | 60 | 0 | 0 | 0 | hours | 5686.2 | 1 | 5686.2 | B | PD | BPDSTAR | B1.5.5STAR | 1.5.5 | Installation | [5 empty] | STAR | 0 | 60 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Service Termination and Testing | [10 empty] | Sum | 45441 | Base Labor
Integration into STAR | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
IFC Gas Service termination | Labor | 0.03 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3032.64 | 1 | 3032.64 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shroud Bias Termination/Test | Labor | 0.03 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3032.64 | 1 | 3032.64 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Beam Pipe Load Transfer/Survey | Labor | 0 | lb | 0 | 0 | 0 | 40 | 0 | 0 | 0 | hours | 3790.8 | 1 | 3790.8 | B | PD | BPDSTAR | B1.5.3.2STAR | 1.5.3.2 | IDS Assembly | [5 empty] | STAR | 0 | 40 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assembly Sub Total | [11 empty] | 60157.08 | Base Labor | [13 empty] | 0 | 404 | 0 | 180 | 0 |  | 0 | 60157.08 |  | 15596.8 | 80 | 0 | 0 | 48 | 0 |  | 1600
[11 empty] | Sum | 14716.08 | Base Labor
Shipping (MSC 2011)
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 473.85 | 1 | 623.85 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 5 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 458.24 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (MSC Tooling 2011) | [11 empty] | 1640.25 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 80 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 200 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 30 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 947.7 | 2 | 1247.7 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 10 | 0 | 0 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 816.48 | 2 | 916.48 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 8 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 1516.32 | 2 | 1516.32 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 16 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 3000 | B | PD | BPD2012 | B1.5.3.12012 | 1.5.3.1 | MSC Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (MSC 2012) | [11 empty] | 3280.5 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 473.85 | 1 | 623.85 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 5 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 458.24 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (MSC 2013 contingency) | [11 empty] | 1640.25 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 40
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 100
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 15
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 473.85 | 1 | 623.85 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 5 | 0 | 0 | 0 | 150
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 458.24 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 50
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | CPD2013 | C1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Shipping (OSC 2011) | [11 empty] | 0 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 473.85 | 1 | 623.85 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 5 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 458.24 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2012 | B1.5.1.22012 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (OSC 2012) | [11 empty] | 1640.25 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 473.85 | 1 | 623.85 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 5 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 458.24 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2013 | B1.5.1.22013 | 1.5.1.2 | Middle Support Cylinder (MSC) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (ESC 2011) | [11 empty] | 1640.25 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 40 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 100 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 15 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 473.85 | 1 | 623.85 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 5 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 458.24 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 4 | 0 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2012 | B1.5.1.1.22012 | 1.5.1.1.2 | East Support Cylinder (ESC) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (IDS Tooling) | [11 empty] | 1640.25 | .
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 3 | 120 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 120 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 3 | 300 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 3 | 45 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 45 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 1421.55 | 3 | 1871.55 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 15 | 0 | 0 | 0 | 450 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 1224.72 | 3 | 1374.72 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 12 | 0 | 0 | 0 | 0 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 2274.48 | 3 | 2274.48 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 24 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 3 | 4500 | B | PD | BPD2012 | B1.5.3.22012 | 1.5.3.2 | IDS Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Shipping (Final Production) | [10 empty] | Sum | 4920.75 | Sum
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 160 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Clear Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 400 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 60 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 60 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Clear Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 1895.4 | 4 | 2495.4 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 0 | 20 | 0 | 0 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 1632.96 | 4 | 1832.96 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 16 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 3032.64 | 4 | 3032.64 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 6000 | B | PD | BPD2009 | B1.52009 | 1.5 | Integration and Global Supports | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 6000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping Subtotal | [11 empty] | 41006.25 | Base Labor | [13 empty] | 56 | 182 | 0 | 0 | 0 |  | 25970 | 48933.5 |  | 1855 | 0 | 0 | 0 | 0 | 0 |  | 1855
[25 empty] | 0 |  | 996 | 5391 | 136 | 3518 | 0 |  | 339865 |  |  |  | 496 | 2071 | 48 | 836 | 0 |  | 152615
[27 empty] | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost |  |  |  | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost
[26 empty] | Checksum | 996 | 5391 | 136 | 3518 | 0 |  | 339865 |  |  |  | 492 | 2058 | 48 | 836 | 0 |  | 152615 | Checksum
[32 empty] | Cost With Contingency | 1898077.05 | 1685715.93 |  | Contributed Labor Excluded…
Description | WBS | [12 empty] | 2009 | B |  |  |  | 1.5 | 16 | 0 | 0 | 2009
Integration and Global Supports | 1.5 | <-- Copy Down from this Cell both columns A and B to update WBS list | [11 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  |  | BASE | [9 empty] | CONTINGENCY
Mechanics | 1.5.1 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
Inner Detector Support (IDS) | 1.5.1.1 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2009 | 16 | 52 | 0 | 0 | 0 | 7420 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
West Support Cylinder Interface | 1.5.1.1.1 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2010 | 82 | 271 | 0 | 758 | 0 | 42895 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
East Support Cylinder (ESC) | 1.5.1.1.2 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2011 | 552 | 1627 | 40 | 1452 | 0 | 150275 |  |  |  | 2011 | 220 | 762 | 8 | 408 | 0 | 14800
Outer Support Cylinder (OSC) | 1.5.1.1.3 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2012 | 328 | 1815 | 40 | 568 | 0 | 132765 |  |  |  | 2012 | 268 | 612 | 8 | 256 | 0 | 131330
E-Field Shroud (EFS) | 1.5.1.1.4 | [12 empty] | 2009 | B |  |  |  | 1.5 |  |  |  | 2009 |  |  | 2013 | 18 | 750 | 56 | 168 | 0 | 9870 |  |  |  | 2013 | 8 | 697 | 32 | 140 | 0 | 9205
[26 empty] | 2014 | 0 | 192 | 0 | 76 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
Middle Support Cylinder (MSC) | 1.5.1.2 | [12 empty] | 2009 | B |  |  |  | 1.5 |  |  |  | 2009 |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
Pixel Insertion Tube | 1.5.1.2.1 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | STAR | 0 | 684 | 0 | 496 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 32 | 0 | 0
Bulkhead Extension | 1.5.1.2.2 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  |  | Project Estimated Cost | [9 empty] | Project Estimated Contingency
Transition Plate | 1.5.1.2.3 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
Pixel Support Tube | 1.5.1.2.4 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beam Pipe Mechanics | 1.5.1.3 | [12 empty] | 2009 | B |  |  |  | 1.5 |  |  |  | 2009 |  |  | 2010 | 10332 | 31707 | 0 | 108570 | 0 | 42895 | 193504 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beam Pipe Model | 1.5.1.3.1 | [12 empty] | 2009 | B |  |  |  | 1.5 |  |  |  | 2009 |  |  | 2011 | 56337.12 | 151537.23 | 4082.4 | 174231 | 0 | 64360 | 450547.75 |  |  | 2011 | 22453.2 | 72214.74 | 816.48 | 49572 | 0 | 14800 | 159856.42
Internal Support (Low Mass) | 1.5.1.3.2 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2012 | 33475.68 | 172007.55 | 4082.4 | 69012 | 0 | 132765 | 411342.63 |  |  | 2012 | 27352.08 | 56672.46 | 816.48 | 30010.5 | 0 | 122997.5 | 237849.02
[26 empty] | 2013 | 1837.08 | 71077.5 | 5715.36 | 20412 | 0 | 9870 | 108911.94 |  |  | 2013 | 816.48 | 66054.69 | 3265.92 | 17010 | 0 | 9205 | 96352.09
Alternate Beam Pipe Support | 1.5.1.3.3 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 |  |  | 2014 | 0 | 19595.52 | 0 | 7756.56 | 0 | 0 | 27352.08 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
External Beam Pipe Support | 1.5.1.3.4 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 | [8 empty] | Base Cost | 1191658.4 | [8 empty] | Contingency | 494057.53
Bake Out Equipment | 1.5.1.3.5 | [12 empty] | 2009 | B |  |  |  | 1.5 |  | 0 | 0 | 2009 | [18 empty] | Percent | 41.46%
Electronics | 1.5.2 | [31 empty] | 1191658.4 | checksum | [8 empty] | 494057.53 | checksum
Detector Grounding/EMI Control | 1.5.2.1
Environmental Control | 1.5.2.2 | [25 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
Shroud Bias | 1.5.2.3 | [25 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
Assembly | 1.5.3 | [15 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
MSC Assembly | 1.5.3.1 | [15 empty] | BPT | [8 empty] | 2010 | 82 | 271 | 0 | 578 | 0 | 42895 |  |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0
IDS Assembly | 1.5.3.2 | [15 empty] | BPT | [8 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2011 | 0 | 0 | 0 | 0 | 0 | 0
Integration Infrastructure | 1.5.4 | [15 empty] | BPT | [8 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2012 | 0 | 0 | 0 | 0 | 0 | 0
Cables | 1.5.4.1 | [15 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0
Dry Gas Services | 1.5.4.2 | [15 empty] | BPT | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | CONT | 0 | 0 | 0 | 0 | 0 | 0
Hall Modifications and Safety | 1.5.4.3 | [15 empty] | BPT | [8 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | STAR | 0 | 0 | 0 | 0 | 0 | 0
Clean Room Modifications | 1.5.4.3.1 | [25 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
External Clean Tent | 1.5.4.3.2 | [25 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
Shield Wall Pass Thru | 1.5.4.3.3 | IF need to copy below this line to contain WBS, need to update Data Validation for cells in column "U" (WBS) AND 'Look Up' vectors for Column "V" (Descriptor) | [14 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installation | 1.5.5 | [15 empty] | BPT | [8 empty] | 2010 | 10332 | 31707 | 0 | 86700 | 0 | 42895 | 171634 |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 171634 | [8 empty] | Contingency | 0
[42 empty] | Percent | 0%
[27 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[27 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 0 | 0 | 0 | 180 | 0 | 0 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 552 | 1599 | 40 | 1434 | 0 | 64360 |  |  | CPD | 2011 | 220 | 762 | 8 | 408 | 0 | 14800
[17 empty] | BPD | [8 empty] | 2012 | 328 | 1815 | 40 | 568 | 0 | 132765 |  |  | CPD | 2012 | 268 | 598 | 8 | 247 | 0 | 122997.5
[17 empty] | BPD | [8 empty] | 2013 | 18 | 750 | 56 | 168 | 0 | 9870 |  |  | CPD | 2013 | 8 | 697 | 32 | 140 | 0 | 9205
[17 empty] | BPD | [8 empty] | 2014 | 0 | 192 | 0 | 76 | 0 | 0 |  |  | CPD | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | STAR | 0 | 684 | 0 | 496 | 0 | 0 |  |  | CPD | STAR | 0 | 0 | 0 | 32 | 0 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 0 | 0 | 0 | 21870 | 0 | 0 | 21870 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 56337.12 | 151537.23 | 4082.4 | 174231 | 0 | 64360 | 450547.75 |  | CPD | 2011 | 22453.2 | 72214.74 | 816.48 | 49572 | 0 | 14800 | 159856.42
[17 empty] | BPD | [8 empty] | 2012 | 33475.68 | 172007.55 | 4082.4 | 69012 | 0 | 132765 | 411342.63 |  | CPD | 2012 | 27352.08 | 56672.46 | 816.48 | 30010.5 | 0 | 122997.5 | 237849.02
[17 empty] | BPD | [8 empty] | 2013 | 1837.08 | 71077.5 | 5715.36 | 20412 | 0 | 9870 | 108911.94 |  | CPD | 2013 | 816.48 | 66054.69 | 3265.92 | 17010 | 0 | 9205 | 96352.09
[17 empty] | BPD | [8 empty] | 2014 | 0 | 19595.52 | 0 | 7756.56 | 0 | 0 | 27352.08 |  | CPD | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 1020024.4 | [8 empty] | Contingency | 494057.53
[42 empty] | Percent | 48.44%

## Rates
Values below used only for reference--not linked to data in sheet estimate…
| Construction | R&D |  | English | Metric | Quoted |  | Metric
Shop | 102.06 | 126 | Material | lb/in^3 | g/cc | Cost/Unit | Unit | Cost/Unit | Unit
CMM | 102.06 | 126 | Aluminum | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
M_Tech | 94.77 | 117 | MIC-6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
Engineer | 121.5 | 150 | 6061-T6 | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
Designer | 101.25 | 125 | 7075-T6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
|  |  | Titanium | 0.198 | 5.4855 | 15 | $/lb | 0.030992 | $/g
Construction Rate does not have full Burden--currently ~81% (below) of Full Burden at LBNL (R&D Rate) |  |  | 6Al4V | 0.198 | 5.4855 | 20 | $/lb | 0.041322 | $/g
|  |  | Steel | 0.298 | 8.256 | 3 | $/lb | 0.0061983 | $/g
|  |  | 304SS | 0.298 | 8.256 | 15 | $/lb | 0.030992 | $/g
|  |  | Carbon Fiber | 0.065 | 1.8008 | 100 | $/lb | 0.20661 | $/g
Differential | 81% |  | M55J-UDT | 0.065 | 1.8008 | 800 | $/lb | 1.6529 | $/g
Change This to change burden rate… |  |  | CN60-PW | 0.065 | 1.8008 | 300 | $/lb | 0.61983 | $/g
|  |  | YSH80A-UDT | 0.065 | 1.8008 | 1000 | $/lb | 2.0661 | $/g
|  |  | Adhesive | 0.055 | 1.5238 | 400 | $/qt | 0.42283 | $/cc
|  |  | EA9396 | 0.055 | 1.5238 | 350 | $/qt | 0.36998 | $/cc
|  |  | EA9394 | 0.075 | 2.0779 | 450 | $/qt | 0.47569 | $/cc
|  |  | CF HoneyComb | 0.0017361 | 0.048099 | 600 | $/bdft | 0.25424 | $/cc
|  |  | Al HoneyComb | 0.0017361 | 0.048099 | 75 | $/bdft | 0.03178 | $/cc
|  |  | Nomex HC | 0.0023148 | 0.064131 | 100 | $/bdft | 0.042373 | $/cc
|  |  | PEEK | 0.055 | 1.5238 | 400 | $/lb | 0.82645 | $/g
|  |  | CF PEEK | 0.055 | 1.5238 | 600 | $/lb | 1.2397 | $/g

## Material Estimates
Material Estimates per component |  |  | Values used to estimate Size/Cost of Batch Orders--Does not report to Cost Summary
Item | Material | Descriptor | Quantity | CPT (microns) | Density (g/cc) | Finished Form | % Waste | Length (cm) | Diameter/Width (cm) | Thickness (cm) | Volume (cc) | Mass (g) | Pre-Preg Area (m^2) | Cost Per Unit | Choose Unit | Cost | Prototype Mass | Prototype Area | Prototype Composites
East Support Cylinder | [20 empty] | /cc | Bulk | 1
Structural Shell | [20 empty] | /g | Plate | 2
Shell | [20 empty] | /m^2 | Round | 3
Transition Flange | CN60 Cloth | Laminate | 1 | 330 | 1.8 | Shell | 30% | 5 | 75 | 0.15 | 229.729 | 413.5121 | 0.69615 | 0.62 | /g | 256.3775 | 0 | 0 | 0 |  |  | Shell | 4
Transtion Plate | CN60 Cloth | Laminate | 1 | 330 | 1.8 | Shell | 30% | 0.6 | 80 | 3 | 588.1061 | 1058.5911 | 1.7821 | 0.62 | /g | 656.3265 | 0 | 0 | 0
Shell Laminate | YSH80A | Laminate | 1 | 75 | 1.8 | Shell | 30% | 180 | 80 | 0.06 | 3528.6369 | 6351.5464 | 47.0485 | 2.066 | /g | 13122.2948 | 0 | 0 | 0
Assembly | [16 empty] | 0 | 0 | 0
Flange Bond | EA9396 | Adhesive | 1 | n/a | 1.52 | Shell | 400% | 3 | 75 | 0.01 | 35.3429 | 53.7212 | #VALUE! | 0.37 | /cc | 13.0769 | 0 | 0 | 0
Flange To Shell | EA9396 | Adhesive | 1 | n/a | 1.52 | Shell | 400% | 3 | 75 | 0.01 | 35.3429 | 53.7212 | #VALUE! | 0.37 | /cc | 13.0769 | 0 | 0 | 0
Conical Transition Plate | [16 empty] | 0 | 0 | 0
Tooling | [16 empty] | 0 | 0 | 0
Skin | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 95 | 95 | 5 | 45125 | 121837.5 | #VALUE! | 0.017 | /g | 2071.2375 | 0 | 0 | 0
Outer Skin/Flanges | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 95 | 95 | 2 | 18050 | 48735 | #VALUE! | 0.017 | /g | 828.495 | 0 | 0 | 0
Assembly | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 0% | 95 | 95 | 2.5 | 45125 | 121837.5 | #VALUE! | 0.017 | /g | 2071.2375 | 0 | 0 | 0
Components | [16 empty] | 0 | 0 | 0
Inner Skin | CN60 Cloth | Laminate | 1 | 330 | 1.8 | Round | 60% | 0.4 | 80 | 0 | 3216.9909 | 5790.5836 | 9.7485 | 0.62 | /g | 3590.1618 | 0 | 0 | 0
Outer Flange | CN60 Cloth | Laminate | 1 | 330 | 1.8 | Shell | 30% | 0.6 | 80 | 3 | 588.1061 | 1058.5911 | 1.7821 | 0.62 | /g | 656.3265 | 0 | 0 | 0
Inner Flange | CN60 Cloth | Laminate | 1 | 330 | 1.8 | Shell | 30% | 0.6 | 40 | 3 | 294.0531 | 529.2955 | 0.89107 | 0.62 | /g | 328.1632 | 0 | 0 | 0
Assembly | [16 empty] | 0 | 0 | 0
Inner Skin Bond | EA9396 | Adhesive | 1 | n/a | 1.52 | Plate | 200% | 75 | 75 | 0.01 | 168.75 | 256.5 | #VALUE! | 0.37 | /cc | 62.4375 | 0 | 0 | 0
Outer Skin Bond | EA9396 | Adhesive | 1 | n/a | 1.52 | Plate | 200% | 75 | 75 | 0.01 | 168.75 | 256.5 | #VALUE! | 0.37 | /cc | 62.4375 | 0 | 0 | 0
Final Bond | EA9396 | Adhesive | 1 | n/a | 1.52 | Plate | 200% | 75 | 75 | 0.01 | 168.75 | 256.5 | #VALUE! | 0.37 | /cc | 62.4375 | 0 | 0 | 0
Outer Support Cylinder
Structural Shell
Shell
Transition Flange | CN60 Cloth | Laminate | 2 | 330 | 1.8 | Shell | 30% | 5 | 43 | 0.15 | 263.4225 | 474.1606 | 0.79825 | 0.62 | /g | 293.9796 | 0 | 0 | 0
Transtion Plate | CN60 Cloth | Laminate | 2 | 330 | 1.8 | Shell | 30% | 0.6 | 43 | 3 | 632.2141 | 1137.9854 | 1.9158 | 0.62 | /g | 705.5509 | 0 | 0 | 0
Transition Flange | CN60 Cloth | Test | 2 | 330 | 1.8 | Shell | 30% | 5 | 43 | 0.15 | 263.4225 | 474.1606 | 0.79825 | 0.62 | /g | 293.9796 | 474.1606 | 0.79825 | 293.9796
Transtion Plate | CN60 Cloth | Test | 2 | 330 | 1.8 | Shell | 30% | 0.6 | 43 | 3 | 632.2141 | 1137.9854 | 1.9158 | 0.62 | /g | 705.5509 | 1137.9854 | 1.9158 | 705.5509
Shell Laminate Test | YSH80A | Test | 3 | 75 | 1.8 | Shell | 30% | 40 | 43 | 0.06 | 1264.4282 | 2275.9708 | 16.859 | 2.066 | /g | 4702.1556 | 2275.9708 | 16.859 | 4702.1556
Shell Laminate | YSH80A | Laminate | 1 | 75 | 1.8 | Shell | 30% | 120 | 43 | 0.06 | 1264.4282 | 2275.9708 | 16.859 | 2.066 | /g | 4702.1556 | 0 | 0 | 0
Assembly | [16 empty] | 0 | 0 | 0
Flange Bond | EA9396 | Test | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 61.6003 | #VALUE! | 14.9948
Flange To Shell | EA9396 | Test | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 61.6003 | #VALUE! | 14.9948
Flange Bond | EA9396 | Adhesive | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 0 | 0 | 0
Flange To Shell | EA9396 | Adhesive | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 0 | 0 | 0
MSC Large (PIT)
Structural Shell
Shell
Transition Flange | CN60 Cloth | Laminate | 2 | 330 | 1.8 | Shell | 30% | 5 | 43 | 0.15 | 263.4225 | 474.1606 | 0.79825 | 0.62 | /g | 293.9796 | 0 | 0 | 0
Transtion Plate | CN60 Cloth | Laminate | 2 | 330 | 1.8 | Shell | 30% | 0.6 | 43 | 3 | 632.2141 | 1137.9854 | 1.9158 | 0.62 | /g | 705.5509 | 0 | 0 | 0
Shell Laminate | YSH80A | Laminate | 1 | 75 | 1.8 | Shell | 30% | 220 | 43 | 0.06 | 2318.1184 | 4172.6131 | 30.9082 | 2.066 | /g | 8620.6187 | 0 | 0 | 0
Assembly | [16 empty] | 0 | 0 | 0
Flange Bond | EA9396 | Adhesive | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 0 | 0 | 0
Flange To Shell | EA9396 | Adhesive | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 0 | 0 | 0
MSC Small (PST)
Structural Shell
Shell
Transition Flange | CN60 Cloth | Test | 2 | 330 | 1.8 | Shell | 30% | 5 | 25 | 0.15 | 153.1526 | 275.6748 | 0.4641 | 0.62 | /g | 170.9183 | 275.6748 | 0.4641 | 170.9183
Transtion Plate | CN60 Cloth | Test | 2 | 330 | 1.8 | Shell | 30% | 0.6 | 25 | 3 | 367.5663 | 661.6194 | 1.1138 | 0.62 | /g | 410.204 | 661.6194 | 1.1138 | 410.204
Shell Laminate | YSH80A | Test | 3 | 75 | 1.8 | Shell | 30% | 40 | 25 | 0.06 | 735.1327 | 1323.2388 | 9.8018 | 2.066 | /g | 2733.8114 | 1323.2388 | 9.8018 | 2733.8114
Transition Flange | CN60 Cloth | Laminate | 2 | 330 | 1.8 | Shell | 30% | 5 | 25 | 0.15 | 153.1526 | 275.6748 | 0.4641 | 0.62 | /g | 170.9183 | 0 | 0 | 0
Transtion Plate | CN60 Cloth | Laminate | 2 | 330 | 1.8 | Shell | 30% | 0.6 | 25 | 3 | 367.5663 | 661.6194 | 1.1138 | 0.62 | /g | 410.204 | 0 | 0 | 0
Shell Laminate | YSH80A | Laminate | 1 | 75 | 1.8 | Shell | 30% | 120 | 25 | 0.06 | 735.1327 | 1323.2388 | 9.8018 | 2.066 | /g | 2733.8114 | 0 | 0 | 0
Assembly | [16 empty] | 0 | 0 | 0
Flange Bond | EA9396 | Test | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 61.6003 | #VALUE! | 14.9948
Flange To Shell | EA9396 | Test | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 61.6003 | #VALUE! | 14.9948
Flange Bond | EA9396 | Adhesive | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 0 | 0 | 0
Flange To Shell | EA9396 | Adhesive | 2 | n/a | 1.52 | Shell | 400% | 3 | 43 | 0.01 | 40.5265 | 61.6003 | #VALUE! | 0.37 | /cc | 14.9948 | 0 | 0 | 0
[13 empty] | LB | Area | Cost $k |  | Material | lbs | m^2 | Cost
|  | Production |  |  |  | Prototype |  |  |  |  | Batch 10
ESC Materials |  | Grams | lbs | Cost | Area | Grams | lbs | Cost | Area |  | OSC P-T | CN60 | 9 | 3 | 1200 |  | CN60 | 9 | 3 | 1200 | 10m^2 is likely minimum order… ($4k)
| CN60 Cloth | 8850.5734 | 19.4947 | 5487.3555 | 14.9 | 0 | 0 | 0 | 0 |  |  | YSH80A | 6 | 17 | 8500 |  | YSH80A | 6 | 17 | 8500 | 12lb is likely minimum order (34m^2 $17k)
| YSH80A | 6351.5464 | 13.9902 | 13122.2948 | 47.0485 | 0 | 0 | 0 | 0 |  | Batch 1 11
[11 empty] | ESC | CN60 | 20 | 15 | 6000 |  | CN60 | 39 | 29 | 11600
|  | Production |  |  |  | Prototype | [5 empty] | YSH80A | 14 | 48 | 24000 |  | YSH80A | 44 | 143 | 71500
OSC Materials |  | Grams | lbs | Cost | Area | Grams | lbs | Cost | Area |  | OSC PD | CN60 | 8 | 6 | 2400
| CN60 Cloth | 3224.2919 | 7.102 | 1999.061 | 5.4281 | 3888.1167 | 8.5641 | 999.5305 | 2.7141 |  |  | YSH80A | 11 | 34 | 17000
| YSH80A | 4551.9416 | 10.0263 | 9404.3113 | 33.7181 | 2275.9708 | 5.0132 | 4702.1556 | 16.859 |  | MSC P-T | CN60 | 3 | 2 | 800
[12 empty] | YSH80A | 3 | 10 | 5000
|  | Production |  |  |  | Prototype |  |  |  |  | MSC PD | CN60 | 8 | 6 | 2400
MSC Materials |  | Grams | lbs | Cost | Area | Grams | lbs | Cost | Area |  |  | YSH80A | 16 | 51 | 25500
| CN60 Cloth | 3486.7343 | 7.68 | 2161.7753 | 5.8699 | 937.2942 | 2.0645 | 581.1224 | 1.5779 |  | Batch 1c 11
| YSH80A | 6819.0907 | 15.02 | 14088.2415 | 50.5118 | 1323.2388 | 2.9146 | 2733.8114 | 9.8018 |  | OSC PD | CN60 | 8 | 6 | 4 |  | CN60 | 16 | 12 | 8
[12 empty] | YSH80A | 11 | 34 | 13 |  | YSH80A | 27 | 85 | 31
[11 empty] | MSC PD | CN60 | 8 | 6 | 4
[12 empty] | YSH80A | 16 | 51 | 18
Batch 2 12
[11 empty] | OSC PD | CN60 | 8 | 6 | 4 |  | CN60 | 16 | 12 | 8
[12 empty] | YSH80A | 11 | 34 | 13 |  | YSH80A | 27 | 85 | 31
[11 empty] | MSC PD | CN60 | 8 | 6 | 4
[12 empty] | YSH80A | 16 | 51 | 18
Batch 2c 12
[11 empty] | OSC PD | CN60 | 8 | 6 | 4 |  | CN60 | 16 | 12 | 8
[12 empty] | YSH80A | 11 | 34 | 13 |  | YSH80A | 27 | 85 | 31
[11 empty] | MSC PD | CN60 | 8 | 6 | 4
[12 empty] | YSH80A | 16 | 51 | 18