## WBS in Estimate
This table drives values in a lookup table in the Pre- and Production Sheet, columns U and V. It is 'copied' into that sheet at the bottom, see notes there to understand how to modify this. 'Inserting' rows does not work, only adding, so must modify whole table--5 rows are available for additions...
WBS | Description
1.2.2 | PXL Electronics
1.2.2.1 | Phase-1 Sensor
1.2.2.1.1 | Phase-1 Prototype
1.2.2.1.2 | Phase-1 Production
1.2.2.2 | PXL Sensor
1.2.2.2.1 | PXL Sensor Prototype
1.2.2.2.2 | PXL Sensor Production
1.2.2.3 | Ladder Cable
1.2.2.3.1 | Infrastructure Test Cable
1.2.2.3.2 | Prototype Ladder Cable (FR-4)
1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor)
1.2.3.3.4 | Ladder Cable (Kapton + Al conductor)
1.2.2.3.5 | Ladder Cable PXL Sensor
1.2.2.4 | Phase-1 Ladder Assembly
1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes
1.2.2.5 | Read-out Electronics
1.2.2.5.1 | RDO Board
1.2.2.5.2 | Mass Termination Board
1.2.2.5.3 | RDO PCs
1.2.2.5.4 | Control PC System
1.2.2.6 | PXL Sensor Ladder Production

## SUMMARY
| BASE | [7 empty] | CONTINGENCY
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 128 | 464 | 2756 | 336 | 2644 | 87108 |  | 2010 | 0 | 208 | 16 | 16 | 48 | 7500
2011 | 136 | 804 | 2052 | 676 | 2256 | 214750 |  | 2011 | 40 | 168 | 88 | 64 | 136 | 22250
2012 | 152 | 1634 | 2122 | 926 | 2516 | 425760 |  | 2012 | 252 | 849 | 52 | 316 | 80 | 256750
2013 | 48 | 2522 | 2546 | 250 | 2594 | 646650 |  | 2013 | 72 | 488 | 0 | 302 | 0 | 55500
2014 | 0 | 296 | 202 | 16 | 222 | 32200 |  | 2014 | 40 | 66 | 40 | 44 | 40 | 63000
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 0 | 0 | 0 | 0 | 0 |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [7 empty] | Project Estimated Contingency
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 15170.4 | 51976.08 | 0 | 48576 | 0 | 87108 | 202830.48 | 2010 | 0 | 24336 | 0 | 2400 | 0 | 7500 | 34236
2011 | 15603.84 | 87487.92 | 0 | 88176 | 0 | 214750 | 406017.76 | 2011 | 4561.2 | 17166.24 | 0 | 8460 | 0 | 22250 | 52437.44
2012 | 18385.92 | 159300.18 | 0 | 115017 | 0 | 425760 | 718463.1 | 2012 | 31464.72 | 88462.53 | 0 | 43638 | 0 | 256750 | 420315.25
2013 | 4898.88 | 239009.94 | 0 | 30375 | 0 | 646650 | 920933.82 | 2013 | 7348.32 | 46247.76 | 0 | 36693 | 0 | 55500 | 145789.08
2014 | 0 | 28051.92 | 0 | 1944 | 0 | 32200 | 62195.92 | 2014 | 4082.4 | 6254.82 | 0 | 5346 | 0 | 63000 | 78683.22
[6 empty] | Base Cost | 2310441.08 | [6 empty] | Contingency | 731460.99
[14 empty] | Percent | 31.66%
| Pre-Production Base Cost | [7 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 88 | 360 | 2184 | 272 | 2188 | 37708 |  | 2010 | 0 | 208 | 8 | 16 | 8 | 7500
2011 | 72 | 508 | 980 | 212 | 1408 | 202100 |  | 2011 | 20 | 56 | 0 | 24 | 0 | 7500
2012 | 120 | 200 | 280 | 88 | 336 | 161500 |  | 2012 | 240 | 360 | 48 | 184 | 80 | 199150
2013 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 0 | 0 | 0 | 0 | 0 |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [7 empty] | Project Estimated Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 11088 | 42120 | 0 | 40800 | 0 | 37708 | 131716 | 2010 | 0 | 24336 | 0 | 2400 | 0 | 7500 | 34236
2011 | 9072 | 59436 | 0 | 31800 | 0 | 202100 | 302408 | 2011 | 2520 | 6552 | 0 | 3600 | 0 | 7500 | 20172
2012 | 15120 | 23400 | 0 | 13200 | 0 | 161500 | 213220 | 2012 | 30240 | 42120 | 0 | 27600 | 0 | 199150 | 299110
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 647344 | [6 empty] | Contingency | 353518
[14 empty] | Percent | 54.61%
| Production Base Cost | [7 empty] | Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 40 | 104 | 572 | 64 | 456 | 49400 |  | 2010 | 0 | 0 | 8 | 0 | 40 | 0
2011 | 64 | 296 | 1072 | 464 | 848 | 12650 |  | 2011 | 20 | 112 | 88 | 40 | 136 | 14750
2012 | 32 | 1434 | 1842 | 838 | 2180 | 264260 |  | 2012 | 12 | 489 | 4 | 132 | 0 | 57600
2013 | 48 | 2522 | 2546 | 250 | 2594 | 646650 |  | 2013 | 72 | 488 | 0 | 302 | 0 | 55500
2014 | 0 | 296 | 202 | 16 | 222 | 32200 |  | 2014 | 40 | 66 | 40 | 44 | 40 | 63000
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 0 | 0 | 0 | 0 | 0 |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [7 empty] | Project Estimated Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 4082.4 | 9856.08 | 0 | 7776 | 0 | 49400 | 71114.48 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 6531.84 | 28051.92 | 0 | 56376 | 0 | 12650 | 103609.76 | 2011 | 2041.2 | 10614.24 | 0 | 4860 | 0 | 14750 | 32265.44
2012 | 3265.92 | 135900.18 | 0 | 101817 | 0 | 264260 | 505243.1 | 2012 | 1224.72 | 46342.53 | 0 | 16038 | 0 | 57600 | 121205.25
2013 | 4898.88 | 239009.94 | 0 | 30375 | 0 | 646650 | 920933.82 | 2013 | 7348.32 | 46247.76 | 0 | 36693 | 0 | 55500 | 145789.08
2014 | 0 | 28051.92 | 0 | 1944 | 0 | 32200 | 62195.92 | 2014 | 4082.4 | 6254.82 | 0 | 5346 | 0 | 63000 | 78683.22
[6 empty] | Base Cost | 1663097.08 | [6 empty] | Contingency | 377942.99
[14 empty] | Percent | 22.73%

## WBS Summary
|  | Shop |  | Tech |  | Post Doc |  | Engineering |  | Eng Contr |  | M & S
WBS | Description | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
1.2.2 | PXL Electronics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.1 | Phase-1 Sensor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.1.1 | Phase-1 Prototype | 64 | 0 | 72 | 84 | 548 | 16 | 40 | 0 | 336 | 48 | 17100 | 3000
1.2.2.1.2 | Phase-1 Production | 64 | 20 | 112 | 112 | 612 | 88 | 64 | 40 | 476 | 136 | 50900 | 14750
1.2.2.2 | PXL Sensor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.2.1 | PXL Sensor Prototype | 72 | 20 | 360 | 16 | 1012 | 8 | 100 | 24 | 1056 | 40 | 342550 | 189900
1.2.2.2.2 | PXL Sensor Production | 64 | 16 | 504 | 96 | 840 | 0 | 396 | 96 | 552 | 0 | 385860 | 21500
1.2.2.3 | Ladder Cable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.3.1 | Infrastructure Test Cable | 0 | 0 | 136 | 24 | 396 | 0 | 96 | 4 | 740 | 0 | 10200 | 1500
1.2.2.3.2 | Prototype Ladder Cable (FR-4) | 0 | 0 | 76 | 100 | 184 | 0 | 32 | 12 | 328 | 0 | 3708 | 3000
1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | 0 | 0 | 136 | 40 | 264 | 0 | 64 | 0 | 444 | 0 | 8700 | 1000
1.2.3.3.4 | Ladder Cable (Kapton + Al conductor) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.3.5 | Ladder Cable PXL Sensor | 0 | 0 | 176 | 40 | 496 | 0 | 320 | 40 | 760 | 0 | 19000 | 4000
1.2.2.4 | Phase-1 Ladder Assembly | 8 | 16 | 712 | 456 | 542 | 4 | 48 | 16 | 632 | 0 | 25300 | 52600
1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | 64 | 120 | 80 | 120 | 80 | 0 | 24 | 16 | 80 | 0 | 3500 | 4500
1.2.2.5 | Read-out Electronics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.5.1 | RDO Board | 0 | 0 | 520 | 205 | 2424 | 0 | 704 | 298 | 2252 | 0 | 181000 | 24750
1.2.2.5.2 | Mass Termination Board | 0 | 0 | 300 | 40 | 312 | 0 | 80 | 40 | 408 | 0 | 26550 | 4000
1.2.2.5.3 | RDO PCs | 0 | 0 | 0 | 0 | 80 | 0 | 32 | 16 | 80 | 0 | 60500 | 8000
1.2.2.5.4 | Control PC System | 0 | 0 | 0 | 0 | 352 | 0 | 16 | 8 | 352 | 0 | 6000 | 1000
1.2.2.6 | PXL Sensor Ladder Production | 128 | 212 | 2536 | 446 | 1536 | 80 | 188 | 132 | 1736 | 80 | 265600 | 71500
| Hours | 464 | 404 | 5720 | 1779 | 9678 | 196 | 2204 | 742 | 10232 | 304 | 1406468 | 405000
| FTE | 0.26977 | 0.23488 | 3.3256 | 1.0343 | 5.6267 | 0.11395 | 1.2814 | 0.4314 | 5.9488 | 0.17674
| Cost Approx | 47355.84 | 41232.24 | 542084.4 | 168595.83 | 0 | 0 | 267786 | 90153 | 0 | 0

## WBS Summary by Year
2009
|  | Shop |  | TTech |  | Post Doc |  | Engineering |  | ENG Contributed |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010
|  | Shop |  | TTech |  | Post Doc |  | Engineering |  | ENG Contributed |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1 | 64 | 0 | 72 | 84 | 548 | 16 | 40 | 0 | 336 | 48 | 17100 | 3000
| 1.2.2.1.2 | 64 | 0 | 112 | 0 | 612 | 0 | 64 | 0 | 476 | 0 | 50900 | 0
| 1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1 | 0 | 0 | 68 | 0 | 376 | 0 | 24 | 0 | 304 | 0 | 5200 | 0
| 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1 | 0 | 0 | 136 | 24 | 396 | 0 | 96 | 4 | 740 | 0 | 10200 | 1500
| 1.2.2.3.2 | 0 | 0 | 76 | 100 | 184 | 0 | 32 | 12 | 328 | 0 | 3708 | 3000
| 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1 | 0 | 0 | 0 | 0 | 640 | 0 | 80 | 0 | 460 | 0 | 0 | 0
| 1.2.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours | 128 | 0 | 464 | 208 | 2756 | 16 | 336 | 16 | 2644 | 48 | 87108 | 7500
| FTE | 0.074419 | 0 | 0.26977 | 0.12093 | 1.6023 | 0.0093023 | 0.19535 | 0.0093023 | 1.5372 | 0.027907
2011
|  | Shop |  | TTech |  | Post Doc |  | Engineering |  | ENG Contributed |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2 | 0 | 20 | 0 | 112 | 0 | 88 | 0 | 40 | 0 | 136 | 0 | 14750
| 1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1 | 72 | 20 | 292 | 16 | 636 | 0 | 76 | 24 | 720 | 0 | 182350 | 6500
| 1.2.2.2.2 | 64 | 0 | 296 | 0 | 232 | 0 | 180 | 0 | 208 | 0 | 7650 | 0
| 1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.3 | 0 | 0 | 136 | 40 | 264 | 0 | 64 | 0 | 444 | 0 | 8700 | 1000
| 1.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1 | 0 | 0 | 80 | 0 | 920 | 0 | 356 | 0 | 884 | 0 | 9550 | 0
| 1.2.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0
| 1.2.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hours | 136 | 40 | 804 | 168 | 2052 | 88 | 676 | 64 | 2256 | 136 | 214750 | 22250
| FTE | 0.07907 | 0.023256 | 0.46744 | 0.097674 | 1.193 | 0.051163 | 0.39302 | 0.037209 | 1.3116 | 0.07907
2012
|  | Shop |  | TTech |  | Post Doc |  | Engineering |  | ENG Contributed |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 32 | 40 | 155000 | 183400
| 1.2.2.2.2 | 0 | 0 | 156 | 8 | 228 | 0 | 160 | 8 | 224 | 0 | 76710 | 10000
| 1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5 | 0 | 0 | 176 | 40 | 496 | 0 | 320 | 40 | 760 | 0 | 19000 | 4000
| 1.2.2.4 | 8 | 0 | 652 | 376 | 62 | 4 | 18 | 8 | 152 | 0 | 25300 | 32600
| 1.2.2.4.1 | 64 | 120 | 80 | 120 | 80 | 0 | 24 | 16 | 80 | 0 | 3500 | 4500
| 1.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1 | 0 | 0 | 200 | 125 | 680 | 0 | 220 | 188 | 604 | 0 | 85200 | 12750
| 1.2.2.5.2 | 0 | 0 | 210 | 0 | 256 | 0 | 72 | 0 | 320 | 0 | 17550 | 0
| 1.2.2.5.3 | 0 | 0 | 0 | 0 | 80 | 0 | 32 | 8 | 80 | 0 | 39500 | 4000
| 1.2.2.5.4 | 0 | 0 | 0 | 0 | 120 | 0 | 16 | 0 | 120 | 0 | 0 | 0
| 1.2.2.6 | 80 | 132 | 160 | 180 | 120 | 40 | 64 | 48 | 144 | 40 | 4000 | 5500
| hours | 152 | 252 | 1634 | 849 | 2122 | 52 | 926 | 316 | 2516 | 80 | 425760 | 256750
| FTE | 0.088372 | 0.14651 | 0.95 | 0.4936 | 1.2337 | 0.030233 | 0.53837 | 0.18372 | 1.4628 | 0.046512
2013
|  | Shop |  | TTech |  | Post Doc |  | Engineering |  | ENG Contributed |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.2 | 0 | 16 | 52 | 88 | 380 | 0 | 56 | 88 | 120 | 0 | 301500 | 11500
| 1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4 | 0 | 16 | 60 | 80 | 480 | 0 | 30 | 8 | 480 | 0 | 0 | 20000
| 1.2.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1 | 0 | 0 | 240 | 80 | 184 | 0 | 48 | 110 | 304 | 0 | 86250 | 12000
| 1.2.2.5.2 | 0 | 0 | 90 | 40 | 56 | 0 | 8 | 40 | 88 | 0 | 9000 | 4000
| 1.2.2.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 14500 | 4000
| 1.2.2.5.4 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 8 | 232 | 0 | 6000 | 1000
| 1.2.2.6 | 48 | 40 | 2080 | 200 | 1214 | 0 | 108 | 40 | 1370 | 0 | 229400 | 3000
| hours | 48 | 72 | 2522 | 488 | 2546 | 0 | 250 | 302 | 2594 | 0 | 646650 | 55500
| FTE | 0.027907 | 0.04186 | 1.4663 | 0.28372 | 1.4802 | 0 | 0.14535 | 0.17558 | 1.5081 | 0
2014
|  | Shop |  | TTech |  | Post Doc |  | Engineering |  | ENG Contributed |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.6 | 0 | 40 | 296 | 66 | 202 | 40 | 16 | 44 | 222 | 40 | 32200 | 63000
| hours | 0 | 40 | 296 | 66 | 202 | 40 | 16 | 44 | 222 | 40 | 32200 | 63000
| FTE | 0 | 0.023256 | 0.17209 | 0.038372 | 0.11744 | 0.023256 | 0.0093023 | 0.025581 | 0.12907 | 0.023256

## Pre- and Production
[17 empty] | (HIDE) |  |  |  | (HIDE AS REQUIRED)
Pixel Electronics Estimate (1.2.2) | [14 empty] | TRACKING | [11 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | Postdoc (cont) | Eng Time | Engineering (cont) | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | Sum Logic Code | WBS | WBS Descriptor | PO/UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | Postdoc (cont) | Engineering | Engineer (cont) | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | Postdoc (cont) | Engineering | Engineer (cont) | Materials Sub Totals | Materials Totals
Phase-1
Phase-1 Prototype | [12 empty] | 1
Initial Phase-1 foundry run (wafers) | Si | 2 | wafer | 2500 | 5000 | 0 | 0 | 0 | 8 | 16 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Initial Phase-1 foundry run (masks and processing) | N/A | 1 | N/A | 150000 | 150000 | 0 | 0 | 0 | 0 | 32 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Second Phase-1 foundry run (masks and processing) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Second Phase-1 foundry run (wafers) | Si | 1 | wafer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PH-1 dicing and back-thinning | Si | 2 | wafer | 1700 | 3400 | 0 | 0 | 8 | 0 | 8 | hours | 0 | 1 | 3400 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 8 | 0 | 8 | 3400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
travel | N/A | 2 | N/A | 5000 | 10000 | 0 | 0 | 0 | 0 | 32 | hours | 0 | 0 | 0 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Individual PH-1 testing + interface PCBs | [10 empty] | Sum | 0 | Base Labor
PCB design and Layout | Labor | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 2 | 160 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication | PCB | 10 | PCB | 150 | 1500 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading | N/A | 10 | N/A | 300 | 3000 | 0 | 60 | 8 | 0 | 8 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and Layout | Labor | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 2 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | PCB | 10 | PCB | 150 | 1500 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 10 | N/A | 300 | 3000 | 0 | 60 | 8 | 0 | 8 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCB | N/A | 1 | N/A | 700 | 700 | 0 | 8 | 8 | 4 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Radiation Dose Testing | N/A | 1 | N/A | 2000 | 2000 | 4 | 8 | 40 | 8 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Phase-1 bench testing (includes firmware/software) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 360 | 16 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PH-1 Telescope Test | [10 empty] | Sum | 0 | Base Labor
PCB board telescope test design and layout | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 160 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB board telescope test fabrication | N/A | 10 | N/A | 150 | 1500 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB board telescope parts and loading | N/A | 5 | N/A | 300 | 1500 | 0 | 60 | 8 | 0 | 8 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.1.12009 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB board telescope test design and layout | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 8 | 0 | 40 | hours | 0 | 1 | 0 | C | PD | CPD2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 8 | 0 | 40 | 0
(iteration) PCB board telescope test fabrication | N/A | 10 | N/A | 150 | 1500 | 0 | 0 | 8 | 0 | 8 | hours | 0 | 1 | 1500 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 8 | 0 | 8 | 1500
(iteration) PCB board telescope parts | N/A | 1 | N/A | 500 | 500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 500 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 500
(iteration) PCB board telescope loading labor | N/A | 1 | N/A | 0 | 0 | 0 | 60 | 0 | 0 | 0 | hours | 7020 | 1 | 7020 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 60 | 0 | 0 | 0 | 0
Interface PCB | N/A | 1 | N/A | 700 | 700 | 0 | 0 | 24 | 0 | 24 | hours | 0 | 1 | 700 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 24 | 0 | 24 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Connectors/cabling | N/A | 1 | N/A | 500 | 500 | 0 | 0 | 24 | 0 | 24 | hours | 0 | 1 | 500 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 24 | 0 | 24 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope mechanical (alignment, box etc) | N/A | 1 | N/A | 2000 | 2000 | 40 | 40 | 40 | 8 | 40 | hours | 10920 | 1 | 12920 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 40 | 40 | 40 | 8 | 40 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope trigger system (scint, electronics, APDs, etc) | N/A | 1 | N/A | 5000 | 5000 | 24 | 32 | 32 | 0 | 40 | hours | 6768 | 1 | 11768 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 24 | 32 | 32 | 0 | 40 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope firmware/software | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 100 | 0 | 40 | hours | 0 | 1 | 0 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 100 | 0 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope test Beam Run | N/A | 1 | N/A | 1000 | 1000 | 0 | 0 | 80 | 24 | 40 | hours | 3600 | 1 | 4600 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 80 | 24 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Data Analysis and feedback | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 160 | 8 | 80 | hours | 1200 | 1 | 1200 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 160 | 8 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
travel | N/A | 1 | N/A | 4500 | 4500 | 0 | 0 | 80 | 0 | 40 | hours | 0 | 1 | 4500 | B | PT | BPT2010 | B1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 80 | 0 | 40 | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 1000 | 1000 | 0 | 24 | 0 | 0 | 0 | hours | 2808 | 1 | 3808 | C | PT | CPT2010 | C1.2.2.1.12010 | 1.2.2.1.1 | Phase-1 Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 0 | 0 | 1000
Phase-1 Production | [10 empty] | Sum | 22488 | Base Labor
Phase-1 Production foundry run (wafers) | Si | 6 | wafer | 5600 | 33600 | 0 | 0 | 40 | 0 | 40 | hours | 0 | 1 | 33600 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 40 | 0 | 40 | 33600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Phase-1 Production foundry run (wafers) contingency | Si | 10 | wafer | 5600 | 56000 | 0 | 0 | 40 | 0 | 40 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Phase-1 production foundry run (masks and processing) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sensor dicing and back-thinning | Contract | 4 | Units | 650 | 2600 | 0 | 0 | 80 | 0 | 64 | hours | 0 | 1 | 2600 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 80 | 0 | 64 | 2600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sensor dicing and back-thinning contingency | Contract | 12 | Units | 650 | 7800 | 0 | 0 | 80 | 0 | 64 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 6000 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6000
Phase-1 Probe Testing | [10 empty] | Sum | 0 | Base Labor
Refurbish ATLAS Probe station | N/A | 1 | Units | 5000 | 5000 | 0 | 8 | 8 | 40 | 40 | hours | 5618.16 | 1 | 10618.16 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 8 | 8 | 40 | 40 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
New control PC | Contract | 1 | Units | 2000 | 2000 | 0 | 0 | 0 | 32 | 24 | hours | 0 | 0 | 0 | B | PD | BPD2009 | B1.2.2.1.22009 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe card design and layout | Labor | 1 | Units | 0 | 0 | 0 | 120 | 24 | 60 | 24 | hours | 0 | 0 | 0 | B | PD | BPD2009 | B1.2.2.1.22009 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe card fabrication | N/A | 3 | Units | 750 | 2250 | 0 | 0 | 0 | 16 | 16 | hours | 0 | 0 | 0 | B | PD | BPD2009 | B1.2.2.1.22009 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe card parts and loading | N/A | 3 | Units | 500 | 1500 | 0 | 40 | 20 | 8 | 40 | hours | 4762.8 | 1 | 6262.8 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 40 | 20 | 8 | 40 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Probe card design and layout | N/A | 1 | Units | 0 | 0 | 0 | 40 | 24 | 8 | 40 | hours | 4762.8 | 1 | 4762.8 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 24 | 8 | 40 | 0
(iteration) Probe card fabrication | N/A | 3 | Units | 750 | 2250 | 0 | 0 | 0 | 8 | 24 | hours | 972 | 1 | 3222 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 8 | 24 | 2250
(iteration) Probe card parts and loading | N/A | 3 | Units | 500 | 1500 | 0 | 40 | 24 | 8 | 32 | hours | 4762.8 | 1 | 6262.8 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 24 | 8 | 32 | 1500
Probe test software and firmware | N/A | 1 | Units | 0 | 0 | 0 | 0 | 160 | 16 | 80 | hours | 1944 | 1 | 1944 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 160 | 16 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCBs , parts and loading | N/A | 1 | Units | 700 | 700 | 0 | 16 | 24 | 0 | 24 | hours | 1516.32 | 1 | 2216.32 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 16 | 24 | 0 | 24 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mechanical design of vacuum chuck for thinned sensors | N/A | 1 | Units | 1500 | 1500 | 24 | 8 | 40 | 0 | 20 | hours | 3960 | 1 | 5460 | B | PT | BPT2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 24 | 8 | 40 | 0 | 20 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Mechanical design of vacuum chuck for thinned sensors | N/A | 1 | Units | 1500 | 1500 | 40 | 80 | 40 | 0 | 40 | hours | 0 | 0 | 0 | C | PT | CPT2010 | C1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
vacuum chuck and positioning (production) | N/A | 1 | Units | 1500 | 1500 | 40 | 80 | 40 | 0 | 80 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Database design and implementation | N/A | 1 | Units | 1000 | 1000 | 0 | 0 | 120 | 0 | 80 | hours | 0 | 1 | 1000 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 120 | 0 | 80 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Chip carriers and tracking hardware | N/A | 1 | Units | 5000 | 5000 | 40 | 40 | 80 | 0 | 40 | hours | 7873.2 | 1 | 12873.2 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 40 | 40 | 80 | 0 | 40 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe testing (production) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 0 | 48 | hours | 0 | 1 | 0 | B | PD | BPD2010 | B1.2.2.1.22010 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2010 | 0 | 0 | 40 | 0 | 48 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe testing (production) contingency | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 8 | 40 | hours | 972 | 1 | 972 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 40 | 8 | 40 | 0
contingency | N/A | 1 | Units | 5000 | 5000 | 20 | 32 | 0 | 8 | 0 | hours | 6045.84 | 1 | 11045.84 | C | PD | CPD2011 | C1.2.2.1.22011 | 1.2.2.1.2 | Phase-1 Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 32 | 0 | 8 | 0 | 5000
[11 empty] | Sum | 15293.52 | Sum | 23493.52
Phase-1 Sub Total | [11 empty] | 48162.48 | Base Labor | [13 empty] | 128 | 184 | 1160 | 104 | 812 |  | 68000 | 111137.36 |  | 43226.12 | 20 | 196 | 104 | 40 | 184 |  | 17750
PXL Sensor
PXL Sensor Prototype
Initial PXL Sensor foundry run (wafers) | Si | 2 | wafer | 2500 | 5000 | 0 | 0 | 0 | 0 | 24 | hours | 0 | 1 | 5000 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 24 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Initial PXL Sensor foundry run (masks and processing) | N/A | 1 | N/A | 150000 | 150000 | 0 | 0 | 0 | 0 | 32 | hours | 0 | 1 | 150000 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 32 | 150000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Second PXL Sensor foundry run (masks and processing) | N/A | 1 | N/A | 150000 | 150000 | 0 | 0 | 0 | 0 | 24 | hours | 0 | 1 | 150000 | B | PT | BPT2012 | B1.2.2.2.12012 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 24 | 150000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Second PXL Sensor foundry run (wafers) | Si | 2 | wafer | 2500 | 5000 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 1 | 5000 | B | PT | BPT2012 | B1.2.2.2.12012 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 8 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(contingency) PXL Sensor foundry run (masks and processing) | N/A | 1 | N/A | 150000 | 150000 | 0 | 0 | 0 | 0 | 24 | hours | 0 | 1 | 150000 | C | PT | CPT2012 | C1.2.2.2.12012 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 24 | 150000
(contingency) PXL Sensor foundry run (wafers) | Si | 2 | wafer | 2500 | 5000 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 1 | 5000 | C | PT | CPT2012 | C1.2.2.2.12012 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 5000
PXL Sensor dicing and back-thinning FY11 | Si | 2 | N/A | 1700 | 3400 | 0 | 0 | 8 | 0 | 8 | hours | 0 | 1 | 3400 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 8 | 0 | 8 | 3400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PXL Sensor dicing and back-thinning FY12 | Si | 2 | N/A | 1700 | 3400 | 0 | 0 | 8 | 0 | 8 | hours | 0 | 1 | 3400 | C | PT | CPT2012 | C1.2.2.2.12012 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 8 | 0 | 8 | 3400
travel | N/A | 2 | N/A | 5000 | 10000 | 0 | 0 | 0 | 0 | 32 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 25000 | C | PT | CPT2012 | C1.2.2.2.12012 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 25000
Individual PXL Sensor testing + interface PCBs | [10 empty] | Sum | 0 | Sum | 313400
PCB design and Layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 4 | 160 | hours | 600 | 1 | 600 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 4 | 160 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication | N/A | 10 | Units | 150 | 1500 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 1 | 1500 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 8 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts | N/A | 10 | Units | 300 | 3000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 3000 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB loading | N/A | 1 | Units | 0 | 0 | 0 | 60 | 8 | 0 | 8 | hours | 7020 | 1 | 7020 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 60 | 8 | 0 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and Layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 4 | 80 | hours | 600 | 1 | 600 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 4 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 10 | Units | 150 | 1500 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 1 | 1500 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 8 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 10 | Units | 300 | 3000 | 0 | 60 | 8 | 0 | 8 | hours | 7020 | 1 | 10020 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 60 | 8 | 0 | 8 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCB | N/A | 1 | Units | 700 | 700 | 0 | 8 | 8 | 4 | 48 | hours | 1536 | 1 | 2236 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 8 | 8 | 4 | 48 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PXL Sensor bench testing (includes firmware/software) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 360 | 16 | 80 | hours | 2400 | 1 | 2400 | B | PT | BPT2010 | B1.2.2.2.12010 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2010 | 0 | 0 | 360 | 16 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 2000 | 2000 | 0 | 0 | 0 | 16 | 0 | hours | 2400 | 1 | 4400 | C | PT | CPT2011 | C1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 16 | 0 | 2000
PXL Sensor Telescope Test | [10 empty] | Sum | 19176 | Sum | 28876
PCB board telescope test design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 8 | 160 | hours | 1200 | 1 | 1200 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 8 | 160 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB board telescope test fabrication | N/A | 3 | Units | 750 | 2250 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 1 | 2250 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 8 | 2250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB board telescope parts and loading | N/A | 5 | Units | 300 | 1500 | 0 | 60 | 8 | 0 | 8 | hours | 7020 | 1 | 8520 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 60 | 8 | 0 | 8 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB board telescope test design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 8 | 0 | 40 | hours | 0 | 1 | 0 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 8 | 0 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB board telescope test fabrication | N/A | 10 | Units | 150 | 1500 | 0 | 0 | 8 | 0 | 8 | hours | 0 | 1 | 1500 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 8 | 0 | 8 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB board telescope parts and loading | N/A | 1 | Units | 500 | 500 | 0 | 60 | 8 | 8 | 8 | hours | 8220 | 1 | 8720 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 60 | 8 | 8 | 8 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCB | N/A | 1 | Units | 700 | 700 | 0 | 16 | 24 | 0 | 24 | hours | 1872 | 1 | 2572 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 16 | 24 | 0 | 24 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Connectors/cabling | N/A | 1 | Units | 500 | 500 | 0 | 16 | 24 | 0 | 24 | hours | 1872 | 1 | 2372 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 16 | 24 | 0 | 24 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope mechanical (allignment, box etc) | N/A | 1 | Units | 2000 | 2000 | 40 | 40 | 40 | 8 | 40 | hours | 10920 | 1 | 12920 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 40 | 40 | 40 | 8 | 40 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope trigger detector and logic system | N/A | 1 | Units | 5000 | 5000 | 32 | 40 | 80 | 16 | 40 | hours | 11112 | 1 | 16112 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 32 | 40 | 80 | 16 | 40 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope firmware/software | N/A | 1 | Units | 0 | 0 | 0 | 0 | 100 | 0 | 40 | hours | 0 | 1 | 0 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 100 | 0 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Telescope test Beam Run | N/A | 1 | Units | 1000 | 1000 | 0 | 0 | 80 | 24 | 40 | hours | 3600 | 1 | 4600 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 80 | 24 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Data Analysis and feedback | N/A | 1 | Units | 0 | 0 | 0 | 0 | 160 | 8 | 80 | hours | 1200 | 1 | 1200 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 160 | 8 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
travel | N/A | 1 | Units | 4500 | 4500 | 0 | 0 | 80 | 0 | 40 | hours | 0 | 1 | 4500 | B | PT | BPT2011 | B1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 80 | 0 | 40 | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 4500 | 4500 | 20 | 16 | 0 | 8 | 0 | hours | 5592 | 1 | 10092 | C | PT | CPT2011 | C1.2.2.2.12011 | 1.2.2.2.1 | PXL Sensor Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 16 | 0 | 8 | 0 | 4500
PXL Sensor Production | [10 empty] | Sum | 45816 | Sum
PXL Production foundry run (wafers) FY12 | Si | 12 | wafer | 5600 | 67200 | 0 | 24 | 0 | 32 | 0 | hours | 6162.48 | 1 | 73362.48 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 24 | 0 | 32 | 0 | 67200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PXL Production foundry run (wafers) FY13 | Si | 48 | wafer | 5600 | 268800 | 0 | 24 | 0 | 32 | 0 | hours | 6162.48 | 1 | 274962.48 | B | PD | BPD2013 | B1.2.2.2.22013 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2013 | 0 | 24 | 0 | 32 | 0 | 268800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PXL Production foundry run (wafers) FY14 | Si | 0 | wafer | 5600 | 0 | 0 | 24 | 0 | 32 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2014 | B1.2.2.2.22014 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PXL production foundry run (masks and processing) | N/A | 1 | Units | 0 | 0 | 0 | 24 | 0 | 16 | 0 | hours | 4218.48 | 1 | 4218.48 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 24 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sensor dicing and back-thinning FY12 | Contract | 12 | Units | 650 | 7800 | 0 | 8 | 80 | 8 | 80 | hours | 1730.16 | 1 | 9530.16 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 8 | 80 | 8 | 80 | 7800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sensor dicing and back-thinning FY13 | Contract | 48 | Units | 650 | 31200 | 0 | 8 | 80 | 8 | 80 | hours | 1730.16 | 1 | 32930.16 | B | PD | BPD2013 | B1.2.2.2.22013 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2013 | 0 | 8 | 80 | 8 | 80 | 31200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sensor dicing and back-thinning FY14 | Contract | 0 | Units | 650 | 0 | 0 | 8 | 80 | 8 | 80 | hours | 0 | 0 | 0 | B | PD | BPD2014 | B1.2.2.2.22014 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency FY12 | N/A | 1 | Units | 10000 | 10000 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 11730.16 | C | PD | CPD2012 | C1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 8 | 0 | 10000
contingency FY13 | N/A | 1 | Units | 10000 | 10000 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 11730.16 | C | PD | CPD2013 | C1.2.2.2.22013 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 8 | 0 | 10000
PXL Sensor Probe Testing | [10 empty] | Sum | 47016 | Sum
Probe card design and layout | N/A | 1 | Units | 0 | 0 | 0 | 120 | 24 | 60 | 24 | hours | 18662.4 | 1 | 18662.4 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 0 | 120 | 24 | 60 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe card fabrication | N/A | 3 | Units | 750 | 2250 | 0 | 0 | 0 | 16 | 16 | hours | 1944 | 1 | 4194 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 0 | 0 | 0 | 16 | 16 | 2250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe card parts and loading | N/A | 3 | Units | 400 | 1200 | 0 | 40 | 20 | 16 | 40 | hours | 5734.8 | 1 | 6934.8 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 0 | 40 | 20 | 16 | 40 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Probe card design and layout | N/A | 1 | Units | 105 | 105 | 0 | 40 | 24 | 40 | 40 | hours | 8650.8 | 1 | 8755.8 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 40 | 24 | 40 | 40 | 105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Probe card fabrication | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 32 | 24 | hours | 3888 | 1 | 3888 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 0 | 0 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Probe card parts and loading | N/A | 1 | Units | 105 | 105 | 0 | 40 | 24 | 16 | 40 | hours | 5734.8 | 1 | 5839.8 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 40 | 24 | 16 | 40 | 105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe test software and firmware modification | N/A | 1 | Units | 0 | 0 | 0 | 0 | 100 | 40 | 40 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 0 | 0 | 100 | 40 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCBs , parts and loading | N/A | 1 | Units | 700 | 700 | 0 | 16 | 8 | 0 | 8 | hours | 1516.32 | 1 | 2216.32 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 0 | 16 | 8 | 0 | 8 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Mechanical adaptation of vacuum chuck | N/A | 1 | Units | 1500 | 1500 | 40 | 80 | 40 | 24 | 40 | hours | 14580 | 1 | 16080 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 40 | 80 | 40 | 24 | 40 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Chip carriers and tracking hardware | N/A | 1 | Units | 2000 | 2000 | 24 | 40 | 40 | 24 | 40 | hours | 9156.24 | 1 | 11156.24 | B | PD | BPD2011 | B1.2.2.2.22011 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2011 | 24 | 40 | 40 | 24 | 40 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe testing (1st batch) | N/A | 1 | Units | 1500 | 1500 | 0 | 20 | 100 | 16 | 40 | hours | 3839.4 | 1 | 5339.4 | B | PD | BPD2012 | B1.2.2.2.22012 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2012 | 0 | 20 | 100 | 16 | 40 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Probe testing (2nd batch) | N/A | 1 | Units | 1500 | 1500 | 0 | 20 | 300 | 16 | 40 | hours | 3839.4 | 1 | 5339.4 | B | PD | BPD2013 | B1.2.2.2.22013 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2013 | 0 | 20 | 300 | 16 | 40 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 1500 | 1500 | 16 | 80 | 0 | 80 | 0 | hours | 18934.56 | 1 | 20434.56 | C | PD | CPD2013 | C1.2.2.2.22013 | 1.2.2.2.2 | PXL Sensor Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 80 | 0 | 80 | 0 | 1500
[11 empty] | Sum | 82406.16 | Sum
Level Subtotal | [11 empty] | 168601.92 | Base Labor | [13 empty] | 136 | 864 | 1852 | 496 | 1608 |  | 728410 | 884435.44 |  | 240268.4 | 36 | 112 | 8 | 120 | 40 |  | 211400
Ladder Cable
Infrastructure Test Cable (PH-1) | [12 empty] | 1
PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 24 | 200 | hours | 3600 | 1 | 3600 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 16 | 24 | 200 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication | N/A | 5 | Units | 350 | 1750 | 0 | 0 | 0 | 8 | 8 | hours | 1200 | 1 | 2950 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 0 | 8 | 8 | 1750 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading material | N/A | 5 | Units | 600 | 3000 | 0 | 0 | 0 | 0 | 80 | hours | 0 | 1 | 3000 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 80 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading labor | N/A | 5 | Units | 600 | 3000 | 0 | 60 | 40 | 0 | 40 | hours | 7020 | 1 | 10020 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 60 | 40 | 0 | 40 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 16 | 8 | 124 | hours | 1200 | 1 | 1200 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 16 | 8 | 124 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | N/A | 350 | 1750 | 0 | 0 | 0 | 0 | 24 | hours | 0 | 1 | 1750 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 24 | 1750 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 1 | N/A | 0 | 0 | 0 | 60 | 0 | 0 | 80 | hours | 7020 | 1 | 7020 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 60 | 0 | 0 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 sensor test software and firmware | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 120 | 24 | 80 | hours | 3600 | 1 | 3600 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 120 | 24 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCBs , parts and loading | N/A | 1 | N/A | 700 | 700 | 0 | 16 | 24 | 8 | 24 | hours | 3072 | 1 | 3772 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 16 | 24 | 8 | 24 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and analysis | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 180 | 24 | 80 | hours | 3600 | 1 | 3600 | B | PT | BPT2010 | B1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 180 | 24 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 1500 | 1500 | 0 | 24 | 0 | 4 | 0 | hours | 3408 | 1 | 4908 | C | PT | CPT2010 | C1.2.2.3.12010 | 1.2.2.3.1 | Infrastructure Test Cable | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 0 | 4 | 0 | 1500
Prototype Ladder Cable (FR-4) | [10 empty] | Sum | 30312 | Sum
PCB design and layout | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 16 | 16 | 160 | hours | 2400 | 1 | 2400 | B | PT | BPT2010 | B1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 16 | 16 | 160 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication | N/A | 5 | Units | 200 | 1000 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 1000 | B | PT | BPT2010 | B1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 16 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading material | N/A | 5 | N/A | 200 | 1000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1000 | B | PT | BPT2010 | B1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading labor | N/A | 5 | N/A | 200 | 1000 | 0 | 60 | 24 | 0 | 40 | hours | 7020 | 1 | 8020 | B | PT | BPT2010 | B1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 60 | 24 | 0 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 1200 | C | PT | CPT2010 | C1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 8 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | N/A | 200 | 1000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1000 | C | PT | CPT2010 | C1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1000
(iteration) PCB parts and loading | N/A | 5 | N/A | 200 | 1000 | 0 | 60 | 0 | 0 | 0 | hours | 7020 | 1 | 8020 | C | PT | CPT2010 | C1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 60 | 0 | 0 | 0 | 1000
Interface PCBs , parts and loading | N/A | 1 | N/A | 700 | 700 | 0 | 16 | 24 | 0 | 32 | hours | 1872 | 1 | 2572 | B | PT | BPT2010 | B1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 16 | 24 | 0 | 32 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and analysis | N/A | 1 | Units | 8 | 8 | 0 | 0 | 120 | 16 | 80 | hours | 2400 | 1 | 2408 | B | PT | BPT2010 | B1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 120 | 16 | 80 | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 1000 | 1000 | 0 | 40 | 0 | 4 | 0 | hours | 5280 | 1 | 6280 | C | PT | CPT2010 | C1.2.2.3.22010 | 1.2.2.3.2 | Prototype Ladder Cable (FR-4) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 4 | 0 | 1000
Ladder Cable (Kapton with Cu conductor) | [10 empty] | Sum | 13692 | Sum
PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 16 | 100 | hours | 2400 | 1 | 2400 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 16 | 16 | 100 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication | N/A | 5 | Units | 500 | 2500 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 2500 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 16 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading material | N/A | 5 | Units | 200 | 1000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1000 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading labor | N/A | 5 | Units | 0 | 0 | 0 | 60 | 24 | 8 | 40 | hours | 8220 | 1 | 8220 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 60 | 24 | 8 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 16 | 80 | hours | 2400 | 1 | 2400 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 16 | 16 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | Units | 500 | 2500 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 2500 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 16 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading material | N/A | 5 | Units | 200 | 1000 | 0 | 0 | 40 | 8 | 40 | hours | 1200 | 1 | 2200 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 40 | 8 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading labor | N/A | 5 | Units | 200 | 1000 | 0 | 60 | 24 | 8 | 40 | hours | 8220 | 1 | 9220 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 60 | 24 | 8 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCBs , parts and loading | N/A | 1 | Units | 700 | 700 | 0 | 16 | 24 | 0 | 32 | hours | 1872 | 1 | 2572 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 16 | 24 | 0 | 32 | 700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and analysis | N/A | 1 | Units | 0 | 0 | 0 | 0 | 120 | 8 | 80 | hours | 1200 | 1 | 1200 | B | PT | BPT2011 | B1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 120 | 8 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1000 | C | PT | CPT2011 | C1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1000
contingency labor | N/A | 1 | Units | 0 | 0 | 0 | 40 | 0 | 0 | 0 | hours | 4680 | 1 | 4680 | C | PT | CPT2011 | C1.2.2.3.32011 | 1.2.2.3.3 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 0 | 0 | 0
Ladder Cable (Kapton with Al conductor) | [10 empty] | Sum | 25512 | Sum
PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 24 | 160 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication | N/A | 5 | Units | 1500 | 7500 | 0 | 0 | 40 | 40 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading | N/A | 5 | Units | 300 | 1500 | 0 | 80 | 24 | 8 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 16 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | Units | 1500 | 7500 | 0 | 0 | 40 | 8 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 5 | Units | 300 | 1500 | 0 | 120 | 24 | 8 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCBs , parts and loading | N/A | 1 | Units | 700 | 700 | 0 | 16 | 24 | 8 | 24 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and analysis | N/A | 1 | Units | 0 | 0 | 0 | 0 | 120 | 80 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | lb | 5000 | 5000 | 0 | 40 | 80 | 32 | 80 | hours | 0 | 0 | 0 | C | PT | CPT2011 | C1.2.3.3.42011 | 1.2.3.3.4 | PXL Sensor Ladder Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ladder Cable PXL Sensor (Al conductor) | [10 empty] | Sum | 0 | Sum
PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 24 | 160 | hours | 2916 | 1 | 2916 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 16 | 24 | 160 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication prototype (Cu) | N/A | 5 | Units | 500 | 2500 | 0 | 0 | 40 | 16 | 16 | hours | 1944 | 1 | 4444 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 40 | 16 | 16 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading prototype (Cu) | N/A | 5 | Units | 300 | 1500 | 0 | 80 | 16 | 16 | 40 | hours | 9525.6 | 1 | 11025.6 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 80 | 16 | 16 | 40 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and analysis prototype | N/A | 1 | Units | 0 | 0 | 0 | 0 | 120 | 40 | 80 | hours | 4860 | 1 | 4860 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 120 | 40 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB design and layout (Al) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 40 | 40 | hours | 4860 | 1 | 4860 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 40 | 40 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication prototype (Al) | N/A | 5 | Units | 1500 | 7500 | 0 | 0 | 40 | 40 | 40 | hours | 4860 | 1 | 12360 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 40 | 40 | 40 | 7500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading (Al) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 16 | 16 | 80 | hours | 1944 | 1 | 1944 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 16 | 16 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 16 | 40 | hours | 1944 | 1 | 1944 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 40 | 16 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | Units | 1500 | 7500 | 0 | 0 | 24 | 16 | 80 | hours | 1944 | 1 | 9444 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 24 | 16 | 80 | 7500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 5 | Units | 0 | 0 | 0 | 80 | 24 | 8 | 24 | hours | 8553.6 | 1 | 8553.6 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 80 | 24 | 8 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface PCBs , parts and loading | N/A | 5 | Units | 0 | 0 | 0 | 16 | 0 | 80 | 80 | hours | 11236.32 | 1 | 11236.32 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 16 | 0 | 80 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and analysis | N/A | 1 | Units | 0 | 0 | 0 | 0 | 120 | 8 | 80 | hours | 972 | 1 | 972 | B | PD | BPD2012 | B1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 120 | 8 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 4000 | 4000 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 12650.8 | C | PD | CPD2012 | C1.2.2.3.52012 | 1.2.2.3.5 | Ladder Cable (Kapton + Cu conductor) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 40 | 0 | 4000
[11 empty] | Sum | 55559.52 | Sum
Level Subtotal | [11 empty] | 125075.52 | Base Labor | [13 empty] | 0 | 524 | 1340 | 512 | 2272 |  | 41608 | 153475.48 |  | 35637.08 | 0 | 204 | 0 | 56 | 0 |  | 9500
PXL Prototype Ladder Assembly
Ladder Mechanical Prototypes | [12 empty] | 1
Positioning and assembly prototypes | N/A | 1 | Units | 2000 | 2000 | 80 | 80 | 40 | 16 | 80 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Positioning and assembly prototypes | N/A | 1 | Units | 2000 | 2000 | 80 | 80 | 0 | 8 | 0 | hours | 20640 | 1 | 22640 | C | PT | CPT2012 | C1.2.2.4.12012 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 80 | 80 | 0 | 8 | 0 | 2000
Thermal testing assembly | N/A | 1 | Units | 500 | 500 | 16 | 80 | 40 | 24 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
adhesives and infrastructure | N/A | 1 | Units | 500 | 500 | 0 | 40 | 0 | 16 | 24 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
wire bonding and encapsulation prototype | N/A | 1 | Units | 0 | 0 | 16 | 40 | 40 | 16 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
storage, tracking and handling hardware prototype | N/A | 1 | Units | 2500 | 2500 | 40 | 40 | 40 | 8 | 40 | hours | 10920 | 1 | 13420 | B | PT | BPT2012 | B1.2.2.4.12012 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2012 | 40 | 40 | 40 | 8 | 40 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 2500 | 2500 | 40 | 40 | 0 | 8 | 0 | hours | 10920 | 1 | 13420 | C | PT | CPT2012 | C1.2.2.4.12012 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 40 | 0 | 8 | 0 | 2500
Ladder Electrical Prototypes | [10 empty] | Sum | 10920 | Sum
Thermal testing cable | N/A | 50 | Units | 120 | 6000 | 0 | 24 | 40 | 16 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Thermal testing RDO board + cables | N/A | 1 | Units | 900 | 900 | 0 | 16 | 24 | 0 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
connector savers, prototype RDO testing interface | N/A | 1 | Units | 1000 | 1000 | 24 | 40 | 40 | 16 | 40 | hours | 10104 | 1 | 11104 | B | PT | BPT2012 | B1.2.2.4.12012 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2012 | 24 | 40 | 40 | 16 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 1000 | 1000 | 24 | 40 | 40 | 16 | 40 | hours | 0 | 0 | 0 | C | PT | CPT2009 | C1.2.2.4.12009 | 1.2.2.4.1 | Ladder Mechanical / Electrical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ladder Assembly Production | [10 empty] | Sum | 10104 | Sum
positioning and assy fixturing | N/A | 1 | Units | 2000 | 2000 | 40 | 40 | 40 | 8 | 16 | hours | 0 | 0 | 0 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CF stiffener plate fabricate | N/A | 1 | Units | 1000 | 1000 | 0 | 24 | 0 | 8 | 8 | hours | 3246.48 | 1 | 4246.48 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 24 | 0 | 8 | 8 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder asembly production | N/A | 1 | Units | 10 | 10 | 0 | 3 | 0.1 | 0.1 | 0.1 | hours | 5929.2 | 20 | 6129.2 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 60 | 2 | 2 | 2 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder asembly production contingency | N/A | 1 | Units | 10 | 10 | 0 | 3 | 0.1 | 0.1 | 0 | hours | 11858.4 | 40 | 12258.4 | C | PD | CPD2012 | C1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 4 | 4 | 0 | 400
wire bonding and encapsulation | N/A | 1 | Units | 5 | 5 | 0 | 6 | 0 | 0 | 0.5 | hours | 11372.4 | 20 | 11472.4 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 120 | 0 | 0 | 10 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
wire bonding and encapsulation contingency | N/A | 1 | Units | 5 | 5 | 0 | 6 | 0 | 0 | 0 | hours | 22744.8 | 40 | 22944.8 | C | PD | CPD2012 | C1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 240 | 0 | 0 | 0 | 200
cable production cables | N/A | 20 | Units | 800 | 16000 | 0 | 16 | 60 | 4 | 60 | hours | 2002.32 | 1 | 18002.32 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 16 | 60 | 4 | 60 | 16000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable production cables contingency | N/A | 40 | Units | 800 | 32000 | 0 | 16 | 0 | 4 | 0 | hours | 2002.32 | 1 | 34002.32 | C | PD | CPD2012 | C1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 4 | 0 | 32000
cable components and loading | N/A | 1 | Units | 100 | 100 | 0 | 4 | 0 | 0 | 0.5 | hours | 22744.8 | 60 | 28744.8 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 240 | 0 | 0 | 30 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
fine wire rdo cable assembly | N/A | 1 | Units | 50 | 50 | 0 | 8 | 0 | 0 | 0.5 | hours | 15163.2 | 20 | 16163.2 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 0 | 160 | 0 | 0 | 10 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder testing | N/A | 1 | Units | 0 | 0 | 0 | 1 | 8 | 0.5 | 8 | hours | 9331.2 | 60 | 9331.2 | B | PD | BPD2013 | B1.2.2.42013 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2013 | 0 | 60 | 480 | 30 | 480 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
connector savers, rdo interface testing (production) | N/A | 1 | Units | 1000 | 1000 | 8 | 32 | 0 | 4 | 32 | hours | 4335.12 | 1 | 5335.12 | B | PD | BPD2012 | B1.2.2.42012 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2012 | 8 | 32 | 0 | 4 | 32 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 20000 | 20000 | 16 | 80 | 0 | 8 | 0 | hours | 10186.56 | 1 | 30186.56 | C | PD | CPD2013 | C1.2.2.42013 | 1.2.2.4 | PXL Prototype Ladder Assembly | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 80 | 0 | 8 | 0 | 20000
[11 empty] | Sum | 74124.72 | Sum
Level Subtotal | [11 empty] | 95148.72 | Base Labor | [13 empty] | 72 | 792 | 622 | 72 | 712 |  | 28800 | 119954.16 |  | 129455.68 | 136 | 576 | 4 | 32 | 0 |  | 57100
RDO Electronics
RDO Motherboard | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design and PCB Layout prototype | N/A | 1 | Units | 0 | 0 | 0 | 0 | 160 | 160 | 320 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication prototype | N/A | 5 | Units | 800 | 4000 | 0 | 0 | 16 | 8 | 24 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading prototype | N/A | 5 | Units | 550 | 2750 | 24 | 80 | 0 | 8 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Xilinx V-5 develpoment boards prototype | N/A | 3 | Units | 3000 | 9000 | 0 | 0 | 0 | 0 | 32 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Xilinx Virtex-5 FPGAs prototype | N/A | 3 | Units | 1500 | 4500 | 0 | 0 | 0 | 0 | 32 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Source Interface Units (fiber optic modules) prototype | N/A | 3 | Units | 1000 | 3000 | 0 | 0 | 0 | 0 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.12009 | 1.2.2.5.1 | RDO Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
RDO motherboard prototype test | N/A | 1 | Units | 0 | 0 | 0 | 0 | 160 | 0 | 140 | hours | 0 | 1 | 0 | B | PT | BPT2010 | B1.2.2.5.12010 | 1.2.2.5.1 | RDO Board | [5 empty] | 2010 | 0 | 0 | 160 | 0 | 140 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 80 | 24 | 180 | hours | 3600 | 1 | 3600 | B | PT | BPT2011 | B1.2.2.5.12011 | 1.2.2.5.1 | RDO Board | [5 empty] | 2011 | 0 | 0 | 80 | 24 | 180 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | Units | 800 | 4000 | 0 | 0 | 0 | 40 | 24 | hours | 6000 | 1 | 10000 | B | PT | BPT2011 | B1.2.2.5.12011 | 1.2.2.5.1 | RDO Board | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 24 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 1 | Units | 550 | 550 | 0 | 80 | 0 | 8 | 40 | hours | 10560 | 1 | 11110 | B | PT | BPT2011 | B1.2.2.5.12011 | 1.2.2.5.1 | RDO Board | [5 empty] | 2011 | 0 | 80 | 0 | 8 | 40 | 550 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(contingency) PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 12000 | 1 | 12000 | C | PT | CPT2012 | C1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 80 | 0 | 0
(contingency) PCB fabrication | N/A | 5 | Units | 800 | 4000 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 10000 | C | PT | CPT2012 | C1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 4000
(contingency) PCB parts and loading | N/A | 5 | Units | 550 | 2750 | 0 | 80 | 0 | 8 | 0 | hours | 10560 | 1 | 13310 | C | PT | CPT2012 | C1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 80 | 0 | 8 | 0 | 2750
PCB Production | N/A | 15 | Units | 800 | 12000 | 0 | 0 | 16 | 16 | 40 | hours | 1944 | 1 | 13944 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 16 | 16 | 40 | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB loading FY11 | N/A | 8 | Units | 550 | 4400 | 0 | 120 | 0 | 8 | 40 | hours | 12344.4 | 1 | 16744.4 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 120 | 0 | 8 | 40 | 4400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB loading FY12 | N/A | 7 | Units | 550 | 3850 | 0 | 120 | 0 | 8 | 40 | hours | 12344.4 | 1 | 16194.4 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 120 | 0 | 8 | 40 | 3850 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
RDO motherboard test | N/A | 15 | Units | 0 | 0 | 0 | 0 | 120 | 0 | 80 | hours | 0 | 1 | 0 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 120 | 0 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Xilinx V-5 develpoment boards | N/A | 12 | Units | 3000 | 36000 | 0 | 0 | 16 | 8 | 32 | hours | 972 | 1 | 36972 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 16 | 8 | 32 | 36000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Xilinx Virtex-5 FPGAs | N/A | 12 | Units | 1500 | 18000 | 0 | 0 | 16 | 8 | 32 | hours | 972 | 1 | 18972 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 16 | 8 | 32 | 18000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Source Interface Units (fiber optic modules) | N/A | 12 | Units | 1000 | 12000 | 0 | 0 | 16 | 0 | 40 | hours | 0 | 1 | 12000 | B | PD | BPD2013 | B1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 16 | 0 | 40 | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test PCB Production | N/A | 12 | Units | 800 | 9600 | 0 | 0 | 16 | 16 | 40 | hours | 1944 | 1 | 11544 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 16 | 16 | 40 | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test PCB loading | N/A | 12 | Units | 550 | 6600 | 0 | 200 | 0 | 8 | 40 | hours | 19926 | 1 | 26526 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 200 | 0 | 8 | 40 | 6600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test RDO motherboard test | N/A | 12 | Units | 0 | 0 | 0 | 0 | 120 | 0 | 80 | hours | 0 | 1 | 0 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 120 | 0 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Xilinx V-5 develpoment boards | N/A | 12 | Units | 3000 | 36000 | 0 | 0 | 16 | 8 | 32 | hours | 972 | 1 | 36972 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 16 | 8 | 32 | 36000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Xilinx Virtex-5 FPGAs | N/A | 12 | Units | 1500 | 18000 | 0 | 0 | 16 | 8 | 32 | hours | 972 | 1 | 18972 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 16 | 8 | 32 | 18000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Source Interface Units (fiber optic modules) | N/A | 12 | Units | 1000 | 12000 | 0 | 0 | 16 | 0 | 40 | hours | 0 | 1 | 12000 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 16 | 0 | 40 | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Scintillator based cosmic ray trigger system (from beam tests) | N/A | 1 | Units | 2000 | 2000 | 0 | 0 | 16 | 0 | 40 | hours | 0 | 1 | 2000 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 16 | 0 | 40 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test firmware and software for cosmic ray readout | N/A | 1 | Units | 1000 | 1000 | 0 | 0 | 200 | 80 | 120 | hours | 9720 | 1 | 10720 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 200 | 80 | 120 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
firmware and software (PH-1 readout) fy10 | N/A | 1 | Units | 0 | 0 | 0 | 0 | 480 | 80 | 320 | hours | 12000 | 1 | 12000 | B | PT | BPT2010 | B1.2.2.5.12010 | 1.2.2.5.1 | RDO Board | [5 empty] | 2010 | 0 | 0 | 480 | 80 | 320 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
software tools / licenses | N/A | 1 | Units | 5000 | 5000 | 0 | 0 | 40 | 24 | 40 | hours | 2916 | 1 | 7916 | B | PD | BPD2011 | B1.2.2.5.12011 | 1.2.2.5.1 | RDO Board | [5 empty] | 2011 | 0 | 0 | 40 | 24 | 40 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) firmware and software (PH-1 readout) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 480 | 100 | 280 | hours | 12150 | 1 | 12150 | B | PD | BPD2011 | B1.2.2.5.12011 | 1.2.2.5.1 | RDO Board | [5 empty] | 2011 | 0 | 0 | 480 | 100 | 280 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
firmware and software (PXL Sensor readout) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 320 | 160 | 320 | hours | 19440 | 1 | 19440 | B | PD | BPD2011 | B1.2.2.5.12011 | 1.2.2.5.1 | RDO Board | [5 empty] | 2011 | 0 | 0 | 320 | 160 | 320 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) firmware and software (PXL Sensor readout) | N/A | 1 | Units | 0 | 0 | 0 | 0 | 280 | 100 | 180 | hours | 12150 | 1 | 12150 | B | PD | BPD2012 | B1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 280 | 100 | 180 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency fy12 | N/A | 1 | Units | 6000 | 6000 | 0 | 45 | 0 | 60 | 0 | hours | 11554.65 | 1 | 17554.65 | C | PD | CPD2012 | C1.2.2.5.12012 | 1.2.2.5.1 | RDO Board | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 45 | 0 | 60 | 0 | 6000
contingency fy13 | N/A | 1 | Units | 6000 | 6000 | 0 | 45 | 0 | 60 | 0 | hours | 11554.65 | 1 | 17554.65 | C | PD | CPD2013 | C1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 45 | 0 | 60 | 0 | 6000
contingency fy14 | N/A | 1 | Units | 6000 | 6000 | 0 | 35 | 0 | 50 | 0 | hours | 9391.95 | 1 | 15391.95 | C | PD | CPD2013 | C1.2.2.5.12013 | 1.2.2.5.1 | RDO Board | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 35 | 0 | 50 | 0 | 6000
Mass Termination Board | [10 empty] | Sum | 140926.8 | Sum
Design and PCB Layout prototype | N/A | 1 | Units | 0 | 0 | 0 | 0 | 120 | 40 | 120 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.22009 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication prototype | N/A | 5 | Units | 500 | 2500 | 0 | 0 | 16 | 8 | 32 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.22009 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading prototype | N/A | 5 | Units | 250 | 1250 | 0 | 40 | 0 | 8 | 24 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.22009 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB design and layout | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 0 | 80 | hours | 0 | 1 | 0 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB fabrication | N/A | 5 | Units | 500 | 2500 | 0 | 0 | 80 | 24 | 24 | hours | 2916 | 1 | 5416 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 0 | 80 | 24 | 24 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) PCB parts and loading | N/A | 5 | Units | 250 | 1250 | 0 | 40 | 0 | 8 | 24 | hours | 4762.8 | 1 | 6012.8 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 40 | 0 | 8 | 24 | 1250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MTB test | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 0 | 40 | hours | 0 | 1 | 0 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 0 | 40 | 0 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB fabrication (production) | N/A | 12 | Units | 500 | 6000 | 0 | 0 | 16 | 8 | 32 | hours | 972 | 1 | 6972 | B | PD | BPD2013 | B1.2.2.5.22013 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2013 | 0 | 0 | 16 | 8 | 32 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
PCB parts and loading (production) | N/A | 12 | Units | 250 | 3000 | 0 | 90 | 40 | 0 | 56 | hours | 8529.3 | 1 | 11529.3 | B | PD | BPD2013 | B1.2.2.5.22013 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2013 | 0 | 90 | 40 | 0 | 56 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
LU Power daughtercard (prototype) | N/A | 5 | Units | 100 | 500 | 0 | 0 | 8 | 8 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.2.5.22009 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
LU Power daughtercard production | N/A | 48 | Units | 50 | 2400 | 0 | 40 | 40 | 8 | 40 | hours | 4762.8 | 1 | 7162.8 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 40 | 40 | 8 | 40 | 2400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test PCB fabrication (production) | N/A | 12 | Units | 500 | 6000 | 0 | 0 | 16 | 8 | 32 | hours | 972 | 1 | 6972 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 0 | 16 | 8 | 32 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test PCB parts and loading (production) | N/A | 12 | Units | 250 | 3000 | 0 | 90 | 40 | 16 | 40 | hours | 10473.3 | 1 | 13473.3 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 90 | 40 | 16 | 40 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test LU Power daughtercard production | N/A | 48 | Units | 50 | 2400 | 0 | 40 | 40 | 8 | 40 | hours | 4762.8 | 1 | 7162.8 | B | PD | BPD2012 | B1.2.2.5.22012 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2012 | 0 | 40 | 40 | 8 | 40 | 2400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 4000 | 4000 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 12650.8 | C | PD | CPD2013 | C1.2.2.5.22013 | 1.2.2.5.2 | Mass Termination Board | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 40 | 0 | 4000
RDO PCs | [10 empty] | Sum | 38151 | Sum
RDO PCs (prototype) | N/A | 2 | Units | 3250 | 6500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 6500 | B | PT | BPT2011 | B1.2.2.5.32011 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
RDO PCs (production) fy12 | N/A | 2 | Units | 3250 | 6500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 6500 | B | PD | BPD2012 | B1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
RDO PCs (production) fy13 | N/A | 2 | Units | 3250 | 6500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 6500 | B | PD | BPD2013 | B1.2.2.5.32013 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
RORC Cards fy12 | N/A | 3 | Units | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 6000 | B | PD | BPD2012 | B1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
RORC Cards fy13 | N/A | 4 | Units | 2000 | 8000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 8000 | B | PD | BPD2013 | B1.2.2.5.32013 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 8000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Setup and initial configuration | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 16 | 40 | hours | 1944 | 1 | 1944 | B | PD | BPD2012 | B1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 40 | 16 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test RDO PCs (production) | N/A | 4 | Units | 3250 | 13000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 13000 | B | PD | BPD2012 | B1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 13000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test RORC Cards | N/A | 7 | Units | 2000 | 14000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 14000 | B | PD | BPD2012 | B1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 14000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Setup and initial configuration | N/A | 1 | Units | 0 | 0 | 0 | 0 | 40 | 16 | 40 | hours | 1944 | 1 | 1944 | B | PD | BPD2012 | B1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 40 | 16 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency FY12 | N/A | 1 | Units | 4000 | 4000 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 4972 | C | PD | CPD2012 | C1.2.2.5.32012 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 8 | 0 | 4000
contingency FY13 | N/A | 1 | Units | 4000 | 4000 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 4972 | C | PD | CPD2013 | C1.2.2.5.32013 | 1.2.2.5.3 | RDO PCs | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 8 | 0 | 4000
Control PC system | [10 empty] | Sum | 3888 | Sum
System Architecture design and protptype | N/A | 1 | Units | 0 | 0 | 0 | 0 | 120 | 16 | 120 | hours | 2400 | 1 | 2400 | B | PT | BPT2012 | B1.2.2.5.42012 | 1.2.2.5.4 | Control PC System | [5 empty] | 2012 | 0 | 0 | 120 | 16 | 120 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Control PCs + communication hardware | N/A | 2 | Units | 2000 | 4000 | 0 | 0 | 32 | 0 | 32 | hours | 0 | 1 | 4000 | B | PD | BPD2013 | B1.2.2.5.42013 | 1.2.2.5.4 | Control PC System | [5 empty] | 2013 | 0 | 0 | 32 | 0 | 32 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
software and firmware | N/A | 1 | Units | 2000 | 2000 | 0 | 0 | 120 | 0 | 120 | hours | 0 | 1 | 2000 | B | PD | BPD2013 | B1.2.2.5.42013 | 1.2.2.5.4 | Control PC System | [5 empty] | 2013 | 0 | 0 | 120 | 0 | 120 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) software and firmware | N/A | 1 | Units | 0 | 0 | 0 | 0 | 80 | 0 | 80 | hours | 0 | 1 | 0 | B | PD | BPD2013 | B1.2.2.5.42013 | 1.2.2.5.4 | Control PC System | [5 empty] | 2013 | 0 | 0 | 80 | 0 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 1000 | 1000 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 1972 | C | PD | CPD2013 | C1.2.2.5.42013 | 1.2.2.5.4 | Control PC System | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 8 | 0 | 1000
[11 empty] | Sum | 2400 | Sum
Level Subtotal | [11 empty] | 185365.8 | Base Labor | [13 empty] | 0 | 820 | 3168 | 832 | 3092 |  | 274050 | 452849.4 |  | 104951.65 | 0 | 245 | 0 | 362 | 0 |  | 37750
PXL Ladder Assembly (production)
Ladder Mechanical | N/A | 1 | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPT2012 | B1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Positioning and assembly prototypes update | N/A | 1 | Units | 2000 | 2000 | 80 | 80 | 40 | 16 | 40 | hours | 0 | 0 | 0 | B | PT | BPT2012 | B1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
(iteration) Positioning and assembly prototypes update | N/A | 1 | Units | 2000 | 2000 | 80 | 80 | 40 | 16 | 40 | hours | 21840 | 1 | 23840 | C | PT | CPT2012 | C1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 80 | 80 | 40 | 16 | 40 | 2000
adhesives and infrastructure | N/A | 1 | Units | 500 | 500 | 0 | 40 | 0 | 16 | 24 | hours | 7080 | 1 | 7580 | B | PT | BPT2012 | B1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 0 | 40 | 0 | 16 | 24 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
wire bonding and encapsulation prototype | N/A | 1 | Units | 0 | 0 | 16 | 40 | 40 | 16 | 40 | hours | 9096 | 1 | 9096 | B | PT | BPT2012 | B1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 16 | 40 | 40 | 16 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
storage, tracking and handling hardware update | N/A | 1 | Units | 2500 | 2500 | 40 | 40 | 40 | 16 | 40 | hours | 12120 | 1 | 14620 | B | PT | BPT2012 | B1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 40 | 40 | 40 | 16 | 40 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 2500 | 2500 | 40 | 80 | 0 | 24 | 0 | hours | 18000 | 1 | 20500 | C | PT | CPT2012 | C1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 80 | 0 | 24 | 0 | 2500
Ladder Electrical | [10 empty] | Sum | 28296 | Sum
connector savers, prototype RDO testing interface update | N/A | 1 | Units | 1000 | 1000 | 24 | 40 | 40 | 16 | 40 | hours | 8184.24 | 1 | 9184.24 | B | PD | BPD2012 | B1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 24 | 40 | 40 | 16 | 40 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | Units | 1000 | 1000 | 12 | 20 | 0 | 8 | 0 | hours | 4092.12 | 1 | 5092.12 | C | PD | CPD2012 | C1.2.2.62012 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 12 | 20 | 0 | 8 | 0 | 1000
Ladder Assembly Production | [10 empty] | Sum | 8184.24 | Sum
positioning and assy fixturing | N/A | 1 | Units | 2000 | 2000 | 40 | 40 | 40 | 8 | 16 | hours | 8845.2 | 1 | 10845.2 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 40 | 40 | 40 | 8 | 16 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CF stiffener plate | N/A | 1 | Units | 1000 | 1000 | 0 | 32 | 0 | 8 | 8 | hours | 4004.64 | 1 | 5004.64 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 32 | 0 | 8 | 8 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder asembly production FY13 | N/A | 1 | Units | 10 | 10 | 0 | 3 | 0.1 | 0.1 | 0.1 | hours | 41504.4 | 140 | 42904.4 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 420 | 14 | 14 | 14 | 1400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder asembly production FY14 | N/A | 1 | Units | 10 | 10 | 0 | 3 | 0.1 | 0.1 | 0.1 | hours | 5929.2 | 20 | 6129.2 | B | PD | BPD2014 | B1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 60 | 2 | 2 | 2 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder testing FY13 | N/A | 1 | Units | 0 | 0 | 0 | 1 | 8 | 0.5 | 8 | hours | 21772.8 | 140 | 21772.8 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 140 | 1120 | 70 | 1120 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ladder testing FY14 | N/A | 1 | Units | 0 | 0 | 0 | 1 | 8 | 0.5 | 8 | hours | 3110.4 | 20 | 3110.4 | B | PD | BPD2014 | B1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 20 | 160 | 10 | 160 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
wire bonding and encapsulation FY13 | N/A | 1 | Units | 0 | 0 | 0 | 6 | 0 | 0 | 0.5 | hours | 79606.8 | 140 | 79606.8 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 840 | 0 | 0 | 70 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
wire bonding and encapsulation FY14 | N/A | 1 | Units | 0 | 0 | 0 | 6 | 0 | 0 | 0.5 | hours | 11372.4 | 20 | 11372.4 | B | PD | BPD2014 | B1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 120 | 0 | 0 | 10 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable production cables fy13 | N/A | 140 | Units | 1500 | 210000 | 0 | 16 | 40 | 4 | 40 | hours | 2002.32 | 1 | 212002.32 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 16 | 40 | 4 | 40 | 210000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable production cables fy14 | N/A | 20 | Units | 1500 | 30000 | 0 | 16 | 40 | 4 | 40 | hours | 2002.32 | 1 | 32002.32 | B | PD | BPD2014 | B1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 16 | 40 | 4 | 40 | 30000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable production cables contingency | N/A | 40 | Units | 1500 | 60000 | 0 | 16 | 40 | 4 | 40 | hours | 2002.32 | 1 | 62002.32 | C | PD | CPD2014 | C1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 40 | 4 | 40 | 60000
cable components and loading FY13 | N/A | 1 | Units | 100 | 100 | 0 | 4 | 0 | 0 | 0.5 | hours | 53071.2 | 140 | 67071.2 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 560 | 0 | 0 | 70 | 14000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable components and loading FY14 | N/A | 1 | Units | 100 | 100 | 0 | 4 | 0 | 0 | 0.5 | hours | 7581.6 | 20 | 9581.6 | B | PD | BPD2014 | B1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 80 | 0 | 0 | 10 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2nd ladder asembly production | N/A | 1 | Units | 10 | 10 | 0 | 3 | 0.1 | 0.1 | 0.1 | hours | 0 | 0 | 0 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2nd ladder testing | N/A | 1 | Units | 0 | 0 | 0 | 1 | 8 | 0.5 | 8 | hours | 0 | 0 | 0 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2nd wire bonding and encapsulation | N/A | 1 | Units | 0 | 0 | 0 | 6 | 0 | 0 | 0.5 | hours | 0 | 0 | 0 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2nd cable components and loading | N/A | 1 | Units | 100 | 100 | 0 | 4 | 0 | 0 | 0.5 | hours | 0 | 0 | 0 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
connector savers, rdo interface testing (production) | N/A | 1 | Units | 1000 | 1000 | 8 | 32 | 0 | 4 | 32 | hours | 4335.12 | 1 | 5335.12 | B | PD | BPD2013 | B1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 8 | 32 | 0 | 4 | 32 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency FY13 | N/A | 1 | Units | 3000 | 3000 | 40 | 200 | 0 | 40 | 0 | hours | 27896.4 | 1 | 30896.4 | C | PD | CPD2013 | C1.2.2.62013 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 200 | 0 | 40 | 0 | 3000
contingency FY14 | N/A | 1 | Units | 3000 | 3000 | 40 | 50 | 0 | 40 | 0 | hours | 13680.9 | 1 | 16680.9 | C | PD | CPD2014 | C1.2.2.62014 | 1.2.2.6 | PXL Sensor Ladder Production | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 50 | 0 | 40 | 0 | 3000
[11 empty] | Sum | 245138.4 | Sum
Level Subtotal | [11 empty] | 281618.64 | Base Labor | [13 empty] | 128 | 2536 | 1536 | 188 | 1736 |  | 265600 | 541842.4 |  | 151442.14 | 212 | 446 | 80 | 132 | 80 |  | 71500
[25 empty] | 0 |  | 464 | 5720 | 9678 | 2204 | 10232 |  | 1406468 |  |  |  | 404 | 1779 | 196 | 742 | 304 |  | 405000
[27 empty] | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost |  |  |  | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost
[26 empty] | Checksum | 464 | 5720 | 9678 | 2204 | 10232 |  | 1406468 |  |  |  | 404 | 1779 | 196 | 742 | 304 |  | 405000 | Checksum
[32 empty] | Cost With Contingency | 2968675.31 | 3041902.07 |  | Contributed Labor Excluded…
Description | WBS | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009
PXL Electronics | 1.2.2 | <-- Copy Down from this Cell both columns A and B to update WBS list | [11 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | BASE | [9 empty] | CONTINGENCY
Phase-1 Sensor | 1.2.2.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
Phase-1 Prototype | 1.2.2.1.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
Phase-1 Production | 1.2.2.1.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2010 | 128 | 464 | 2756 | 336 | 2644 | 87108 |  |  |  | 2010 | 0 | 208 | 16 | 16 | 48 | 7500
PXL Sensor | 1.2.2.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2011 | 136 | 804 | 2052 | 676 | 2256 | 214750 |  |  |  | 2011 | 40 | 168 | 88 | 64 | 136 | 22250
PXL Sensor Prototype | 1.2.2.2.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 152 | 1634 | 2122 | 926 | 2516 | 425760 |  |  |  | 2012 | 252 | 849 | 52 | 316 | 80 | 256750
PXL Sensor Production | 1.2.2.2.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2013 | 48 | 2522 | 2546 | 250 | 2594 | 646650 |  |  |  | 2013 | 72 | 488 | 0 | 302 | 0 | 55500
[14 empty] | 2009 | B | [10 empty] | 2014 | 0 | 296 | 202 | 16 | 222 | 32200 |  |  |  | 2014 | 40 | 66 | 40 | 44 | 40 | 63000
Ladder Cable | 1.2.2.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure Test Cable | 1.2.2.3.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
Prototype Ladder Cable (FR-4) | 1.2.2.3.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Project Estimated Cost | [9 empty] | Project Estimated Contingency
Ladder Cable (Kapton + Cu conductor) | 1.2.2.3.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
Ladder Cable (Kapton + Al conductor) | 1.2.3.3.4 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ladder Cable PXL Sensor | 1.2.2.3.5 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2010 | 15170.4 | 51976.08 | 0 | 48576 | 0 | 87108 | 202830.48 |  |  | 2010 | 0 | 24336 | 0 | 2400 | 0 | 7500 | 34236
PXL Prototype Ladder Assembly | 1.2.2.4 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2011 | 15603.84 | 87487.92 | 0 | 88176 | 0 | 214750 | 406017.76 |  |  | 2011 | 4561.2 | 17166.24 | 0 | 8460 | 0 | 22250 | 52437.44
Ladder Mechanical / Electrical Prototypes | 1.2.2.4.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 18385.92 | 159300.18 | 0 | 115017 | 0 | 425760 | 718463.1 |  |  | 2012 | 31464.72 | 88462.53 | 0 | 43638 | 0 | 256750 | 420315.25
[26 empty] | 2013 | 4898.88 | 239009.94 | 0 | 30375 | 0 | 646650 | 920933.82 |  |  | 2013 | 7348.32 | 46247.76 | 0 | 36693 | 0 | 55500 | 145789.08
Read-out Electronics | 1.2.2.5 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2014 | 0 | 28051.92 | 0 | 1944 | 0 | 32200 | 62195.92 |  |  | 2014 | 4082.4 | 6254.82 | 0 | 5346 | 0 | 63000 | 78683.22
RDO Board | 1.2.2.5.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [8 empty] | Base Cost | 2310441.08 | [8 empty] | Contingency | 731460.99
Mass Termination Board | 1.2.2.5.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [18 empty] | Percent | 31.66%
RDO PCs | 1.2.2.5.3 | [31 empty] | 2310441.08 | checksum | [8 empty] | 731460.99 | checksum
Control PC System | 1.2.2.5.4
PXL Sensor Ladder Production | 1.2.2.6 | IF need to copy below this line to contain WBS, need to update Data Validation for cells in column "U" (WBS) AND 'Look Up' vectors for Column "V" (Descriptor) | [24 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
PXL Electronics | 1.2.2.7 | [25 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2010 | 88 | 360 | 2184 | 272 | 2188 | 37708 |  |  | CPT | 2010 | 0 | 208 | 8 | 16 | 8 | 7500
[17 empty] | BPT | [8 empty] | 2011 | 72 | 508 | 980 | 212 | 1408 | 202100 |  |  | CPT | 2011 | 20 | 56 | 0 | 24 | 0 | 7500
[17 empty] | BPT | [8 empty] | 2012 | 120 | 200 | 280 | 88 | 336 | 161500 |  |  | CPT | 2012 | 240 | 360 | 48 | 184 | 80 | 199150
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | STAR | 0 | 0 | 0 | 0 | 0 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2010 | 11088 | 42120 | 0 | 40800 | 0 | 37708 | 131716 |  | CPT | 2010 | 0 | 24336 | 0 | 2400 | 0 | 7500 | 34236
[17 empty] | BPT | [8 empty] | 2011 | 9072 | 59436 | 0 | 31800 | 0 | 202100 | 302408 |  | CPT | 2011 | 2520 | 6552 | 0 | 3600 | 0 | 7500 | 20172
[17 empty] | BPT | [8 empty] | 2012 | 15120 | 23400 | 0 | 13200 | 0 | 161500 | 213220 |  | CPT | 2012 | 30240 | 42120 | 0 | 27600 | 0 | 199150 | 299110
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 647344 | [8 empty] | Contingency | 353518
[42 empty] | Percent | 54.61%
[27 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[27 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 40 | 104 | 572 | 64 | 456 | 49400 |  |  | CPD | 2010 | 0 | 0 | 8 | 0 | 40 | 0
[17 empty] | BPD | [8 empty] | 2011 | 64 | 296 | 1072 | 464 | 848 | 12650 |  |  | CPD | 2011 | 20 | 112 | 88 | 40 | 136 | 14750
[17 empty] | BPD | [8 empty] | 2012 | 32 | 1434 | 1842 | 838 | 2180 | 264260 |  |  | CPD | 2012 | 12 | 489 | 4 | 132 | 0 | 57600
[17 empty] | BPD | [8 empty] | 2013 | 48 | 2522 | 2546 | 250 | 2594 | 646650 |  |  | CPD | 2013 | 72 | 488 | 0 | 302 | 0 | 55500
[17 empty] | BPD | [8 empty] | 2014 | 0 | 296 | 202 | 16 | 222 | 32200 |  |  | CPD | 2014 | 40 | 66 | 40 | 44 | 40 | 63000
[17 empty] | BPD | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | STAR | 0 | 0 | 0 | 0 | 0 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 4082.4 | 9856.08 | 0 | 7776 | 0 | 49400 | 71114.48 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 6531.84 | 28051.92 | 0 | 56376 | 0 | 12650 | 103609.76 |  | CPD | 2011 | 2041.2 | 10614.24 | 0 | 4860 | 0 | 14750 | 32265.44
[17 empty] | BPD | [8 empty] | 2012 | 3265.92 | 135900.18 | 0 | 101817 | 0 | 264260 | 505243.1 |  | CPD | 2012 | 1224.72 | 46342.53 | 0 | 16038 | 0 | 57600 | 121205.25
[17 empty] | BPD | [8 empty] | 2013 | 4898.88 | 239009.94 | 0 | 30375 | 0 | 646650 | 920933.82 |  | CPD | 2013 | 7348.32 | 46247.76 | 0 | 36693 | 0 | 55500 | 145789.08
[17 empty] | BPD | [8 empty] | 2014 | 0 | 28051.92 | 0 | 1944 | 0 | 32200 | 62195.92 |  | CPD | 2014 | 4082.4 | 6254.82 | 0 | 5346 | 0 | 63000 | 78683.22
[32 empty] | Base Cost | 1663097.08 | [8 empty] | Contingency | 377942.99
[42 empty] | Percent | 22.73%
Note on C40: leo: 10 wafers / detector at 75% yield 16 wafers / detector at 50% yield This is full yield to sector level

## Rates
Values below used only for reference--not linked to data in sheet estimate…
| Construction | R&D |  | English | Metric | Quoted |  | Metric
Shop | 102.06 | 126 | Material | lb/in^3 | g/cc | Cost/Unit | Unit | Cost/Unit | Unit
Postdoc (cont) | 0 | 0 | Aluminum | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
M_Tech | 94.77 | 117 | MIC-6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
Engineer | 121.5 | 150 | 6061-T6 | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
Eng (cont) | 0 | 0 | 7075-T6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
|  |  | Titanium | 0.198 | 5.4855 | 15 | $/lb | 0.030992 | $/g
Construction Rate does not have full Burden--currently ~81% (below) of Full Burden at LBNL (R&D Rate) |  |  | 6Al4V | 0.198 | 5.4855 | 20 | $/lb | 0.041322 | $/g
|  |  | Steel | 0.298 | 8.256 | 3 | $/lb | 0.0061983 | $/g
|  |  | 304SS | 0.298 | 8.256 | 15 | $/lb | 0.030992 | $/g
|  |  | Carbon Fiber | 0.065 | 1.8008 | 100 | $/lb | 0.20661 | $/g
Differential | 81% |  | M55J-UDT | 0.065 | 1.8008 | 800 | $/lb | 1.6529 | $/g
Change This to change burden rate… |  |  | CN60-PW | 0.065 | 1.8008 | 500 | $/lb | 1.0331 | $/g
|  |  | YSH80A-UDT | 0.065 | 1.8008 | 1200 | $/lb | 2.4793 | $/g
|  |  | Adhesive | 0.055 | 1.5238 | 400 | $/qt | 0.42283 | $/cc
|  |  | EA9396 | 0.055 | 1.5238 | 350 | $/qt | 0.36998 | $/cc
|  |  | EA9394 | 0.075 | 2.0779 | 450 | $/qt | 0.47569 | $/cc
|  |  | CF HoneyComb | 0.0017361 | 0.048099 | 600 | $/bdft | 0.25424 | $/cc
|  |  | Al HoneyComb | 0.0017361 | 0.048099 | 75 | $/bdft | 0.03178 | $/cc
|  |  | Nomex HC | 0.0023148 | 0.064131 | 100 | $/bdft | 0.042373 | $/cc
|  |  | PEEK | 0.055 | 1.5238 | 400 | $/lb | 0.82645 | $/g
|  |  | CF PEEK | 0.055 | 1.5238 | 600 | $/lb | 1.2397 | $/g

## Material Estimates
Material Estimates per component |  |  | Values used to estimate Size/Cost of Batch Orders--Does not report to Cost Summary
Item | Material | Descriptor | Quantity | CPT (microns) | Density (g/cc) | Finished Form | % Waste | Length (cm) | Diameter/Width (cm) | Thickness (cm) | Volume (cc) | Mass (g) | Pre-Preg Area (m^2) | Cost Per Unit | Choose Unit | Cost | Prototype Mass | Prototype Area | Prototype Composites
Material Volumes | [19 empty] | /cc | Bulk | 1
D-Tube | [19 empty] | /g | Plate | 2
Tooling | [19 empty] | /m^2 | Round | 3
Mandrel | Steel | Pipe | 1 | n/a | 8.3 | Shell | 0% | 60 | 20 | 1.5 | 5654.8668 | 46935.3942 | #VALUE! | 0.006 | /g | 281.6124 | 0 | 0 | 0 |  | Shell | 4
Mandrel End Plates | Steel | Plate | 1 | n/a | 8.3 | Plate | 0% | 60 | 25 | 3 | 4500 | 37350 | #VALUE! | 0.006 | /g | 224.1 | 0 | 0 | 0
D-Tube Bond Tool
Tooling
Support Beam Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 100 | 30 | 3 | 9000 | 24300 | #VALUE! | 0.017 | /g | 413.1 | 0 | 0 | 0
Support Beam Machining Tool | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 0% | 30 | 15 | 5 | 4500 | 12150 | #VALUE! | 0.017 | /g | 206.55 | 0 | 0 | 0
Components | [11 empty] | 80.2863
Thick Laminate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Plate | 30% | 80 | 2.5 | 0.8 | 1040 | 1872 | 3.1515 | 1.033 | /g | 1933.776 | 0 | 0 | 0
Thick Laminate Test | CN60 Cloth | Test | 2 | 330 | 1.8 | Plate | 50% | 20 | 3 | 0.8 | 144 | 259.2 | 0.43636 | 1.033 | /g | 267.7536 | 259.2 | 0.43636 | 267.7536
Insertion Test Bed
Support Components
Item Bars | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 250 | 7.5 | 7.5 | 73125 | 197437.5 | #VALUE! | 0.017 | /g | 3356.4375 | 0 | 0 | 0
Station Plates | Aluminum | Plate | 3 | n/a | 2.7 | Plate | 30% | 50 | 50 | 5 | 48750 | 131625 | #VALUE! | 0.017 | /g | 2237.625 | 0 | 0 | 0
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Iteration | [11 empty] | 840.7764 |  |  |  | 6489.1125
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Prototype | [11 empty] | 115.9692 |  |  |  | 895.05
Cart Rail Rider prototype | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Low Mass Cart | [11 empty] | 154.6256 |  |  |  | 1193.4
Cart Rail Rider | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Tooling | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 60 | 30 | 5 | 11700 | 31590 | 35.4545 | 0.017 | /g | 537.03 | 0 | 0 | 0