## WBS in Estimate
This table drives values in a lookup table in the Pre- and Production Sheet, columns U and V. It is 'copied' into that sheet at the bottom, see notes there to understand how to modify this. 'Inserting' rows does not work, only adding, so must modify whole table--5 rows are available for additions...
WBS | Description
1.2.4 | Infrastructure
1.2.4.1 | Cables
1.2.4.1.1 | Internal Cables (Engineering)
1.2.4.1.2 | Internal Cables (Production)
1.2.4.1.3 | External Cables
1.2.4.1.3.1 | Type 1 (Bulkhead to DAQ Crate)
1.2.4.1.3.2 | Type 2 (DAQ to PS)
1.2.4.1.3.3 | Data/Control Fibers
1.2.4.1.3.4 | Test Cables (External)
1.2.4.1.3.5 | Type 1 (Bulkhead to DAQ Crate)
1.2.4.1.3.6 | Type 2 (DAQ to PS)
1.2.4.1.3.7 | Data/Control Fibers
1.2.4.2 | Cooling Services
1.2.4.2.1 | Internal Ducting (Engineering)
1.2.4.2.2 | Internal Ducting (Production)
1.2.4.2.3 | External Ducting
1.2.4.2.4 | Test Ducting
1.2.4.3 | Rack Equipment
1.2.4.3.1 | DAQ Crate Prototype
1.2.4.3.2 | DAQ Crate Production
1.2.4.3.3 | Power Supplies
1.2.4.3.4 | Cooling Plant
1.2.4.3.5 | Test DAQ
1.2.4.3.6 | Test Power Supplies
1.2.4.3.7 | Test Cooling Plant

## SUMMARY
| BASE | [9 empty] | CONTINGENCY
| Shop Labor | Tech Labor | PostDoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 5 | 73 | 80 | 106.5 | 157.5 | 43450 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 40 | 142 | 253 | 112 | 224 | 22000 |  |  |  | 2011 | 8 | 56 | 184 | 92 | 128 | 4000
2012 | 192 | 1053.2 | 434 | 335.6 | 298.4 | 111660 |  |  |  | 2012 | 45 | 212 | 172 | 192 | 136 | 42300
2013 | 4 | 710.4 | 372 | 53.8 | 111 | 35820 |  |  |  | 2013 | 8 | 68 | 80 | 28.6 | 65.2 | 9900
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 40 | 224 | 40 | 280 | 32 | 12000 |  |  |  | STAR | 0 | 0 | 0 | 16 | 8 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Contingency
| Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals | V0.5 | Delta |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals | V0.5 | Delta | FY | V0.5 | V0.6 | Delta
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0
2010 | 630 | 8363.16 | 0 | 13809 | 0 | 43450 | 66252.16 | 66252.16 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 66252.16 | 66252.16 | 0
2011 | 5040 | 15546.96 | 0 | 15432 | 0 | 22000 | 58018.96 | 283600.794 | 225581.834 | 2011 | 1008 | 5484.96 | 0 | 11862 | 0 | 4000 | 22354.96 | 89658.4 | 67303.44 | 2011 | 373259.194 | 80373.92 | -292885.274
2012 | 23425.92 | 107903.484 | 0 | 46486.8 | 0 | 111660 | 289476.204 | 169067.918 | -120408.286 | 2012 | 5191.2 | 22669.92 | 0 | 12000 | 0 | 42300 | 82161.12 | 32934.52 | -49226.6 | 2012 | 202002.438 | 371637.324 | 169634.886
2013 | 408.24 | 67324.608 | 0 | 6536.7 | 0 | 35820 | 110089.548 | 4916 | -105173.548 | 2013 | 816.48 | 6444.36 | 0 | 8262 | 0 | 9900 | 25422.84 | 13178 | -12244.84 | 2013 | 18094 | 135512.388 | 117418.388
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 0 | 0 | 0 | 13608 | 0 | 0 | 13608 | 13194.9 | -413.1 | 2014 | 13194.9 | 13608 | 413.1
[6 empty] | Base Cost | 523836.872 | [8 empty] | Contingency | 143546.92 |  |  | Totals | 672802.692 | 667383.792 | -5418.9
[16 empty] | Percent | 27.4%
| Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 5 | 65 | 16 | 30.5 | 93.5 | 2050 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 40 | 94 | 101 | 64 | 192 | 15500 |  |  |  | 2011 | 8 | 8 | 8 | 24 | 48 | 500
2012 | 160 | 364 | 92 | 200.4 | 112.8 | 64720 |  |  |  | 2012 | 25 | 116 | 84 | 80 | 64 | 27600
2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 24 | 144 | 0 | 160 | 16 | 4000 |  |  |  | STAR | 0 | 0 | 0 | 16 | 8 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 630 | 7605 | 0 | 4575 | 0 | 2050 | 14860 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 5040 | 10998 | 0 | 9600 | 0 | 15500 | 41138 |  |  | 2011 | 1008 | 936 | 0 | 3600 | 0 | 500 | 6044
2012 | 20160 | 42588 | 0 | 30060 | 0 | 64720 | 157528 |  |  | 2012 | 3150 | 13572 | 0 | 12000 | 0 | 27600 | 56322
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 213526 | [8 empty] | Contingency | 62366
[16 empty] | Percent | 29.21%
| Production Base Cost | [9 empty] | Production Contingency Cost
| Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 8 | 64 | 76 | 64 | 41400 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0 | 48 | 152 | 48 | 32 | 6500 |  |  |  | 2011 | 0 | 48 | 176 | 68 | 80 | 3500
2012 | 32 | 689.2 | 342 | 135.2 | 185.6 | 46940 |  |  |  | 2012 | 20 | 96 | 88 | 112 | 72 | 14700
2013 | 4 | 710.4 | 372 | 53.8 | 111 | 35820 |  |  |  | 2013 | 8 | 68 | 80 | 28.6 | 65.2 | 9900
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 16 | 80 | 40 | 120 | 16 | 8000 |  |  |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 0 | 758.16 | 0 | 9234 | 0 | 41400 | 51392.16 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 0 | 4548.96 | 0 | 5832 | 0 | 6500 | 16880.96 |  |  | 2011 | 0 | 4548.96 | 0 | 8262 | 0 | 3500 | 16310.96
2012 | 3265.92 | 65315.484 | 0 | 16426.8 | 0 | 46940 | 131948.204 |  |  | 2012 | 2041.2 | 9097.92 | 0 | 0 | 0 | 14700 | 25839.12
2013 | 408.24 | 67324.608 | 0 | 6536.7 | 0 | 35820 | 110089.548 |  |  | 2013 | 816.48 | 6444.36 | 0 | 8262 | 0 | 9900 | 25422.84
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 13608 | 0 | 0 | 13608
[6 empty] | Base Cost | 310310.872 | [8 empty] | Contingency | 81180.92
[16 empty] | Percent | 26.16%

## Pre- and Production
[17 empty] | (HIDE) |  |  |  | (HIDE AS REQUIRED)
Infrastructure (1.2.4) | [14 empty] | TRACKING | [11 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | PostDoc (cont) | Eng Time | Engineer (cont) | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | Sum Logic Code | WBS | WBS Descriptor | PO/UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | PostDoc (cont) | Engineering | Engineer (cont) | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | PostDoc (cont) | Engineering | Engineer (cont) | Materials Sub Totals | Materials Totals
Cables | [24 empty] | Underage(-)
Internal Cables (Engineering) | [12 empty] | 1 | [11 empty] | Underage(-)
cable design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 40 | hours | 1200 | 1 | 1200 | B | PT | BPT2010 | B1.2.4.1.12010 | 1.2.4.1.1 | Internal Cables (Engineering) | [5 empty] | 2010 | 0 | 0 | 0 | 8 | 40 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
connectors specify | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 20 | 20 | hours | 3000 | 1 | 3000 | B | PT | BPT2010 | B1.2.4.1.12010 | 1.2.4.1.1 | Internal Cables (Engineering) | [5 empty] | 2010 | 0 | 0 | 0 | 20 | 20 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
prototype construction | N/A | 1 | N/A | 400 | 400 | 0.5 | 6 | 0 | 0 | 0.2 | hours | 3825 | 5 | 5825 | B | PT | BPT2010 | B1.2.4.1.12010 | 1.2.4.1.1 | Internal Cables (Engineering) | [5 empty] | 2010 | 2.5 | 30 | 0 | 0 | 1 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cable Fabrication | N/A | 20 | N/A | 600 | 12000 | 0 | 0 | 16 | 8 | 16 | hours | 1200 | 1 | 13200 | B | PT | BPT2011 | B1.2.4.1.22011 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2011 | 0 | 0 | 16 | 8 | 16 | 12000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency | N/A | 36 | N/A | 600 | 21600 | 0 | 0 | 16 | 8 | 16 | hours | 1200 | 1 | 22800 | C | PT | CPT2012 | C1.2.4.1.22012 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 16 | 8 | 16 | 21600
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 2 | 1 | 0 | 0 | hours | 1170 | 5 | 1170 | B | PT | BPT2011 | B1.2.4.1.12011 | 1.2.4.1.1 | Internal Cables (Engineering) | [5 empty] | 2011 | 0 | 10 | 5 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 8 | 8 | 8 | 8 | 8 | hours | 3144 | 1 | 3644 | C | PT | CPT2011 | C1.2.4.1.12011 | 1.2.4.1.1 | Internal Cables (Engineering) | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 8 | 8 | 8 | 8 | 500
Internal Cables (Production) | [10 empty] | Sum | 10395 | Base Labor
Cable Fabrication | N/A | 46 | N/A | 600 | 27600 | 0 | 0 | 16 | 8 | 16 | hours | 972 | 1 | 28572 | B | PD | BPD2013 | B1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 0 | 16 | 8 | 16 | 27600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency | N/A | 6 | N/A | 600 | 3600 | 0 | 0 | 16 | 8 | 16 | hours | 972 | 1 | 4572 | C | PD | CPD2013 | C1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 16 | 8 | 16 | 3600
Acceptance testing | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | hours | 4359.42 | 46 | 4359.42 | B | PD | BPD2013 | B1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 46 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable modification (cut and solder PCB connector - 1/2 cable) | N/A | 1 | N/A | 50 | 50 | 0 | 6 | 1 | 0.1 | 0.2 | hours | 26715.42 | 46 | 29015.42 | B | PD | BPD2013 | B1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 276 | 46 | 4.6 | 9.2 | 2300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable modification (contingency) | N/A | 1 | N/A | 50 | 50 | 0 | 6 | 4 | 0.1 | 0.2 | hours | 3484.62 | 6 | 3784.62 | C | PD | CPD2013 | C1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 36 | 24 | 0.6 | 1.2 | 300
Power distribution cable to MTBs | N/A | 1 | N/A | 10 | 10 | 0 | 0.2 | 0 | 0 | 0 | hours | 871.884 | 46 | 1331.884 | B | PD | BPD2013 | B1.2.4.1.3.12013 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2013 | 0 | 9.2 | 0 | 0 | 0 | 460 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
interface PCB to cable tester, both ends | N/A | 4 | N/A | 700 | 2800 | 4 | 24 | 16 | 8 | 40 | hours | 3654.72 | 1 | 6454.72 | B | PD | BPD2013 | B1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 4 | 24 | 16 | 8 | 40 | 2800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
acceptance testing | N/A | 1 | N/A | 200 | 200 | 0 | 24 | 40 | 0 | 8 | hours | 2274.48 | 1 | 2474.48 | B | PD | BPD2013 | B1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 24 | 40 | 0 | 8 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 2000 | 2000 | 4 | 16 | 8 | 8 | 16 | hours | 2896.56 | 1 | 4896.56 | C | PD | CPD2013 | C1.2.4.1.22013 | 1.2.4.1.2 | Internal Cables (Production) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 16 | 8 | 8 | 16 | 2000
[11 empty] | Sum | 38847.924 | Base Labor
External Cables | [12 empty] | 1 | [11 empty] | Underage(-)
Type 1 (Bulkhead to RDO Crate) | [12 empty] | 1 | [11 empty] | Underage(-)
cable design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 0 | B | PT | BPT2010 | B1.2.4.1.3.12010 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
connectors | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 16 | 0 | 16 | hours | 0 | 1 | 0 | B | PT | BPT2010 | B1.2.4.1.3.12010 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2010 | 0 | 0 | 16 | 0 | 16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
prototype construction | N/A | 1 | N/A | 0 | 0 | 0.5 | 6 | 0 | 0.5 | 0.1 | hours | 4200 | 5 | 4200 | B | PT | BPT2010 | B1.2.4.1.3.12010 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2010 | 2.5 | 30 | 0 | 2.5 | 0.5 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 10 | 10 | 0 | 1 | 0 | 0 | 0 | hours | 585 | 5 | 635 | B | PT | BPT2010 | B1.2.4.1.3.12010 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2010 | 0 | 5 | 0 | 0 | 0 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Batch 1 procurement (procured above) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPD2012 | B1.2.4.1.3.12012 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Batch 1 cable modification | N/A | 1 | N/A | 0 | 0 | 0 | 6 | 4 | 0.1 | 0.2 | hours | 9292.32 | 16 | 9292.32 | B | PD | BPD2012 | B1.2.4.1.3.12012 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 96 | 64 | 1.6 | 3.2 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Batch 1 power distribution cable to MTB | N/A | 1 | N/A | 10 | 10 | 0 | 0.2 | 0 | 0 | 0 | hours | 303.264 | 16 | 463.264 | B | PD | BPD2012 | B1.2.4.1.3.12012 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 3.2 | 0 | 0 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 10 | 10 | 0 | 1 | 0 | 0 | 0 | hours | 1516.32 | 16 | 1676.32 | B | PD | BPD2012 | B1.2.4.1.3.12012 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 16 | 0 | 0 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Batch 2 procurement (procured above) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPD2013 | B1.2.4.1.3.12013 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Batch 2 cable modification | N/A | 1 | N/A | 0 | 0 | 0 | 6 | 4 | 0.1 | 0.2 | hours | 26715.42 | 46 | 26715.42 | B | PD | BPD2013 | B1.2.4.1.3.12013 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2013 | 0 | 276 | 184 | 4.6 | 9.2 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Batch 2 power distribution cable to MTB | N/A | 1 | N/A | 10 | 10 | 0 | 0.2 | 0 | 0 | 0 | hours | 871.884 | 46 | 1331.884 | B | PD | BPD2013 | B1.2.4.1.3.12013 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2013 | 0 | 9.2 | 0 | 0 | 0 | 460 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 1 | 0.1 | 0.1 | hours | 4918.32 | 46 | 4918.32 | B | PD | BPD2013 | B1.2.4.1.3.12013 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2013 | 0 | 46 | 46 | 4.6 | 4.6 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 2000 | 2000 | 4 | 16 | 16 | 4 | 16 | hours | 2410.56 | 1 | 4410.56 | C | PD | CPD2013 | C1.2.4.1.3.12013 | 1.2.4.1.3.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 16 | 16 | 4 | 16 | 2000
Type 2 (RDO to PS) | [10 empty] | Sum | 48402.528 | Base Labor
Power cable design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 32 | hours | 2400 | 1 | 2400 | B | PT | BPT2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 0 | 0 | 16 | 32 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
System control/config design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 32 | hours | 2400 | 1 | 2400 | B | PT | BPT2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 0 | 0 | 16 | 32 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Power cable prototype | N/A | 1 | N/A | 500 | 500 | 0 | 24 | 24 | 0 | 8 | hours | 2808 | 1 | 3308 | B | PT | BPT2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 24 | 24 | 0 | 8 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
System control/config prototype | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPD2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 8 | 16 | 0 | 4 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 8 | 16 | 0 | 4 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Power cable production | N/A | 1 | N/A | 1000 | 1000 | 0 | 40 | 16 | 0 | 4 | hours | 3790.8 | 1 | 4790.8 | B | PD | BPD2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 40 | 16 | 0 | 4 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
System control/config production | N/A | 1 | N/A | 400 | 400 | 0 | 8 | 8 | 0 | 8 | hours | 758.16 | 1 | 1158.16 | B | PD | BPD2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 8 | 8 | 0 | 8 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 16 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPD2012 | B1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 0 | 16 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 0 | 8 | 8 | 4 | 16 | hours | 1244.16 | 1 | 1744.16 | C | PD | CPD2012 | C1.2.4.1.3.22012 | 1.2.4.1.3.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 8 | 4 | 16 | 500
Data Control Fibers | [10 empty] | Sum | 12915.12 | Base Labor
cable specify | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 8 | 16 | hours | 972 | 1 | 972 | B | PD | BPD2012 | B1.2.4.1.3.32012 | 1.2.4.1.3.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 0 | 0 | 8 | 16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable procurement | N/A | 14 | N/A | 300 | 4200 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 4200 | B | PD | BPD2012 | B1.2.4.1.3.32012 | 1.2.4.1.3.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 16 | 4200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | hours | 1326.78 | 14 | 1326.78 | B | PD | BPD2012 | B1.2.4.1.3.32012 | 1.2.4.1.3.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 14 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 10 | 10 | 0 | 0.5 | 1 | 0.1 | 0.1 | hours | 2738.61 | 46 | 3198.61 | B | PD | BPD2012 | B1.2.4.1.3.32012 | 1.2.4.1.3.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 23 | 46 | 4.6 | 4.6 | 460 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 600 | 600 | 0 | 4 | 0 | 0 | 8 | hours | 379.08 | 1 | 979.08 | C | PD | CPD2012 | C1.2.4.1.3.32012 | 1.2.4.1.3.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 0 | 8 | 600
[11 empty] | Sum | 5037.39 | Base Labor
Test Cables (External) | [12 empty] | 1 | [11 empty] | Underage(-)
Type 1 (Bulkhead to RDO Crate) | [12 empty] | 1 | [11 empty] | Underage(-)
Cable Fabrication | N/A | 44 | N/A | 600 | 26400 | 0 | 0 | 16 | 8 | 16 | hours | 972 | 1 | 27372 | B | PD | BPD2012 | B1.2.4.1.4.12012 | 1.2.4.1.4.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 0 | 16 | 8 | 16 | 26400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency | N/A | 6 | N/A | 600 | 3600 | 0 | 0 | 0 | 0 | 8 | hours | 0 | 1 | 3600 | B | PD | BPD2012 | B1.2.4.1.4.12012 | 1.2.4.1.4.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 8 | 3600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | hours | 0 | 44 | 0 | B | PD | BPD2012 | B1.2.4.1.4.12012 | 1.2.4.1.4.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 0 | 22 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
cable modification (cut and solder PCB connector - 1/2 cable) | N/A | 1 | N/A | 0 | 0 | 0 | 6 | 1 | 0.1 | 0.2 | hours | 25553.88 | 44 | 25553.88 | B | PD | BPD2012 | B1.2.4.1.4.12012 | 1.2.4.1.4.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 264 | 44 | 4.4 | 8.8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0.1 | hours | 4169.88 | 44 | 4169.88 | B | PD | BPD2012 | B1.2.4.1.4.12012 | 1.2.4.1.4.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 44 | 0 | 0 | 4.4 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 10 | 10 | 0 | 0.5 | 1 | 0.1 | 0.1 | hours | 2738.61 | 46 | 3198.61 | B | PD | BPD2012 | B1.2.4.1.3.32012 | 1.2.4.1.3.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 23 | 46 | 4.6 | 4.6 | 460 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 2000 | 2000 | 4 | 8 | 32 | 8 | 16 | hours | 2138.4 | 1 | 4138.4 | C | PD | CPD2012 | C1.2.4.1.4.12012 | 1.2.4.1.4.1 | Type 1 (Bulkhead to RDO Crate) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 8 | 32 | 8 | 16 | 2000
Type 2 (RDO to PS) | [10 empty] | Sum | 33434.37 | Base Labor
Power cable production | N/A | 1 | N/A | 1000 | 1000 | 0 | 40 | 16 | 8 | 8 | hours | 4762.8 | 1 | 5762.8 | B | PD | BPD2012 | B1.2.4.1.4.22012 | 1.2.4.1.4.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 40 | 16 | 8 | 8 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
System control/config production | N/A | 1 | N/A | 400 | 400 | 0 | 8 | 8 | 0 | 8 | hours | 758.16 | 1 | 1158.16 | B | PD | BPD2012 | B1.2.4.1.4.22012 | 1.2.4.1.4.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 8 | 8 | 0 | 8 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 8 | 16 | 0 | 8 | hours | 758.16 | 1 | 758.16 | B | PD | BPD2012 | B1.2.4.1.4.22012 | 1.2.4.1.4.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 8 | 16 | 0 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 0 | 8 | 8 | 4 | 8 | hours | 1244.16 | 1 | 1744.16 | C | PD | CPD2012 | C1.2.4.1.4.22012 | 1.2.4.1.4.2 | Type 2 (RDO to PS) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 8 | 4 | 8 | 500
Data Control Fibers | [10 empty] | Sum | 48402.528 | Base Labor
cable procurement | N/A | 14 | N/A | 300 | 4200 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 4200 | B | PD | BPD2012 | B1.2.4.1.4.32012 | 1.2.4.1.4.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 16 | 4200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | hours | 1326.78 | 14 | 1326.78 | B | PD | BPD2012 | B1.2.4.1.4.32012 | 1.2.4.1.4.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 14 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 600 | 600 | 0 | 4 | 0 | 0 | 8 | hours | 379.08 | 1 | 979.08 | C | PD | CPD2012 | C1.2.4.1.4.32012 | 1.2.4.1.4.3 | Data/Control Fibers | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 0 | 8 | 600
Cables Subtotal | [11 empty] | 156638.232 | Base Labor | [13 empty] | 9 | 1418.6 | 743 | 139.5 | 406.1 |  | 90810 | 243118.512 |  | 52867.26 | 20 | 108 | 136 | 52.6 | 129.2 |  | 34200
Cooling Services
Internal Ducting (Engineering) | [12 empty] | 1
engineering design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 8 | hours | 6000 | 1 | 6000 | B | PT | BPTSTAR | B1.2.4.2.1STAR | 1.2.4.2.1 | Internal Ducting (Engineering) | [5 empty] | STAR | 0 | 0 | 0 | 40 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
spec size, insulation, material | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 8 | hours | 2400 | 1 | 2400 | B | PT | BPTSTAR | B1.2.4.2.1STAR | 1.2.4.2.1 | Internal Ducting (Engineering) | [5 empty] | STAR | 0 | 0 | 0 | 16 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 8 | hours | 2400 | 1 | 2400 | C | PT | CPTSTAR | C1.2.4.2.1STAR | 1.2.4.2.1 | Internal Ducting (Engineering) | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 16 | 8 | 0
Internal Ducting (Production) | [10 empty] | Sum | 8400 | Base Labor
ducting prototype section | N/A | 1 | N/A | 2000 | 2000 | 24 | 40 | 0 | 40 | 16 | hours | 13704 | 1 | 15704 | B | PT | BPT2012 | B1.2.4.2.22012 | 1.2.4.2.2 | Internal Ducting (Production) | [5 empty] | 2012 | 24 | 40 | 0 | 40 | 16 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and validation | N/A | 1 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 6144 | 1 | 6144 | B | PT | BPT2012 | B1.2.4.2.22012 | 1.2.4.2.2 | Internal Ducting (Production) | [5 empty] | 2012 | 0 | 32 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
production ducting procure | N/A | 1 | N/A | 2000 | 2000 | 0 | 0 | 0 | 8 | 8 | hours | 972 | 1 | 2972 | B | PD | BPD2012 | B1.2.4.2.22012 | 1.2.4.2.2 | Internal Ducting (Production) | [5 empty] | 2012 | 0 | 0 | 0 | 8 | 8 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 40 | 0 | 16 | 8 | hours | 5734.8 | 1 | 5734.8 | B | PD | BPD2012 | B1.2.4.2.22012 | 1.2.4.2.2 | Internal Ducting (Production) | [5 empty] | 2012 | 0 | 40 | 0 | 16 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
flange passthrough | N/A | 1 | N/A | 500 | 500 | 32 | 40 | 8 | 32 | 8 | hours | 10944.72 | 1 | 11444.72 | B | PD | BPD2012 | B1.2.4.2.22012 | 1.2.4.2.2 | Internal Ducting (Production) | [5 empty] | 2012 | 32 | 40 | 8 | 32 | 8 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 8 | 24 | 0 | 16 | 8 | hours | 5034.96 | 1 | 5534.96 | C | PD | CPD2012 | C1.2.4.2.22012 | 1.2.4.2.2 | Internal Ducting (Production) | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 24 | 0 | 16 | 8 | 500
External Ducting | [10 empty] | Sum | 37499.52 | Base Labor
engineering design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 32 | 16 | hours | 3888 | 1 | 3888 | B | PD | BPD2012 | B1.2.4.2.32012 | 1.2.4.2.3 | External Ducting | [5 empty] | 2012 | 0 | 0 | 0 | 32 | 16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ducting prototype section | N/A | 1 | N/A | 0 | 0 | 0 | 32 | 8 | 8 | 8 | hours | 4944 | 1 | 4944 | B | PT | BPT2012 | B1.2.4.2.32012 | 1.2.4.2.3 | External Ducting | [5 empty] | 2012 | 0 | 32 | 8 | 8 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
testing and validation | N/A | 1 | N/A | 500 | 500 | 0 | 24 | 0 | 8 | 8 | hours | 4008 | 1 | 4508 | B | PT | BPT2012 | B1.2.4.2.32012 | 1.2.4.2.3 | External Ducting | [5 empty] | 2012 | 0 | 24 | 0 | 8 | 8 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
production ducting procure | N/A | 200 | N/A | 10 | 2000 | 0 | 0 | 0 | 8 | 8 | hours | 972 | 1 | 2972 | B | PD | BPD2012 | B1.2.4.2.32012 | 1.2.4.2.3 | External Ducting | [5 empty] | 2012 | 0 | 0 | 0 | 8 | 8 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PD | BPDSTAR | B1.2.4.2.3STAR | 1.2.4.2.3 | External Ducting | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 0 | 16 | 8 | 24 | 8 | hours | 5472 | 1 | 5972 | C | PT | CPT2012 | C1.2.4.2.32012 | 1.2.4.2.3 | External Ducting | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 8 | 24 | 8 | 500
Test Ducting | [10 empty] | Sum | 9924 | Base Labor
engineering design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2012 | B1.2.4.2.42012 | 1.2.4.2.4 | Test Ducting | [5 empty] | 2012 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
spec size, insulation, material | N/A | 1 | N/A | 0 | 0 | 0 | 24 | 24 | 24 | 0 | hours | 6408 | 1 | 6408 | B | PT | BPT2012 | B1.2.4.2.42012 | 1.2.4.2.4 | Test Ducting | [5 empty] | 2012 | 0 | 24 | 24 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
production ducting procure | N/A | 200 | ft | 10 | 2000 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 2000 | B | PT | BPT2012 | B1.2.4.2.42012 | 1.2.4.2.4 | Test Ducting | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
installation | N/A | 1 | N/A | 20 | 20 | 16 | 60 | 20 | 8 | 0 | hours | 10236 | 1 | 10256 | B | PT | BPT2012 | B1.2.4.2.42012 | 1.2.4.2.4 | Test Ducting | [5 empty] | 2012 | 16 | 60 | 20 | 8 | 0 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 500 | 500 | 16 | 60 | 20 | 8 | 0 | hours | 10236 | 1 | 10736 | C | PT | CPT2012 | C1.2.4.2.42012 | 1.2.4.2.4 | Test Ducting | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 60 | 20 | 8 | 0 | 500
[11 empty] | Sum | 22644 | Base Labor
Cooling Services Subtotal | [11 empty] | 82355.52 | Base Labor | [13 empty] | 81 | 2274.6 | 1143 | 509.7 | 713.1 |  | 51640 | 337399.252 |  | 53865.14 | 52 | 256 | 228 | 136.6 | 225.2 |  | 7700
Rack Equipment
RDO Crate Prototype
Crate design | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 80 | hours | 6000 | 1 | 6000 | B | PT | BPT2011 | B1.2.4.3.12011 | 1.2.4.3.1 | RDO Crate Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 80 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
prototype construction | N/A | 1 | N/A | 3000 | 3000 | 40 | 60 | 40 | 16 | 40 | hours | 14460 | 1 | 17460 | B | PT | BPT2011 | B1.2.4.3.12011 | 1.2.4.3.1 | RDO Crate Prototype | [5 empty] | 2011 | 40 | 60 | 40 | 16 | 40 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Testing and validation | N/A | 1 | N/A | 500 | 500 | 0 | 24 | 40 | 0 | 40 | hours | 2808 | 1 | 3308 | B | PT | BPT2011 | B1.2.4.3.12011 | 1.2.4.3.1 | RDO Crate Prototype | [5 empty] | 2011 | 0 | 24 | 40 | 0 | 40 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 16 | 40 | hours | 2400 | 1 | 2400 | C | PT | CPT2011 | C1.2.4.3.12011 | 1.2.4.3.1 | RDO Crate Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 16 | 40 | 0
RDO Crate Production | [10 empty] | Sum | 23268 | Sum
Crate Production | N/A | 4 | N/A | 3000 | 12000 | 24 | 12 | 0 | 0.1 | 0.2 | hours | 17772 | 4 | 65772 | B | PT | BPT2012 | B1.2.4.3.22012 | 1.2.4.3.2 | RDO Crate Production | [5 empty] | 2012 | 96 | 48 | 0 | 0.4 | 0.8 | 48000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
mount to pole tip or roll assembly | N/A | 4 | N/A | 800 | 3200 | 24 | 24 | 0 | 0 | 0 | hours | 5832 | 1 | 9032 | B | PT | BPT2012 | B1.2.4.3.22012 | 1.2.4.3.2 | RDO Crate Production | [5 empty] | 2012 | 24 | 24 | 0 | 0 | 0 | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
mount to pole tip or roll assembly - STAR cont | N/A | 1 | N/A | 0 | 0 | 24 | 24 | 0 | 24 | 0 | hours | 9432 | 1 | 9432 | B | PT | BPTSTAR | B1.2.4.3.2STAR | 1.2.4.3.2 | RDO Crate Production | [5 empty] | STAR | 24 | 24 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 0 | B | PT | BPT2011 | B1.2.4.3.22011 | 1.2.4.3.2 | RDO Crate Production | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Power Supplies | [10 empty] | Sum | 33036 | Sum
Power supply specify | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 32 | 16 | 32 | hours | 1944 | 1 | 1944 | B | PD | BPD2010 | B1.2.4.3.32010 | 1.2.4.3.3 | Power Supplies | [5 empty] | 2010 | 0 | 0 | 32 | 16 | 32 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
procure 1st piece | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 8 | 4 | 8 | hours | 486 | 1 | 1986 | B | PD | BPD2010 | B1.2.4.3.32010 | 1.2.4.3.3 | Power Supplies | [5 empty] | 2010 | 0 | 0 | 8 | 4 | 8 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
test and validate | N/A | 1 | N/A | 400 | 400 | 0 | 8 | 16 | 8 | 16 | hours | 1730.16 | 1 | 2130.16 | B | PD | BPD2010 | B1.2.4.3.32010 | 1.2.4.3.3 | Power Supplies | [5 empty] | 2010 | 0 | 8 | 16 | 8 | 16 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
power supply production purchase | N/A | 3 | N/A | 1500 | 4500 | 0 | 0 | 8 | 0 | 8 | hours | 0 | 1 | 4500 | B | PD | BPD2010 | B1.2.4.3.32010 | 1.2.4.3.3 | Power Supplies | [5 empty] | 2010 | 0 | 0 | 8 | 0 | 8 | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
test and validate | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 8 | 8 | 16 | hours | 2916 | 3 | 2916 | C | PD | CPD2011 | C1.2.4.3.32011 | 1.2.4.3.3 | Power Supplies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 24 | 24 | 48 | 0
contingency | N/A | 1 | N/A | 1500 | 1500 | 0 | 4 | 16 | 8 | 16 | hours | 1351.08 | 1 | 2851.08 | C | PD | CPD2011 | C1.2.4.3.32011 | 1.2.4.3.3 | Power Supplies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 16 | 8 | 16 | 1500
Cooling Plant | [10 empty] | Sum | 4160.16 | Sum
heat exchanger procure | N/A | 1 | N/A | 10000 | 10000 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 11944 | B | PD | BPD2010 | B1.2.4.3.42010 | 1.2.4.3.4 | Cooling Plant | [5 empty] | 2010 | 0 | 0 | 0 | 16 | 0 | 10000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
blower plant procure | N/A | 1 | N/A | 20000 | 20000 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 21944 | B | PD | BPD2010 | B1.2.4.3.42010 | 1.2.4.3.4 | Cooling Plant | [5 empty] | 2010 | 0 | 0 | 0 | 16 | 0 | 20000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
HEPA filter procure procure | N/A | 1 | N/A | 5000 | 5000 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 6944 | B | PD | BPD2010 | B1.2.4.3.42010 | 1.2.4.3.4 | Cooling Plant | [5 empty] | 2010 | 0 | 0 | 0 | 16 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
integration onto STAR platform | N/A | 1 | N/A | 4000 | 4000 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 13720 | B | PD | BPDSTAR | B1.2.4.3.4STAR | 1.2.4.3.4 | Cooling Plant | [5 empty] | STAR | 0 | 0 | 0 | 80 | 0 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Control / monitor and interlock system | N/A | 1 | N/A | 2000 | 2000 | 0 | 40 | 120 | 32 | 0 | hours | 7678.8 | 1 | 9678.8 | B | PD | BPD2011 | B1.2.4.3.42011 | 1.2.4.3.4 | Cooling Plant | [5 empty] | 2011 | 0 | 40 | 120 | 32 | 0 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Control / monitor and interlock system cont | N/A | 1 | N/A | 2000 | 2000 | 0 | 40 | 120 | 32 | 0 | hours | 7678.8 | 1 | 9678.8 | C | PD | CPD2011 | C1.2.4.3.42011 | 1.2.4.3.4 | Cooling Plant | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 120 | 32 | 0 | 2000
installation at STAR | N/A | 1 | N/A | 4000 | 4000 | 16 | 80 | 40 | 40 | 16 | hours | 14074.56 | 1 | 18074.56 | B | PD | BPDSTAR | B1.2.4.3.4STAR | 1.2.4.3.4 | Cooling Plant | [5 empty] | STAR | 16 | 80 | 40 | 40 | 16 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 10000 | 10000 | 8 | 40 | 40 | 80 | 8 | hours | 14327.28 | 1 | 24327.28 | C | PD | CPD2012 | C1.2.4.3.42012 | 1.2.4.3.4 | Cooling Plant | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8 | 40 | 40 | 80 | 8 | 10000
Test RDO | [10 empty] | Sum | 37305.36 | Sum
control/config PC | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 8 | 8 | 8 | hours | 972 | 1 | 2472 | B | PD | BPD2013 | B1.2.4.3.52013 | 1.2.4.3.5 | Test RDO | [5 empty] | 2013 | 0 | 0 | 8 | 8 | 8 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
control/config cables | N/A | 1 | N/A | 500 | 500 | 0 | 0 | 8 | 8 | 8 | hours | 972 | 1 | 1472 | B | PD | BPD2013 | B1.2.4.3.52013 | 1.2.4.3.5 | Test RDO | [5 empty] | 2013 | 0 | 0 | 8 | 8 | 8 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
nominal system configuration | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 8 | 8 | 8 | hours | 972 | 1 | 972 | B | PD | BPD2013 | B1.2.4.3.52013 | 1.2.4.3.5 | Test RDO | [5 empty] | 2013 | 0 | 0 | 8 | 8 | 8 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 2000 | 2000 | 0 | 0 | 16 | 8 | 16 | hours | 972 | 1 | 2972 | C | PD | CPD2013 | C1.2.4.3.52013 | 1.2.4.3.5 | Test RDO | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 16 | 8 | 16 | 2000
Test Power Supplies | [10 empty] | Sum | 2916 | Sum
power supply production purchase | N/A | 3 | N/A | 1500 | 4500 | 0 | 0 | 16 | 8 | 16 | hours | 972 | 1 | 5472 | B | PD | BPD2011 | B1.2.4.3.62011 | 1.2.4.3.6 | Test Power Supplies | [5 empty] | 2011 | 0 | 0 | 16 | 8 | 16 | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
test and validate | N/A | 1 | N/A | 0 | 0 | 0 | 8 | 16 | 8 | 16 | hours | 1730.16 | 1 | 1730.16 | B | PD | BPD2011 | B1.2.4.3.62011 | 1.2.4.3.6 | Test Power Supplies | [5 empty] | 2011 | 0 | 8 | 16 | 8 | 16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 0 | 0 | 0 | 4 | 16 | 4 | 16 | hours | 865.08 | 1 | 865.08 | C | PD | CPD2011 | C1.2.4.3.62011 | 1.2.4.3.6 | Test Power Supplies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 16 | 4 | 16 | 0
Test Cooling Plant | [10 empty] | Sum | 2702.16 | Sum
blower plant procure (LBL has) | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 16 | hours | 0 | 1 | 0 | B | PT | BPT2011 | B1.2.4.3.72011 | 1.2.4.3.7 | Test Cooling Plant | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 16 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ship to BNL | N/A | 1 | N/A | 1500 | 1500 | 0 | 16 | 0 | 8 | 0 | hours | 3072 | 1 | 4572 | B | PT | BPT2012 | B1.2.4.3.72012 | 1.2.4.3.7 | Test Cooling Plant | [5 empty] | 2012 | 0 | 16 | 0 | 8 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
HEPA filter procure | N/A | 1 | N/A | 5000 | 5000 | 0 | 0 | 0 | 8 | 0 | hours | 1200 | 1 | 6200 | B | PT | BPT2012 | B1.2.4.3.72012 | 1.2.4.3.7 | Test Cooling Plant | [5 empty] | 2012 | 0 | 0 | 0 | 8 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
integration into clean area tent | N/A | 1 | N/A | 4000 | 4000 | 0 | 120 | 0 | 80 | 0 | hours | 26040 | 1 | 30040 | B | PT | BPTSTAR | B1.2.4.3.7STAR | 1.2.4.3.7 | Test Cooling Plant | [5 empty] | STAR | 0 | 120 | 0 | 80 | 0 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Control / monitor and interlock system (as above) | N/A | 1 | N/A | 2000 | 2000 | 0 | 40 | 16 | 8 | 8 | hours | 5880 | 1 | 7880 | B | PT | BPT2012 | B1.2.4.3.72012 | 1.2.4.3.7 | Test Cooling Plant | [5 empty] | 2012 | 0 | 40 | 16 | 8 | 8 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
contingency | N/A | 1 | N/A | 5000 | 5000 | 9 | 40 | 40 | 40 | 40 | hours | 11814 | 1 | 16814 | C | PT | CPT2012 | C1.2.4.3.72012 | 1.2.4.3.7 | Test Cooling Plant | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 9 | 40 | 40 | 40 | 40 | 5000
Level Subtotal | [11 empty] | 139579.68 | Base Labor | [13 empty] | 200 | 492 | 376 | 452.4 | 320.8 |  | 125100 | 247105.44 |  | 60123.58 | 17 | 128 | 272 | 212 | 184 |  | 20500
[11 empty] | Sum | 36192 | Sum
[25 empty] | 0 |  | 281 | 2202.6 | 1179 | 887.9 | 822.9 |  | 267550 |  |  |  | 61 | 336 | 436 | 328.6 | 337.2 |  | 62400
[27 empty] | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) |  | M&S Cost |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) |  | M&S Cost
[26 empty] | Checksum | #REF! | #REF! | #REF! | #REF! | #REF! |  | 267550 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | 62400 | Checksum
[32 empty] | Cost With Contingency | #REF! | 667383.792 |  | Contributed Labor Excluded…
Description | WBS | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009
Infrastructure | 1.2.4 | <-- Copy Down from this Cell both columns A and B to update WBS list | [11 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | BASE | [9 empty] | CONTINGENCY
Cables | 1.2.4.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Labor | Tech Labor | PostDoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
Internal Cables (Engineering) | 1.2.4.1.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
Internal Cables (Production) | 1.2.4.1.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2010 | 5 | 73 | 80 | 106.5 | 157.5 | 43450 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
External Cables | 1.2.4.1.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2011 | 40 | 142 | 253 | 112 | 224 | 22000 |  |  |  | 2011 | 8 | 56 | 184 | 92 | 128 | 4000
Type 1 (Bulkhead to RDO Crate) | 1.2.4.1.3.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 192 | 1053.2 | 434 | 335.6 | 298.4 | 111660 |  |  |  | 2012 | 45 | 212 | 172 | 192 | 136 | 42300
Type 2 (RDO to PS) | 1.2.4.1.3.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2013 | 4 | 710.4 | 372 | 53.8 | 111 | 35820 |  |  |  | 2013 | 8 | 68 | 80 | 28.6 | 65.2 | 9900
[26 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
Data/Control Fibers | 1.2.4.1.3.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
Test Cables (External) | 1.2.4.1.4 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | STAR | 40 | 224 | 40 | 280 | 32 | 12000 |  |  |  | STAR | 0 | 0 | 0 | 16 | 8 | 0
Type 1 (Bulkhead to RDO Crate) | 1.2.4.1.4.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Project Estimated Cost | [9 empty] | Project Estimated Contingency
Type 2 (RDO to PS) | 1.2.4.1.4.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
Data/Control Fibers | 1.2.4.1.4.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cooling Services | 1.2.4.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2010 | 630 | 8363.16 | 0 | 13809 | 0 | 43450 | 66252.16 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Internal Ducting (Engineering) | 1.2.4.2.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2011 | 5040 | 15546.96 | 0 | 15432 | 0 | 22000 | 58018.96 |  |  | 2011 | 1008 | 5484.96 | 0 | 11862 | 0 | 4000 | 22354.96
Internal Ducting (Production) | 1.2.4.2.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 23425.92 | 107903.484 | 0 | 46486.8 | 0 | 111660 | 289476.204 |  |  | 2012 | 5191.2 | 22669.92 | 0 | 12000 | 0 | 42300 | 82161.12
[26 empty] | 2013 | 408.24 | 67324.608 | 0 | 6536.7 | 0 | 35820 | 110089.548 |  |  | 2013 | 816.48 | 6444.36 | 0 | 8262 | 0 | 9900 | 25422.84
External Ducting | 1.2.4.2.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 13608 | 0 | 0 | 13608
Test Ducting | 1.2.4.2.4 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [8 empty] | Base Cost | 523836.872 | [8 empty] | Contingency | 143546.92
Rack Equipment | 1.2.4.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [18 empty] | Percent | 27.4%
RDO Crate Prototype | 1.2.4.3.1 | [31 empty] | 523836.872 | checksum | [8 empty] | 143546.92 | checksum
RDO Crate Production | 1.2.4.3.2
Power Supplies | 1.2.4.3.3 | IF need to copy below this line to contain WBS, need to update Data Validation for cells in column "U" (WBS) AND 'Look Up' vectors for Column "V" (Descriptor) | [24 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
Cooling Plant | 1.2.4.3.4 | [25 empty] | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
Test RDO | 1.2.4.3.5 | [15 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
Test Power Supplies | 1.2.4.3.6 | [15 empty] | BPT | [8 empty] | 2010 | 5 | 65 | 16 | 30.5 | 93.5 | 2050 |  |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0
Test Cooling Plant | 1.2.4.3.7 | [15 empty] | BPT | [8 empty] | 2011 | 40 | 94 | 101 | 64 | 192 | 15500 |  |  | CPT | 2011 | 8 | 8 | 8 | 24 | 48 | 500
[17 empty] | BPT | [8 empty] | 2012 | 160 | 364 | 92 | 200.4 | 112.8 | 64720 |  |  | CPT | 2012 | 25 | 116 | 84 | 80 | 64 | 27600
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2013 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | STAR | 24 | 144 | 0 | 160 | 16 | 4000 |  |  | CPT | STAR | 0 | 0 | 0 | 16 | 8 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
[17 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2010 | 630 | 7605 | 0 | 4575 | 0 | 2050 | 14860 |  | CPT | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2011 | 5040 | 10998 | 0 | 9600 | 0 | 15500 | 41138 |  | CPT | 2011 | 1008 | 936 | 0 | 3600 | 0 | 500 | 6044
[17 empty] | BPT | [8 empty] | 2012 | 20160 | 42588 | 0 | 30060 | 0 | 64720 | 157528 |  | CPT | 2012 | 3150 | 13572 | 0 | 12000 | 0 | 27600 | 56322
[17 empty] | BPT | [8 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 213526 | [8 empty] | Contingency | 62366
[42 empty] | Percent | 29.21%
[27 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[27 empty] | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost |  |  |  |  | Shop Time | MT Time | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 0 | 8 | 64 | 76 | 64 | 41400 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 0 | 48 | 152 | 48 | 32 | 6500 |  |  | CPD | 2011 | 0 | 48 | 176 | 68 | 80 | 3500
[17 empty] | BPD | [8 empty] | 2012 | 32 | 689.2 | 342 | 135.2 | 185.6 | 46940 |  |  | CPD | 2012 | 20 | 96 | 88 | 112 | 72 | 14700
[17 empty] | BPD | [8 empty] | 2013 | 4 | 710.4 | 372 | 53.8 | 111 | 35820 |  |  | CPD | 2013 | 8 | 68 | 80 | 28.6 | 65.2 | 9900
[17 empty] | BPD | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | STAR | 16 | 80 | 40 | 120 | 16 | 8000 |  |  | CPD | STAR | 0 | 0 | 0 | 0 | 0 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | Postdoc (cont) | Engineering | Engineer (cont) | M&S Cost | Totals
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 0 | 758.16 | 0 | 9234 | 0 | 41400 | 51392.16 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 0 | 4548.96 | 0 | 5832 | 0 | 6500 | 16880.96 |  | CPD | 2011 | 0 | 4548.96 | 0 | 8262 | 0 | 3500 | 16310.96
[17 empty] | BPD | [8 empty] | 2012 | 3265.92 | 65315.484 | 0 | 16426.8 | 0 | 46940 | 131948.204 |  | CPD | 2012 | 2041.2 | 9097.92 | 0 | 0 | 0 | 14700 | 25839.12
[17 empty] | BPD | [8 empty] | 2013 | 408.24 | 67324.608 | 0 | 6536.7 | 0 | 35820 | 110089.548 |  |  | 2013 | 816.48 | 6444.36 | 0 | 8262 | 0 | 9900 | 25422.84
[17 empty] | BPD | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2014 | 0 | 0 | 0 | 13608 | 0 | 0 | 13608
[32 empty] | Base Cost | 310310.872 | [8 empty] | Contingency | 81180.92
[42 empty] | Percent | 26.16%
Note on A123: Eric C. Anderssen: engineering done in pixel heating test 1.2.1…

## Rates
Values below used only for reference--not linked to data in sheet estimate…
| Construction | R&D |  | English | Metric | Quoted |  | Metric
Shop | 102.06 | 126 | Material | lb/in^3 | g/cc | Cost/Unit | Unit | Cost/Unit | Unit
CMM | 0 | 0 | Aluminum | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
M_Tech | 94.77 | 117 | MIC-6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
Engineer | 121.5 | 150 | 6061-T6 | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
DES | 0 | 0 | 7075-T6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
|  |  | Titanium | 0.198 | 5.4855 | 15 | $/lb | 0.030992 | $/g
Construction Rate does not have full Burden--currently ~81% (below) of Full Burden at LBNL (R&D Rate) |  |  | 6Al4V | 0.198 | 5.4855 | 20 | $/lb | 0.041322 | $/g
|  |  | Steel | 0.298 | 8.256 | 3 | $/lb | 0.0061983 | $/g
|  |  | 304SS | 0.298 | 8.256 | 15 | $/lb | 0.030992 | $/g
|  |  | Carbon Fiber | 0.065 | 1.8008 | 100 | $/lb | 0.20661 | $/g
Differential | 81% |  | M55J-UDT | 0.065 | 1.8008 | 800 | $/lb | 1.6529 | $/g
Change This to change burden rate… |  |  | CN60-PW | 0.065 | 1.8008 | 500 | $/lb | 1.0331 | $/g
|  |  | YSH80A-UDT | 0.065 | 1.8008 | 1200 | $/lb | 2.4793 | $/g
|  |  | Adhesive | 0.055 | 1.5238 | 400 | $/qt | 0.42283 | $/cc
|  |  | EA9396 | 0.055 | 1.5238 | 350 | $/qt | 0.36998 | $/cc
|  |  | EA9394 | 0.075 | 2.0779 | 450 | $/qt | 0.47569 | $/cc
|  |  | CF HoneyComb | 0.0017361 | 0.048099 | 600 | $/bdft | 0.25424 | $/cc
|  |  | Al HoneyComb | 0.0017361 | 0.048099 | 75 | $/bdft | 0.03178 | $/cc
|  |  | Nomex HC | 0.0023148 | 0.064131 | 100 | $/bdft | 0.042373 | $/cc
|  |  | PEEK | 0.055 | 1.5238 | 400 | $/lb | 0.82645 | $/g
|  |  | CF PEEK | 0.055 | 1.5238 | 600 | $/lb | 1.2397 | $/g

## Material Estimates
Material Estimates per component |  |  | Values used to estimate Size/Cost of Batch Orders--Does not report to Cost Summary
Item | Material | Descriptor | Quantity | CPT (microns) | Density (g/cc) | Finished Form | % Waste | Length (cm) | Diameter/Width (cm) | Thickness (cm) | Volume (cc) | Mass (g) | Pre-Preg Area (m^2) | Cost Per Unit | Choose Unit | Cost | Prototype Mass | Prototype Area | Prototype Composites
Material Volumes | [19 empty] | /cc | Bulk | 1
D-Tube | [19 empty] | /g | Plate | 2
Tooling | [19 empty] | /m^2 | Round | 3
Mandrel | Steel | Pipe | 1 | n/a | 8.3 | Shell | 0% | 60 | 20 | 1.5 | 5654.8668 | 46935.3942 | #VALUE! | 0.006 | /g | 281.6124 | 0 | 0 | 0 |  | Shell | 4
Mandrel End Plates | Steel | Plate | 1 | n/a | 8.3 | Plate | 0% | 60 | 25 | 3 | 4500 | 37350 | #VALUE! | 0.006 | /g | 224.1 | 0 | 0 | 0
D-Tube Bond Tool
Tooling
Support Beam Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 100 | 30 | 3 | 9000 | 24300 | #VALUE! | 0.017 | /g | 413.1 | 0 | 0 | 0
Support Beam Machining Tool | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 0% | 30 | 15 | 5 | 4500 | 12150 | #VALUE! | 0.017 | /g | 206.55 | 0 | 0 | 0
Components | [11 empty] | 80.2863
Thick Laminate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Plate | 30% | 80 | 2.5 | 0.8 | 1040 | 1872 | 3.1515 | 1.033 | /g | 1933.776 | 0 | 0 | 0
Thick Laminate Test | CN60 Cloth | Test | 2 | 330 | 1.8 | Plate | 50% | 20 | 3 | 0.8 | 144 | 259.2 | 0.43636 | 1.033 | /g | 267.7536 | 259.2 | 0.43636 | 267.7536
Insertion Test Bed
Support Components
Item Bars | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 250 | 7.5 | 7.5 | 73125 | 197437.5 | #VALUE! | 0.017 | /g | 3356.4375 | 0 | 0 | 0
Station Plates | Aluminum | Plate | 3 | n/a | 2.7 | Plate | 30% | 50 | 50 | 5 | 48750 | 131625 | #VALUE! | 0.017 | /g | 2237.625 | 0 | 0 | 0
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Iteration | [11 empty] | 840.7764 |  |  |  | 6489.1125
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Prototype | [11 empty] | 115.9692 |  |  |  | 895.05
Cart Rail Rider prototype | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Low Mass Cart | [11 empty] | 154.6256 |  |  |  | 1193.4
Cart Rail Rider | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Tooling | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 60 | 30 | 5 | 11700 | 31590 | 35.4545 | 0.017 | /g | 537.03 | 0 | 0 | 0