## WBS in Estimate
This table drives values in a lookup table in the Pre- and Production Sheet, columns U and V. It is 'copied' into that sheet at the bottom, see notes there to understand how to modify this. 'Inserting' rows does not work, only adding, so must modify whole table--5 rows are available for additions...
WBS | Description
1.2.1 | Pixel Mechanics
1.2.1.1 | Module Support (Sector)
1.2.1.1.1 | Sector Mechanical Prototypes
1.2.1.1.2 | Production Sectors
1.2.1.2 | D-Tube and Kinematic Mounts
1.2.1.2.1 | Prototype D-Tube
1.2.1.2.2 | Prototype Kinematic Mounts
1.2.1.2.3 | Production D-Tube and Kinematic Mounts
1.2.1.3 | Insertion Mechanism and Internal Service Supports
1.2.1.3.1 | Thermal Prototype
1.2.1.3.2 | Insertion Test Bed
1.2.1.3.3 | Prototype Insertion Mechanism
1.2.1.3.4 | Production Insertion Mechanism
1.2.1.3.5 | Prototype Patch Panel Bulkhead
1.2.1.3.6 | Production Patch Panel Bulkhead
1.2.3 | Detector Assembly
1.2.3.1 | Sector Assembly
1.2.3.1.1 | Mechanical Sector Assemblies
1.2.3.1.2 | Electrical Sector Assemblies
1.2.3.2 | D-Tube Assembly and Survey Tool
1.2.3.3 | Sector Mount And Survey
1.2.3.4 | Final Assembly
1.2.3.4.1 | Detector Half Enclosure
1.2.3.4.2 | Half Detector Assembly
1.2.3.5 | System Test
1.2.5 | Installation
1.2.5.1 | Pixel Installation In-Situ
1.2.5.1.1 | Work Platform
1.2.5.1.2 | Detector Installation
1.2.5.1.3 | Service Termination
1.2.5.2 | Pixel Auxiliary Acess
1.2.5.2.1 | Work Platform
1.2.5.2.2 | Detector Installation
1.2.5.2.3 | Service Termination

## WBS Summary
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
WBS | Description | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont |  | Hours
1.2.1 | Pixel Mechanics | 40 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26702.5 | 0 | 1.2.1 | 8458.75 |  | 183
1.2.1.1 | Module Support (Sector) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.1 |  | 1438.75 | 0
1.2.1.1.1 | Sector Mechanical Prototypes | 54.75 | 109 | 32 | 44 | 0 | 0 | 100 | 128 | 0 | 0 | 1500 | 2544 | 1.2.1.1.1 |  |  | 467.75
1.2.1.1.2 | Production Sectors | 387.5 | 77.5 | 224 | 14 | 0 | 0 | 159 | 109 | 0 | 0 | 25552.5 | 21632.5 | 1.2.1.1.2 |  |  | 971
1.2.1.2 | D-Tube and Kinematic Mounts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 |  | 2575 | 0
1.2.1.2.1 | Prototype D-Tube | 166 | 52 | 382 | 270 | 4 | 0 | 409 | 179 | 0 | 0 | 16632.5 | 11592.5 | 1.2.1.2.1 |  |  | 1462
1.2.1.2.2 | Prototype Kinematic Mounts | 132 | 48 | 0 | 0 | 0 | 0 | 230 | 12 | 0 | 0 | 240 | 48 | 1.2.1.2.2 |  |  | 422
1.2.1.2.3 | Production D-Tube and Kinematic Mounts | 80 | 112 | 182 | 128 | 0 | 0 | 87 | 102 | 0 | 0 | 13034.5 | 1796 | 1.2.1.2.3 |  |  | 691
1.2.1.3 | Insertion Mechanism and Internal Service Supports | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3 |  | 4262 | 0
1.2.1.3.1 | Thermal Prototype | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 |  |  | 80
1.2.1.3.2 | Insertion Test Bed | 104 | 60 | 648 | 80 | 80 | 16 | 838 | 60 | 0 | 0 | 19400 | 960 | 1.2.1.3.2 |  |  | 1886
1.2.1.3.3 | Prototype Insertion Mechanism | 120 | 0 | 192 | 0 | 0 | 0 | 476 | 0 | 0 | 0 | 2300 | 0 | 1.2.1.3.3 |  |  | 788
1.2.1.3.4 | Production Insertion Mechanism | 64 | 96 | 112 | 112 | 0 | 0 | 72 | 112 | 0 | 0 | 1160 | 1160 | 1.2.1.3.4 |  |  | 568
1.2.1.3.5 | Prototype Patch Panel Bulkhead | 56 | 0 | 116 | 0 | 0 | 0 | 152 | 0 | 8 | 0 | 3280 | 0 | 1.2.1.3.5 |  |  | 332
1.2.1.3.6 | Production Patch Panel Bulkhead | 96 | 48 | 248 | 120 | 0 | 0 | 72 | 16 | 8 | 0 | 3280 | 640 | 1.2.1.3.6 |  |  | 608
1.2.3 | Detector Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3 | 6056.75 |  | 0
1.2.3.1 | Sector Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.1 |  | 2406.75 | 0
1.2.3.1.1 | Mechanical Sector Assemblies | 352 | 516.75 | 236 | 148 | 56 | 48 | 264 | 296 | 0 | 0 | 2560 | 4344 | 1.2.3.1.1 |  |  | 1916.75
1.2.3.1.2 | Electrical Sector Assemblies | 0 | 0 | 300 | 120 | 0 | 0 | 50 | 20 | 0 | 0 | 0 | 0 | 1.2.3.1.2 |  |  | 490
1.2.3.2 | D-Tube Assembly and Survey Tool | 0 | 0 | 256 | 48 | 96 | 16 | 120 | 8 | 0 | 0 | 0 | 0 | 1.2.3.2 |  | 544 | 544
1.2.3.3 | Sector Mount And Survey | 0 | 40 | 226 | 102 | 384 | 76 | 388 | 86 | 0 | 0 | 240 | 240 | 1.2.3.3 |  | 1302 | 1302
1.2.3.4 | Final Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.4 |  | 1804 | 0
1.2.3.4.1 | Detector Half Enclosure | 64 | 64 | 256 | 128 | 0 | 0 | 96 | 48 | 0 | 0 | 19200 | 9600 | 1.2.3.4.1 |  |  | 656
1.2.3.4.2 | Half Detector Assembly | 40 | 0 | 648 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 2200 | 0 | 1.2.3.4.2 |  |  | 1148
1.2.3.5 | System Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3.5 |  |  | 0
1.2.5 | Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5 | 1904 |  | 0
1.2.5.1 | Pixel Installation In-Situ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.1 |  | 1904 | 0
1.2.5.1.1 | Work Platform | 40 | 0 | 120 | 0 | 0 | 0 | 384 | 280 | 0 | 0 | 18000 | 0 | 1.2.5.1.1 |  |  | 824
1.2.5.1.2 | Detector Installation | 40 | 40 | 220 | 60 | 0 | 0 | 216 | 56 | 0 | 0 | 2800 | 2800 | 1.2.5.1.2 |  |  | 632
1.2.5.1.3 | Service Termination | 96 | 48 | 128 | 48 | 0 | 0 | 112 | 16 | 0 | 0 | 1280 | 640 | 1.2.5.1.3 |  |  | 448
1.2.5.2 | Pixel Auxiliary Acess | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2 |  | 0 | 0
1.2.5.2.1 | Work Platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.1 |  |  | 0
1.2.5.2.2 | Detector Installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 |  |  | 0
1.2.5.2.3 | Service Termination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 |  |  | 0
| Hours | 1932.25 | 1311.25 | 4749 | 1422 | 620 | 156 | 4685 | 1528 | 16 | 0 | 159362 | 57997
| FTE | 1.1234 | 0.76235 | 2.761 | 0.82674 | 0.36047 | 0.090698 | 2.7238 | 0.88837 | 0.0093023 | 0
| Cost Approx | 197205.435 | 133826.175 | 450062.73 | 134762.94 | 36.7891 | 15921.36 | 569227.5 | 185652 | 1620 | 0

## WBS Summary by Year
2009
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cost Approx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 126 | 0 | 270 | 32 | 4 | 0 | 357 | 0 | 0 | 0 | 14872.5 | 105
| 1.2.1.2.2 | 36 | 48 | 0 | 0 | 0 | 0 | 224 | 12 | 0 | 0 | 144 | 48
| 1.2.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 56 | 0 | 368 | 0 | 48 | 0 | 198 | 0 | 0 | 0 | 14800 | 0
| 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 16 | 0 | 0 | 0 | 56 | 0 | 88 | 0 | 0 | 0 | 240 | 0
| 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 234 | 48 | 721 | 32 | 108 | 0 | 1115 | 12 | 0 | 0 | 31556.5 | 153
| FTE | 0.13605 | 0.027907 | 0.41919 | 0.018605 | 0.062791 | 0 | 0.64826 | 0.0069767 | 0 | 0
| Cost Approx | 23882.04 | 4898.88 | 68329.17 | 3032.64 | 6.4084 | 0 | 135472.5 | 1458 | 0 | 0
2011
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4207.5 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.2 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 20652.5
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 40 | 52 | 16 | 22 | 0 | 0 | 36 | 85 | 0 | 0 | 1760 | 5172.5
| 1.2.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 48 | 60 | 280 | 80 | 32 | 16 | 640 | 60 | 0 | 0 | 4600 | 960
| 1.2.1.3.3 | 56 | 0 | 80 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 1140 | 0
| 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 16 | 103.75 | 88 | 8 | 0 | 48 | 44 | 164 | 0 | 0 | 720 | 2160
| 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 160 | 0 | 64 | 0 | 88 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 64 | 0 | 128 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 9600 | 0
| 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 224 | 215.75 | 787 | 124 | 96 | 64 | 1140 | 318 | 0 | 0 | 22027.5 | 28945
| FTE | 0.13023 | 0.12544 | 0.45756 | 0.072093 | 0.055814 | 0.037209 | 0.66279 | 0.18488 | 0 | 0
| Cost Approx | 22861.44 | 22019.445 | 74583.99 | 11751.48 | 5.6964 | 6531.84 | 138510 | 38637 | 0 | 0
2012
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 8 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6155 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 38.75 | 93 | 0 | 42 | 0 | 0 | 60 | 88 | 0 | 0 | 1340 | 584
| 1.2.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 210
| 1.2.1.2.2 | 96 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 96 | 0
| 1.2.1.2.3 | 32 | 0 | 118 | 48 | 0 | 0 | 59 | 16 | 0 | 0 | 12632.5 | 210
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.3 | 64 | 0 | 112 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 1160 | 0
| 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.5 | 56 | 0 | 116 | 0 | 0 | 0 | 104 | 0 | 8 | 0 | 3280 | 0
| 1.2.1.3.6 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 2000 | 0
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 320 | 93 | 148 | 84 | 0 | 0 | 132 | 62 | 0 | 0 | 1600 | 576
| 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 40 | 80 | 78 | 124 | 60 | 178 | 62 | 0 | 0 | 240 | 240
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.2 | 40 | 0 | 328 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 2200 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 40 | 0 | 80 | 0 | 0 | 0 | 224 | 160 | 0 | 0 | 18000 | 0
| 1.2.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 694.75 | 226 | 1021 | 356 | 124 | 60 | 1135 | 454 | 16 | 0 | 48703.5 | 1820
| FTE | 0.40392 | 0.1314 | 0.5936 | 0.20698 | 0.072093 | 0.034884 | 0.65988 | 0.26395 | 0.0093023 | 0
| Cost Approx | 70906.185 | 23065.56 | 96760.17 | 33738.12 | 7.3578 | 6123.6 | 137902.5 | 55161 | 1620 | 0
2013
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 16 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7420 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 16 | 16 | 2 | 2 | 0 | 0 | 0 | 40 | 0 | 0 | 160 | 1960
| 1.2.1.1.2 | 387.5 | 77.5 | 224 | 0 | 0 | 0 | 159 | 100 | 0 | 0 | 25552.5 | 980
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 0 | 0 | 96 | 112 | 0 | 0 | 16 | 28 | 0 | 0 | 0 | 6105
| 1.2.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.3 | 48 | 112 | 64 | 80 | 0 | 0 | 28 | 86 | 0 | 0 | 402 | 1586
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.4 | 64 | 96 | 112 | 112 | 0 | 0 | 72 | 112 | 0 | 0 | 1160 | 1160
| 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.6 | 96 | 48 | 240 | 120 | 0 | 0 | 32 | 16 | 0 | 0 | 1280 | 640
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 0 | 320 | 0 | 56 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 1608
| 1.2.3.1.2 | 0 | 0 | 300 | 120 | 0 | 0 | 50 | 20 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 96 | 48 | 32 | 16 | 32 | 8 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 0 | 126 | 24 | 220 | 16 | 190 | 24 | 0 | 0 | 0 | 0
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 0 | 64 | 128 | 128 | 0 | 0 | 48 | 48 | 0 | 0 | 9600 | 9600
| 1.2.3.4.2 | 0 | 0 | 160 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.2 | 40 | 0 | 100 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 2800 | 0
| 1.2.5.1.3 | 96 | 0 | 104 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 1280 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 763.5 | 733.5 | 1804 | 802 | 252 | 32 | 843 | 552 | 0 | 0 | 49654.5 | 23639
| FTE | 0.4439 | 0.42645 | 1.0488 | 0.46628 | 0.14651 | 0.018605 | 0.49012 | 0.32093 | 0 | 0
| Cost Approx | 77922.81 | 74861.01 | 170965.08 | 76005.54 | 14.953 | 3265.92 | 102424.5 | 67068 | 0 | 0
CONT
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cost Approx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STAR
|  | Shop |  | M Tech |  | CMM |  | Engineering |  | Design |  | M & S
|  | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont | Base | Cont
| 1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | 0 | 0 | 40 | 0 | 0 | 0 | 160 | 120 | 0 | 0 | 0 | 0
| 1.2.5.1.2 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3 | 0 | 0 | 16 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 136 | 0 | 0 | 0 | 304 | 120 | 0 | 0 | 0 | 0
| FTE | 0 | 0 | 0.07907 | 0 | 0 | 0 | 0.17674 | 0.069767 | 0 | 0
| Cost Approx | 0 | 0 | 12888.72 | 0 | 0 | 0 | 36936 | 14580 | 0 | 0

## SUMMARY
| BASE | [9 empty] | CONTINGENCY
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 234 | 721 | 108 | 1115 | 0 | 31556.5 |  |  |  | 2010 | 48 | 32 | 0 | 12 | 0 | 153
2011 | 224 | 787 | 96 | 1140 | 0 | 22027.5 |  |  |  | 2011 | 215.75 | 124 | 64 | 318 | 0 | 28945
2012 | 694.75 | 1021 | 124 | 1135 | 16 | 48703.5 |  |  |  | 2012 | 226 | 356 | 60 | 454 | 0 | 1820
2013 | 763.5 | 1804 | 252 | 843 | 0 | 49654.5 |  |  |  | 2013 | 733.5 | 802 | 32 | 552 | 0 | 23639
2014 | 16 | 280 | 40 | 148 | 0 | 7420 |  |  |  | 2014 | 88 | 108 | 0 | 72 | 0 | 3440
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 136 | 0 | 304 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 120 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Contingency
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals | Plan B | Delta |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals | Plan B | Delta | FY | VB0.9 | V0.9 | Delta
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009 | 0 | 0 | 0
2010 | 28526.4 | 82445.22 | 12267.36 | 164029.5 | 0 | 31556.5 | 318824.98 | 191132.98 | 127692 | 2010 | 6048 | 3744 | 0 | 1800 | 0 | 153 | 11745 | 11745 | 0 | 2010 | 202877.98 | 330569.98 | 127692
2011 | 25925.76 | 83164.77 | 10563.84 | 165300 | 0 | 22027.5 | 306981.87 | 549053.59 | -242071.72 | 2011 | 23838.885 | 13707.72 | 6914.88 | 42057 | 0 | 28945 | 115463.485 | 167034.945 | -51571.46 | 2011 | 716088.535 | 422445.355 | -293643.18
2012 | 71833.86 | 96804.63 | 12655.44 | 139612.5 | 1620 | 48703.5 | 371229.93 | 336395.935 | 34833.995 | 2012 | 23065.56 | 33738.12 | 6123.6 | 56301 | 0 | 1820 | 121048.28 | 129237.3 | -8189.02 | 2012 | 465633.235 | 492278.21 | 26644.975
2013 | 78305.85 | 171009.54 | 25719.12 | 102424.5 | 0 | 49654.5 | 427113.51 | 220237.745 | 206875.765 | 2013 | 75244.05 | 76050 | 3265.92 | 68208 | 0 | 23639 | 246406.97 | 218050.93 | 28356.04 | 2013 | 438288.675 | 673520.48 | 235231.805
2014 | 1632.96 | 26535.6 | 4082.4 | 17982 | 0 | 7420 | 57652.96 | 33291 | 24361.96 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 33291 | 57652.96 | 24361.96
[6 empty] | Base Cost | 1481803.25 | 1330111.25 | 151692 | [6 empty] | Contingency | 494663.735 | 526068.175 | -31404.44 | Total | 1856179.425 | 1976466.985 | 120287.56
[9 empty] | 151692 | [6 empty] | Percent | 33.38% |  | -31404.44
| Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 61
2010 | 194 | 635 | 52 | 1002 | 0 | 21134 |  |  |  | 2010 | 48 | 32 | 0 | 12 | 0 | 153 |  |  |  | 64
2011 | 128 | 386 | 32 | 940 | 0 | 7827.5 |  |  |  | 2011 | 76 | 88 | 16 | 120 | 0 | 1080 |  |  |  | 18
2012 | 38.75 | 2 | 0 | 60 | 0 | 2285 |  |  |  | 2012 | 0 | 0 | 0 | 40 | 0 | 8 |  |  |  | 46
2013 | 16 | 2 | 0 | 0 | 0 | 160 |  |  |  | 2013 | 16 | 2 | 0 | 40 | 0 | 160
2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 0 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 24444 | 74295 | 6552 | 150300 | 0 | 21134 | 276725 |  |  | 2010 | 6048 | 3744 | 0 | 1800 | 0 | 153 | 11745
2011 | 16128 | 45162 | 4032 | 141000 | 0 | 7827.5 | 214149.5 |  |  | 2011 | 9576 | 10296 | 2016 | 18000 | 0 | 1080 | 40968
2012 | 4882.5 | 234 | 0 | 9000 | 0 | 2285 | 16401.5 |  |  | 2012 | 0 | 0 | 0 | 6000 | 0 | 8 | 6008
2013 | 2016 | 234 | 0 | 0 | 0 | 160 | 2410 |  |  | 2013 | 2016 | 234 | 0 | 6000 | 0 | 160 | 8410
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 509686 | [8 empty] | Contingency | 67131
[16 empty] | Percent | 13.17%
| Production Base Cost | [9 empty] | Production Contingency Cost
| Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 40 | 86 | 56 | 113 | 0 | 10422.5 |  |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 96 | 401 | 64 | 200 | 0 | 14200 |  |  |  | 2011 | 139.75 | 36 | 48 | 198 | 0 | 27865
2012 | 656 | 1019 | 124 | 1075 | 16 | 46418.5 |  |  |  | 2012 | 226 | 356 | 60 | 414 | 0 | 1812
2013 | 747.5 | 1802 | 252 | 843 | 0 | 49494.5 |  |  |  | 2013 | 717.5 | 800 | 32 | 512 | 0 | 23479
2014 | 16 | 280 | 40 | 148 | 0 | 7420 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
STAR | 0 | 136 | 0 | 304 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 120 | 0 | 0
| Project Estimated Cost | [9 empty] | Project Estimated Cost
| Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | 4082.4 | 8150.22 | 5715.36 | 13729.5 | 0 | 10422.5 | 42099.98 |  |  | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | 9797.76 | 38002.77 | 6531.84 | 24300 | 0 | 14200 | 92832.37 |  |  | 2011 | 14262.885 | 3411.72 | 4898.88 | 24057 | 0 | 27865 | 74495.485
2012 | 66951.36 | 96570.63 | 12655.44 | 130612.5 | 1620 | 46418.5 | 354828.43 |  |  | 2012 | 23065.56 | 33738.12 | 6123.6 | 50301 | 0 | 1812 | 115040.28
2013 | 76289.85 | 170775.54 | 25719.12 | 102424.5 | 0 | 49494.5 | 424703.51 |  |  | 2013 | 73228.05 | 75816 | 3265.92 | 62208 | 0 | 23479 | 237996.97
2014 | 1632.96 | 26535.6 | 4082.4 | 17982 | 0 | 7420 | 57652.96 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Base Cost | 972117.25 | [8 empty] | Contingency | 427532.735
[16 empty] | Percent | 43.98%

## Pre- and Production
[17 empty] | (HIDE) |  |  |  | (HIDE AS REQUIRED)
Pixel Estimate (1.2.1 and 1.2.3) | [14 empty] | TRACKING | [11 empty] | BASE | [9 empty] | CONTINGENCY
Item | Material | Material Amt | Units | Material Cost/Unit | Material Cost | Shop Time | MT Time | CMM | Eng Time | Des Time | Units | Labor Cost Total (includes contingency) | # (line-item-zeroing) | Materials and Labor | Base or Contingency | Protot or Production | Sum Logic Code | Sum Logic Code | WBS | WBS Descriptor | PO/UC Number | Estimate | Spent To Date | Est Remaining | Overage | YEAR | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals |  |  |  | Shop Labor | Tech Labor | CMM | Engineering | Design | Materials Sub Totals | Materials Totals
Material Batches | [24 empty] | Underage(-)
Sector Laminates (Prototype) | M46J | 40 | m^2 | 400 | 16000 | 0 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 4 | N/A | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Laminates Contingency | M46J | 40 | m^2 | 400 | 16000 | 0 | 0 | 0 | 2 | 0 | hours | 243 | 1 | 16243 | C | PD | CPD2011 | C1.2.1.1.22011 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 16000
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | CPD2011 | C1.2.1.1.22011 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Order Contingency (+10% Areal) | N/A | 4 | N/A | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1600 | C | PD | CPD2011 | C1.2.1.1.22011 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1600
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | C | PD | CPD2011 | C1.2.1.1.22011 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 2 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | C | PD | CPD2011 | C1.2.1.1.22011 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 52.5
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | C | PD | CPD2011 | C1.2.1.1.22011 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 1500
Sector Laminates Production | M46J | 40 | m^2 | 400 | 16000 | 0 | 0 | 0 | 2 | 0 | hours | 243 | 1 | 16243 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 2 | 0 | 16000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 4 | N/A | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1600 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 2 | 0 | hours | 432.54 | 1 | 432.54 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 2 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
D-Tube Laminates | CN60 | 10 | m^2 | 600 | 6000 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 6972 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 8 | 0 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 1 | N/A | 600 | 600 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 600 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 189.54 | 1 | 189.54 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 2 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
D-Tube Laminates Contingency | CN60 | 10 | m^2 | 600 | 6000 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 6972 | C | PD | CPD2013 | C1.2.1.2.12013 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 8 | 0 | 6000
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1500
Order Contingency (+10% Areal) | N/A | 1 | N/A | 600 | 600 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 600 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 600
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 189.54 | 1 | 189.54 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 2 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 1 | 0 | 52.5
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4 | 0 | 4 | 0 | 1500
D-Tube Laminates Production | CN60 | 10 | m^2 | 600 | 6000 | 0 | 0 | 0 | 8 | 0 | hours | 972 | 1 | 6972 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 0 | 0 | 8 | 0 | 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Minimum Order Surcharge | N/A | 1 | N/A | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1500 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Order Contingency (+10% Areal) | N/A | 1 | N/A | 600 | 600 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 600 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Acceptance | N/A | 0 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 0 | hours | 189.54 | 1 | 189.54 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 2 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bleed Studies | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 1 | 0 | hours | 879.66 | 1 | 932.16 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 8 | 0 | 1 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Test | N/A | 1 | Order | 1500 | 1500 | 0 | 4 | 0 | 4 | 0 | hours | 865.08 | 1 | 2365.08 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 4 | 0 | 4 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Pre-Production | Hysol 9396 | 1 | Order | 500 | 500 | 0 | 1 | 0 | 0 | 0 | hours | 351 | 3 | 1851 | B | PT | BPT2010 | B1.2.12010 | 1.2.1 | Pixel Mechanics | [5 empty] | 2010 | 0 | 3 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Production | Hysol 9396 | 2 | Order | 500 | 1000 | 0 | 1 | 0 | 0 | 0 | hours | 284.31 | 3 | 3284.31 | B | PD | BPD2011 | B1.2.12011 | 1.2.1 | Pixel Mechanics | [5 empty] | 2011 | 0 | 3 | 0 | 0 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hysol Adhesive Production | Hysol 9396 | 1 | Order | 500 | 500 | 0 | 1 | 0 | 0 | 0 | hours | 284.31 | 3 | 1784.31 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 3 | 0 | 0 | 0 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables Base | Expendable | 1 | Order | 1207.5 | 1207.5 | 0 | 2 | 0 | 0 | 0 | hours | 234 | 1 | 1441.5 | B | PT | BPT2011 | B1.2.12011 | 1.2.1 | Pixel Mechanics | [5 empty] | 2011 | 0 | 2 | 0 | 0 | 0 | 1207.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Expendables Contingency | Expendable | 1 | Order | 945 | 945 | 0 | 2 | 0 | 0 | 0 | hours | 234 | 1 | 1179 | B | PT | BPT2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 2 | 0 | 0 | 0 | 945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Material Batches Subtotal | [11 empty] | 9620.46 | Base Labor | [13 empty] | 0 | 55 | 0 | 35 | 0 |  | 48110 | 57574.85 |  | 35631.56 | 0 | 28 | 0 | 22 | 0 |  | 30305
Module Supports (Sectors)
Prototype Sector Tooling | [12 empty] | 1
Sector Tool EDM | Aluminum | 20 | lb | 8 | 160 | 8 | 2 | 0 | 4 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.1.12009 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Tool Machined Iteration Engineering | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Tool Machined Iteration (Engineering Contingency) | Labor | 1 | N/A | 8 | 8 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6008 | C | PT | CPT2012 | C1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 8
Sector Tool Machined Iteration | Aluminum | 20 | lb | 8 | 160 | 16 | 2 | 0 | 0 | 0 | hours | 2250 | 1 | 2410 | B | PT | BPT2013 | B1.2.1.1.12013 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2013 | 16 | 2 | 0 | 0 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Tool Machined Iteration (Contingency) | Aluminum | 20 | lb | 8 | 160 | 16 | 2 | 0 | 40 | 0 | hours | 8250 | 1 | 8410 | C | PT | CPT2013 | C1.2.1.1.12013 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 2 | 0 | 40 | 0 | 160
Prototype Sector Laminates | [10 empty] | Sum | 8250 | Base Labor
Thermal Model Laminates | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.1.12009 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Insertion Laminates (Iterated Tool (?)) | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.1.1.12010 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Engineering Run Laminates | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 0 | 0 | hours | 2843.1 | 5 | 2843.1 | B | PD | BPD2011 | B1.2.1.1.12011 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2011 | 0 | 30 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Engineering Run Laminates (Contingency) | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 0 | 0 | hours | 3980.34 | 7 | 3980.34 | C | PD | CPD2012 | C1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 42 | 0 | 0 | 0 | 0
Production Sector Laminates | [10 empty] | Sum | 2843.1 | Base Labor
Production Sector Laminates | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 0 | 0 | hours | 14215.5 | 25 | 14215.5 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 150 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Sector Laminates (Contingency) | Labor | 0.03 | N/A | 0 | 0 | 0 | 6 | 0 | 0 | 0 | hours | 5686.2 | 10 | 5686.2 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 60 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface Parts (Prototype) | [10 empty] | Sum | 19901.7 | Base Labor
Prototype Dovetail (Al) | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.1.12009 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Dovetail (SLA) | Contract | 1 | Units | 150 | 150 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.1.12009 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Dovetail Iteration Engineering | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 9000 | 1 | 9000 | B | PT | BPT2012 | B1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Dovetail (Al) (Iteration) | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 0 | 0 | hours | 4882.5 | 5 | 5122.5 | B | PT | BPT2012 | B1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 38.75 | 0 | 0 | 0 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Dovetail (SLA) (Iteration) | Contract | 1 | Units | 150 | 150 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.1.1.12011 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Dovetail (Al) (Iteration-Contingency) | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 4 | 0 | hours | 15323.58 | 12 | 15899.58 | C | PD | CPD2012 | C1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 93 | 0 | 0 | 48 | 0 | 576
Prototype Dovetail (SLA) (Iteration-Contingency) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.2.1.1.12011 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype End Reinforcement (SLA) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 10 | 500 | B | PT | BPT2012 | B1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype End Reinforcement (SLA) (Iteration) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 12 | 600 | B | PT | BPT2012 | B1.2.1.1.12012 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype End Reinforcement (SLA) (Iteration-Contingency) | Contract | 1 | Units | 150 | 150 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 12 | 1800 | C | PD | CPD2013 | C1.2.1.1.12013 | 1.2.1.1.1 | Sector Mechanical Prototypes | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1800
Interface Parts (Production) | [10 empty] | Sum | 13882.5 | Base Labor
Dovetail | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 2 | 0 | hours | 25849.125 | 25 | 27049.125 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 193.75 | 0 | 0 | 50 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
End Reinforcement (SLA) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 1 | 0 | hours | 3037.5 | 25 | 4287.5 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 25 | 0 | 1250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Dovetail Contingency | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 8 | 0 | hours | 8814.825 | 5 | 9054.825 | C | PD | CPD2013 | C1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 38.75 | 0 | 0 | 40 | 0 | 240
End Reinforcement (SLA) Contingency | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 2 | 0 | hours | 1215 | 5 | 1465 | C | PD | CPD2013 | C1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 250
Sector Component Assembly (Prototype) | [10 empty] | Sum | 28886.625 | Base Labor
Bonded Assembly Tool | Aluminum | 15 | lb | 8 | 120 | 16 | 8 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.3.1.12009 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 0 | 0 | 0 | B | PT | BPTCONT | B1.2.3.1.1CONT | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration) | Aluminum | 15 | lb | 8 | 120 | 16 | 8 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration Contingency Engineering) | Labor | 0 | N/A | 0 | 0 | 16 | 8 | 0 | 40 | 0 | hours | 0 | 0 | 0 | C | PT | CPT2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration Contingency) | Aluminum | 15 | lb | 8 | 120 | 0 | 0 | 0 | 20 | 0 | hours | 0 | 0 | 0 | C | PT | CPT2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Thermal Model) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.3.1.12009 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Insertion Model) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Engineering Run) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Engineering Run Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 1 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Component Assembly (Production) | [10 empty] | Sum | 0 | Base Labor
Bonded Assembly Production | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 1 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Engineering and Oversight) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 40 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 1 | 0 | hours | 0 | 0 | 0 | B | PD | BPD2013 | B1.2.3.1.12013 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pixel Sector Sub Total | [11 empty] | 73763.925 | Base Labor | [13 empty] | 248.5 | 242 | 0 | 175 | 0 |  | 3950 | 73508.75 |  | 43910.245 | 147.75 | 44 | 0 | 178 | 0 |  | 3034
Sector Assembly and Survey | [12 empty] | .
Ladder Mount Tooling | [12 empty] | .
Ladder Mount Tool Engineering | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7290 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ladder Mount Tool (Engineering Contingency) | Labor | 1 | N/A | 8 | 8 | 0 | 0 | 0 | 60 | 0 | hours | 7290 | 1 | 7298 | C | PD | CPD2013 | C1.2.3.1.12013 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 60 | 0 | 8
Ladder Mount Tool | Aluminum | 50 | lb | 8 | 400 | 80 | 4 | 0 | 0 | 0 | hours | 34175.52 | 4 | 35775.52 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 320 | 16 | 0 | 0 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ladder Mount Tool | Aluminum | 50 | lb | 8 | 400 | 80 | 4 | 0 | 0 | 0 | hours | 34175.52 | 4 | 35775.52 | C | PD | CPD2013 | C1.2.3.1.12013 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 320 | 16 | 0 | 0 | 0 | 1600
Prototype Sector Assemblies | [10 empty] | Sum | 41465.52 | Base Labor
Thermal Model Sectors | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.3.1.12009 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Insertion Sectors Engineering Oversight | Labor | 0.03 | N/A | 0 | 0 | 0 | 0 | 0 | 24 | 0 | hours | 0 | 0 | 0 | B | PT | BPTCONT | B1.2.3.1.1CONT | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Insertion Sectors | Labor | 0.03 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Engineering Run Sectors | Labor | 0.03 | N/A | 0 | 0 | 0 | 12 | 0 | 2 | 0 | hours | 6901.2 | 5 | 6901.2 | B | PD | BPD2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 60 | 0 | 10 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Engineering Run Sectors (Contingency) | Labor | 0.03 | N/A | 0 | 0 | 0 | 12 | 0 | 2 | 0 | hours | 9661.68 | 7 | 9661.68 | C | PD | CPD2012 | C1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 84 | 0 | 14 | 0 | 0
Production Sector Assemblies | [10 empty] | Sum | 6901.2 | Base Labor
Production Sector Sectors | Labor | 0.03 | N/A | 0 | 0 | 0 | 12 | 0 | 2 | 0 | hours | 34506 | 25 | 34506 | B | PD | BPD2013 | B1.2.3.1.22013 | 1.2.3.1.2 | Electrical Sector Assemblies | [5 empty] | 2013 | 0 | 300 | 0 | 50 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Sector Sectors (Contingency) | Labor | 0.03 | N/A | 0 | 0 | 0 | 12 | 0 | 2 | 0 | hours | 13802.4 | 10 | 13802.4 | C | PD | CPD2013 | C1.2.3.1.22013 | 1.2.3.1.2 | Electrical Sector Assemblies | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 120 | 0 | 20 | 0 | 0
Sector Survey and Tooling | [10 empty] | Sum | 34506 | Base Labor
Sector Survey Tool | Aluminum | 15 | lb | 8 | 120 | 8 | 0 | 16 | 4 | 0 | hours | 5870.88 | 2 | 6110.88 | B | PD | BPD2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 16 | 0 | 32 | 8 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Survey Tool Contingency | Aluminum | 15 | Units | 8 | 120 | 40 | 0 | 16 | 20 | 0 | hours | 16290.72 | 2 | 16530.72 | C | PD | CPD2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 80 | 0 | 32 | 40 | 0 | 240
Survey Procedure Development (contributed ENG) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Survey Procedure Development | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 24 | 0 | 0 | hours | 2449.44 | 1 | 2449.44 | B | PD | BPD2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 24 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Survey Procedure Contingency | Labor | 0 | N/A | 0 | 0 | 7.75 | 0 | 16 | 40 | 0 | hours | 7283.925 | 1 | 7283.925 | C | PD | CPD2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 7.75 | 0 | 16 | 40 | 0 | 0
Prototype Dovetail (SLA) (Iteration) | Contract | 1 | Units | 150 | 150 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Dovetail (Al) (Iteration-Contingency) | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 4 | 0 | hours | 15323.58 | 12 | 15899.58 | C | PD | CPD2012 | C1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 93 | 0 | 0 | 48 | 0 | 576
Prototype Dovetail (SLA) (Iteration-Contingency) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | C | PD | CPD2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype End Reinforcement (SLA) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.3.1.12009 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype End Reinforcement (SLA) (Iteration) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 2 | 0 | hours | 3600 | 12 | 4200 | B | PT | BPT2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 24 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype End Reinforcement (SLA) (Iteration-Contingency) | Contract | 1 | Units | 150 | 150 | 0 | 0 | 0 | 2 | 0 | hours | 2916 | 12 | 4716 | C | PD | CPD2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 24 | 0 | 1800
Interface Parts (Production) | [10 empty] | Sum | 16780.32 | Base Labor
Dovetail | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 2 | 0 | hours | 25849.125 | 25 | 27049.125 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 193.75 | 0 | 0 | 50 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
End Reinforcement (SLA) | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 1 | 0 | hours | 3037.5 | 25 | 4287.5 | B | PD | BPD2013 | B1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 25 | 0 | 1250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Dovetail Contingency | Aluminum | 6 | lb | 8 | 48 | 7.75 | 0 | 0 | 8 | 0 | hours | 8814.825 | 5 | 9054.825 | C | PD | CPD2013 | C1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 38.75 | 0 | 0 | 40 | 0 | 240
End Reinforcement (SLA) Contingency | Contract | 1 | Units | 50 | 50 | 0 | 0 | 0 | 2 | 0 | hours | 1215 | 5 | 1465 | C | PD | CPD2013 | C1.2.1.1.22013 | 1.2.1.1.2 | Production Sectors | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 250
Sector Component Assembly (Prototype) | [10 empty] | Sum | 28886.625 | Base Labor
Bonded Assembly Tool | Aluminum | 15 | lb | 8 | 120 | 16 | 8 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.3.1.12009 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration) | Aluminum | 15 | lb | 8 | 120 | 16 | 8 | 0 | 0 | 0 | hours | 2952 | 1 | 3072 | B | PT | BPT2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 16 | 8 | 0 | 0 | 0 | 120 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly Tool (Iteration Contingency Engineering) | Labor | 0 | N/A | 0 | 0 | 16 | 8 | 0 | 40 | 0 | hours | 8952 | 1 | 8952 | C | PT | CPT2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 8 | 0 | 40 | 0 | 0
Bonded Assembly Tool (Iteration Contingency) | Aluminum | 15 | lb | 8 | 120 | 0 | 0 | 0 | 20 | 0 | hours | 3000 | 1 | 3120 | C | PT | CPT2011 | C1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 20 | 0 | 120
Bonded Assembly (Thermal Model) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.3.1.12009 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Insertion Model) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.3.1.12010 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Engineering Run) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 2 | 0 | hours | 3110.4 | 5 | 3110.4 | B | PD | BPD2011 | B1.2.3.1.12011 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2011 | 0 | 20 | 0 | 10 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Engineering Run Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 1 | 0 | hours | 3504.06 | 7 | 3504.06 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 28 | 0 | 7 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Component Assembly (Production) | [10 empty] | Sum | 15566.46 | Base Labor
Bonded Assembly Production | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 1 | 0 | hours | 12514.5 | 25 | 12514.5 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 100 | 0 | 25 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Engineering and Oversight) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 40 | 0 | hours | 5239.08 | 1 | 5239.08 | B | PD | BPD2012 | B1.2.3.1.12012 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2012 | 0 | 4 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 1 | 0 | hours | 5005.8 | 10 | 5005.8 | C | PD | CPD2013 | C1.2.3.1.12013 | 1.2.3.1.1 | Mechanical Sector Assemblies | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 40 | 0 | 10 | 0 | 0
Sector Mount and Survey | [10 empty] | Sum | 17753.58 | Base Labor
Sector Survey Tool Production | Aluminum | 15 | lb | 8 | 120 | 0 | 8 | 0 | 20 | 0 | hours | 6376.32 | 2 | 6616.32 | B | PD | BPD2012 | B1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 16 | 0 | 40 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Survey Tool Contingency | Aluminum | 15 | lb | 8 | 120 | 20 | 8 | 0 | 0 | 0 | hours | 5598.72 | 2 | 5838.72 | C | PD | CPD2012 | C1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 16 | 0 | 0 | 0 | 240
Sector Survey Engineering Run | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 8 | 16 | 0 | hours | 8850.06 | 3 | 8850.06 | B | PD | BPD2012 | B1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 6 | 24 | 48 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Survey Engineering Run (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 4 | 2 | 0 | hours | 5885.46 | 7 | 5885.46 | C | PD | CPD2012 | C1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 14 | 28 | 14 | 0 | 0
Sector Survey 2013 Install (partial 5) | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 4 | 2 | 0 | hours | 4203.9 | 5 | 4203.9 | B | PD | BPD2012 | B1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 10 | 20 | 10 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Survey 2013 Install (partial 10) | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 4 | 2 | 0 | hours | 8407.8 | 10 | 8407.8 | B | PD | BPD2013 | B1.2.3.32013 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2013 | 0 | 20 | 40 | 20 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Survey 2013 Install (partial 10) | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 4 | 2 | 0 | hours | 8407.8 | 10 | 8407.8 | B | PD | BPD2014 | B1.2.3.32014 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2014 | 0 | 20 | 40 | 20 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Survey 2013 Install (Contingency 5 2013) | Labor | 0 | N/A | 0 | 0 | 0 | 2 | 4 | 2 | 0 | hours | 4203.9 | 5 | 4203.9 | B | PD | BPD2013 | B1.2.3.32013 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2013 | 0 | 10 | 20 | 10 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Mount and Survey Eng Run | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 40 | 40 | 0 | hours | 22433.76 | 2 | 22433.76 | B | PD | BPD2012 | B1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 48 | 80 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Mount and Survey Eng Run (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 16 | 24 | 0 | hours | 13646.88 | 2 | 13646.88 | C | PD | CPD2012 | C1.2.3.32012 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 32 | 48 | 0 | 0
Sector Mount and Survey 2013 Install | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 40 | 40 | 0 | hours | 22433.76 | 2 | 22433.76 | B | PD | BPD2013 | B1.2.3.32013 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2013 | 0 | 48 | 80 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Mount and Survey 2013 Install (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 16 | 24 | 0 | hours | 6823.44 | 1 | 6823.44 | C | PD | CPD2013 | C1.2.3.32013 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 24 | 16 | 24 | 0 | 0
Sector Mount and Survey Spare | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 40 | 40 | 0 | hours | 22433.76 | 2 | 22433.76 | B | PD | BPD2013 | B1.2.3.32013 | 1.2.3.3 | Sector Mount And Survey | [5 empty] | 2013 | 0 | 48 | 80 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pixel Sector Sub Total | [11 empty] | 269610.765 | Base Labor | [13 empty] | 545.75 | 762 | 440 | 777 | 0 |  | 5010 | 272235.885 |  | 168249.07 | 595.5 | 370 | 124 | 452 | 0 |  | 4834
[11 empty] | Sum | 107751.06 | Base Labor
D-Tube and Kinematic Mounts
Tooling D-Tube_Shell
Half Shell Lamination
D-Tube Tooling Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 18000 | 1 | 18000 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Welded Tube Assembly/Machine | Steel | 200 | lb | 4 | 800 | 40 | 0 | 0 | 0 | 0 | hours | 5040 | 1 | 5840 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 40 | 0 | 0 | 0 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Material CTE Study | Labor | 0 | N/A | 0 | 0 | 2 | 8 | 0 | 0 | 0 | hours | 1188 | 1 | 1188 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 2 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Nickel Plate | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 504 | 1 | 1704 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 4 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Re-Machine (contingency) | Labor | 0 | N/A | 0 | 0 | 24 | 0 | 0 | 40 | 0 | hours | 7309.44 | 1 | 7309.44 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 0 | 0 | 40 | 0 | 0
Nickel Plate (contingency) | Contract | 1 | N/A | 1200 | 1200 | 4 | 0 | 0 | 0 | 0 | hours | 408.24 | 1 | 1608.24 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 4 | 0 | 0 | 0 | 0 | 1200
Trim Fixture | Aluminum | 40 | lb | 8 | 320 | 24 | 0 | 0 | 0 | 0 | hours | 6048 | 2 | 6688 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 48 | 0 | 0 | 0 | 0 | 640 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Dovetail Transition Tooling | [10 empty] | Sum | 30780 | Sum | 33420
Lamination Tool Design | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 9000 | 1 | 9000 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool | Aluminum | 40 | lb | 8 | 320 | 24 | 8 | 0 | 0 | 0 | hours | 3207.6 | 1 | 3527.6 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 24 | 8 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Lamination Tool (Contingency) | Aluminum | 40 | lb | 8 | 320 | 24 | 8 | 0 | 40 | 0 | hours | 8067.6 | 1 | 8387.6 | C | PD | CPD2011 | C1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 24 | 8 | 0 | 40 | 0 | 320
Trim Tool | Aluminum | 40 | lb | 8 | 320 | 16 | 0 | 0 | 0 | 0 | hours | 1632.96 | 1 | 1952.96 | B | PD | BPD2011 | B1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 16 | 0 | 0 | 0 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Half Shell Bond | [10 empty] | Sum | 13840.56 | Sum | 14480.56
Assmbly Jig (w/out Kinematic Mounts) | Aluminum | 80 | lb | 8 | 640 | 8 | 8 | 0 | 0 | 0 | hours | 1944 | 1 | 2584 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 8 | 8 | 0 | 0 | 0 | 640 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assmbly Jig (w/out Kinematic Mounts) (CTB ENG) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 32 | 0 | hours | 4800 | 1 | 4800 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Assmbly Jig (w/ Kinematic Mounts) | Aluminum | 20 | lb | 8 | 160 | 8 | 16 | 0 | 32 | 0 | hours | 7680 | 1 | 7840 | B | PT | BPT2011 | B1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 8 | 16 | 0 | 32 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Interface Parts (Duct and Dovetail Plate) | [10 empty] | Sum | 14424 | Sum
3" Duct Thermal Model | Contract | 2 | Units | 600 | 1200 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.2.12009 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3" Duct Insertion Model | Contract | 2 | Units | 600 | 1200 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1200 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3" Duct Engineering Run (contingency) | Contract | 2 | Units | 600 | 1200 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 1 | 1200 | B | PD | BPD2011 | B1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Dovetail Plate Insertion Model | Aluminum | 5 | lb | 8 | 40 | 8 | 0 | 0 | 2 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.2.12009 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Dovetail Plate Engineering Run | Aluminum | 5 | lb | 8 | 40 | 8 | 0 | 0 | 2 | 0 | hours | 2118.96 | 2 | 2198.96 | B | PD | BPD2011 | B1.2.1.2.12011 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2011 | 16 | 0 | 0 | 4 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3" Duct Production | Contract | 2 | Units | 600 | 1200 | 0 | 0 | 0 | 2 | 0 | hours | 486 | 2 | 2886 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 0 | 0 | 4 | 0 | 2400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Dovetail Plate Production | Aluminum | 5 | lb | 8 | 40 | 8 | 0 | 0 | 2 | 0 | hours | 4237.92 | 4 | 4397.92 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 32 | 0 | 0 | 8 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3" Duct Production (contingency) | Contract | 2 | Units | 600 | 1200 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 4116 | C | PD | CPD2013 | C1.2.1.2.32013 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 24 | 0 | 1200
Dovetail Plate Production (contingency) | Aluminum | 5 | lb | 8 | 40 | 8 | 0 | 0 | 12 | 0 | hours | 4548.96 | 2 | 4628.96 | C | PD | CPD2013 | C1.2.1.2.32013 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 16 | 0 | 0 | 24 | 0 | 80
D-Tube Laminate Fabrication | [10 empty] | Sum | 6842.88 | Sum
Ply Trim and Kit | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 936 | 1 | 936 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Half Shell Engineering | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Half Shell | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 0 | 0 | hours | 3744 | 1 | 3744 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Half Shell Engineering | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | C | PD | CPD2012 | C1.2.1.2.12012 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 40 | 0 | 0
Prototype Half Shell Iteration | Bagging | 1 | m^2 | 105 | 105 | 0 | 32 | 0 | 0 | 0 | hours | 3744 | 1 | 3849 | C | PT | CPT2010 | C1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 0 | 0 | 105
Prototype Half Shell Insertion Test Bed | Bagging | 1 | m^2 | 105 | 105 | 0 | 24 | 0 | 0 | 0 | hours | 5616 | 2 | 5826 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 48 | 0 | 0 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Ply Trim and Kit (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | C | PD | CPD2012 | C1.2.1.2.12012 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 2 | 0 | 0
Prototype Half Shell Engineering Run (Contingency) | Bagging | 1 | m^2 | 105 | 105 | 0 | 24 | 0 | 8 | 0 | hours | 6492.96 | 2 | 6702.96 | C | PD | CPD2012 | C1.2.1.2.12012 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 16 | 0 | 210
Ply Trim and Kit Production | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 2 | 0 | hours | 1001.16 | 1 | 1001.16 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 8 | 0 | 2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Half Shell | Bagging | 1 | m^2 | 105 | 105 | 0 | 24 | 0 | 8 | 0 | hours | 12985.92 | 4 | 13405.92 | B | PD | BPD2012 | B1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 96 | 0 | 32 | 0 | 420 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Half Shell (Contingency) | Bagging | 1 | m^2 | 105 | 105 | 0 | 24 | 0 | 8 | 0 | hours | 6492.96 | 2 | 6702.96 | C | PD | CPD2012 | C1.2.1.2.32012 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 16 | 0 | 210
Dovetail Transition Ring Fabrication | [10 empty] | Sum | 30283.08 | Sum
Prototype Shell Fabrication Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 48 | 0 | hours | 5832 | 1 | 5832 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 48 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Shell | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2326.98 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 24 | 0 | 0 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Shell Iteration | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 24 | 0 | 0 | 0 | hours | 2274.48 | 1 | 2326.98 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 24 | 0 | 0 | 0 | 52.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Shell Insertion Test Bed | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 2 | 0 | hours | 2002.32 | 2 | 2107.32 | B | PD | BPD2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 16 | 0 | 4 | 0 | 105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Shell Engineering Run (Contingency) | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 8 | 0 | 2 | 0 | hours | 2002.32 | 2 | 2107.32 | C | PD | CPD2013 | C1.2.1.2.12013 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 16 | 0 | 4 | 0 | 105
Production Shell | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 16 | 0 | 4 | 0 | hours | 8009.28 | 4 | 8219.28 | B | PD | BPD2013 | B1.2.1.2.32013 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2013 | 0 | 64 | 0 | 16 | 0 | 210 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production Shell (Contingency) | Bagging | 0.5 | m^2 | 105 | 52.5 | 0 | 20 | 0 | 8 | 0 | hours | 11469.6 | 4 | 11679.6 | C | PD | CPD2013 | C1.2.1.2.32013 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 80 | 0 | 32 | 0 | 210
D-Tube Bonded Assembly (w/out mounts) | [10 empty] | Sum | 20392.56 | Sum
Assembly and Survey Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Tool Assembly and Survey | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 4 | 0 | 0 | hours | 2376 | 1 | 2376 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 16 | 4 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype D-Tube Assembly First Article | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 0 | 0 | hours | 5616 | 2 | 5616 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 48 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype D-Tube Assembly insertion test bed | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 0 | 0 | 0 | hours | 1872 | 1 | 1872 | B | PT | BPT2010 | B1.2.1.2.12010 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2010 | 0 | 16 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype D-Tube Assembly (Engineereing Run) | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 4 | 0 | hours | 5520.96 | 2 | 5520.96 | C | PD | CPD2012 | C1.2.1.2.12012 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 8 | 0 | 0
Production D-Tube Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 4 | 0 | hours | 11041.92 | 4 | 11041.92 | B | PD | BPD2013 | B1.2.1.2.12013 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2013 | 0 | 96 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production D-Tube Assembly (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 24 | 0 | 4 | 0 | hours | 11041.92 | 4 | 11041.92 | C | PD | CPD2013 | C1.2.1.2.12013 | 1.2.1.2.1 | Prototype D-Tube | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 96 | 0 | 16 | 0 | 0
Kinematic Mounts | [10 empty] | Sum | 26905.92 | Sum
Kinematic Mount Prototype Design and Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 18000 | 1 | 18000 | B | PT | BPT2010 | B1.2.1.2.22010 | 1.2.1.2.2 | Prototype Kinematic Mounts | [5 empty] | 2010 | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Prototype Design (ITB) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 12000 | 1 | 12000 | B | PT | BPT2010 | B1.2.1.2.22010 | 1.2.1.2.2 | Prototype Kinematic Mounts | [5 empty] | 2010 | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Prototype (1/2 Detector) | Aluminum | 2 | lb | 8 | 16 | 4 | 0 | 0 | 0 | 0 | hours | 1512 | 3 | 1560 | B | PT | BPT2010 | B1.2.1.2.22010 | 1.2.1.2.2 | Prototype Kinematic Mounts | [5 empty] | 2010 | 12 | 0 | 0 | 0 | 0 | 48 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Prototype (1/2 Detector Iteration) | Aluminum | 2 | lb | 8 | 16 | 16 | 0 | 0 | 4 | 0 | hours | 7848 | 3 | 7896 | C | PT | CPT2010 | C1.2.1.2.22010 | 1.2.1.2.2 | Prototype Kinematic Mounts | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 48 | 0 | 0 | 12 | 0 | 48
Kinematic Mount Prototype (Insertion Test Bed) | Aluminum | 2 | lb | 8 | 16 | 4 | 0 | 0 | 4 | 0 | hours | 6624 | 6 | 6720 | B | PT | BPT2010 | B1.2.1.2.22010 | 1.2.1.2.2 | Prototype Kinematic Mounts | [5 empty] | 2010 | 24 | 0 | 0 | 24 | 0 | 96 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Prototype (Engineering Run) | Aluminum | 2 | lb | 8 | 16 | 16 | 0 | 0 | 1 | 0 | hours | 10526.76 | 6 | 10622.76 | B | PD | BPD2012 | B1.2.1.2.22012 | 1.2.1.2.2 | Prototype Kinematic Mounts | [5 empty] | 2012 | 96 | 0 | 0 | 6 | 0 | 96 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount (Production) | Aluminum | 2 | lb | 8 | 16 | 4 | 0 | 0 | 1 | 0 | hours | 6356.88 | 12 | 6548.88 | B | PD | BPD2013 | B1.2.1.2.32013 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2013 | 48 | 0 | 0 | 12 | 0 | 192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount (Production Contingency) | Aluminum | 2 | lb | 8 | 16 | 16 | 0 | 0 | 1 | 0 | hours | 10526.76 | 6 | 10622.76 | C | PD | CPD2013 | C1.2.1.2.32013 | 1.2.1.2.3 | Production D-Tube and Kinematic Mounts | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 96 | 0 | 0 | 6 | 0 | 96
Kinematic Mount Bond Operation | [10 empty] | Sum | 55019.64 | Sum
Tool Assembly and Survey Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Tool Assembly and Survey (1/2 Detector) | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 8 | 8 | 0 | hours | 3304.8 | 1 | 3304.8 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 16 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Iteration Tool Assembly and Survey (1/2 Detector) | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 8 | 8 | 0 | hours | 3304.8 | 1 | 3304.8 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 16 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
'Final' Tool Assembly and Survey (Full Detector) | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 8 | 4 | 0 | hours | 5637.6 | 2 | 5637.6 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 32 | 16 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Bonded Assembly (insertion test bed) | Labor | 1 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 24 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Bonded Assembly (Iteration) | Labor | 1 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 4062.96 | 1 | 4062.96 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 24 | 8 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Bonded Assembly (Engineering Run) | Labor | 1 | N/A | 0 | 0 | 0 | 24 | 8 | 4 | 0 | hours | 7153.92 | 2 | 7153.92 | B | PD | BPD2011 | B1.2.3.22011 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2011 | 0 | 48 | 16 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Bonded Assembly (Production) | Labor | 1 | N/A | 0 | 0 | 0 | 24 | 8 | 8 | 0 | hours | 16251.84 | 4 | 16251.84 | B | PD | BPD2013 | B1.2.3.22013 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2013 | 0 | 96 | 32 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Kinematic Mount Bonded Assembly (Contingency) | Labor | 1 | N/A | 0 | 0 | 0 | 24 | 8 | 4 | 0 | hours | 7153.92 | 2 | 7153.92 | C | PD | CPD2013 | C1.2.3.22013 | 1.2.3.2 | D-Tube Assembly and Survey Tool | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 16 | 8 | 0 | 0
Level Subtotal | [11 empty] | 247127.52 | Base Labor | [13 empty] | 378 | 792 | 100 | 820 | 0 |  | 10602 | 234074.52 |  | 102986.32 | 212 | 432 | 16 | 288 | 0 |  | 3784
[11 empty] | Sum | 48638.88 | Sum
Insertion Mechanism and Service Supports
Thermal Prototype | [12 empty] | 1
Sector Supports/D-tube Mockup Assembly | Contract | 1 | Units | 2800 | 2800 | 0 | 32 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.3.12009 | 1.2.1.3.1 | Thermal Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sector Supports/D-tube Mockup Assembly (Iteration) | Contract | 1 | Units | 2800 | 2800 | 0 | 32 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.3.12009 | 1.2.1.3.1 | Thermal Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MSC Volume Mock-up and IR Camera supports | Acrylic/Lexan | 40 | lb | 20 | 800 | 0 | 40 | 0 | 8 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.3.12009 | 1.2.1.3.1 | Thermal Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Thermal Testing Base Effort | Labor | 0 | N/A | 0 | 0 | 0 | 80 | 0 | 24 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2009 | B1.2.1.3.12009 | 1.2.1.3.1 | Thermal Prototype | [5 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Thermal Testing Extended Test Effort | Labor | 0 | N/A | 0 | 0 | 0 | 80 | 0 | 0 | 0 | hours | 9360 | 1 | 9360 | B | PT | BPT2010 | B1.2.1.3.12010 | 1.2.1.3.1 | Thermal Prototype | [5 empty] | 2010 | 0 | 80 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Thermal Testing Engineering 2011 | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2011 | B1.2.1.3.12011 | 1.2.1.3.1 | Thermal Prototype | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Thermal Testing Contributed Effort | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 60 | 0 | hours | 0 | 0 | 0 | B | PT | BPTCONT | B1.2.1.3.1CONT | 1.2.1.3.1 | Thermal Prototype | [5 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insertion Test Bed | [10 empty] | Sum | 9360 | Sum
Design Effort | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 60 | 0 | hours | 13680 | 1 | 13680 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 0 | 40 | 0 | 60 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Bed Fabrication | Aluminum | 850 | lb | 8 | 6800 | 40 | 160 | 24 | 30 | 0 | hours | 31284 | 1 | 38084 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 40 | 160 | 24 | 30 | 0 | 6800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Bed Assembly | Labor | 0 | N/A | 0 | 0 | 8 | 80 | 24 | 30 | 0 | hours | 17892 | 1 | 17892 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 8 | 80 | 24 | 30 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Bed Iteration | Labor | 120 | lb | 8 | 960 | 12 | 80 | 16 | 60 | 0 | hours | 21888 | 1 | 22848 | B | PT | BPT2011 | B1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 12 | 80 | 16 | 60 | 0 | 960 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Test Bed Iteration | Labor | 120 | lb | 8 | 960 | 60 | 80 | 16 | 60 | 0 | hours | 27936 | 1 | 28896 | C | PT | CPT2011 | C1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 60 | 80 | 16 | 60 | 0 | 960
Insertion Testing | Labor | 0 | N/A | 0 | 0 | 0 | 80 | 0 | 80 | 0 | hours | 21360 | 1 | 21360 | B | PT | BPT2011 | B1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 0 | 80 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Insertion Mechanism | [10 empty] | Sum | 106104 | Sum
Design Effort Contributed | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 160 | 0 | hours | 24000 | 1 | 24000 | B | PT | BPT2011 | B1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 0 | 0 | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Effort | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 160 | 0 | hours | 24000 | 1 | 24000 | B | PT | BPT2011 | B1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 0 | 0 | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Effort | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 40 | 0 | hours | 10680 | 1 | 10680 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 0 | 40 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Fabrication and Assembly | Aluminum | 80 | lb | 8 | 640 | 120 | 160 | 24 | 60 | 0 | hours | 0 | 0 | 0 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware (Bearings, Fasteners et-al) | Contract | 1 | Order | 5000 | 5000 | 0 | 8 | 0 | 8 | 0 | hours | 2136 | 1 | 7136 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 0 | 8 | 0 | 8 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hinge and Transfer Mechanism | Contract | 1 | Order | 3000 | 3000 | 8 | 40 | 0 | 30 | 0 | hours | 10188 | 1 | 13188 | B | PT | BPT2010 | B1.2.1.3.22010 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2010 | 8 | 40 | 0 | 30 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hinge and Transfer Mechanism (Iteration) | Contract | 1 | Order | 3000 | 3000 | 24 | 40 | 0 | 60 | 0 | hours | 16704 | 1 | 19704 | B | PT | BPT2011 | B1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 24 | 40 | 0 | 60 | 0 | 3000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Prototype Iteration (Low Mass Design) | Aluminum | 80 | lb | 8 | 640 | 12 | 80 | 16 | 120 | 0 | hours | 30888 | 1 | 31528 | B | PT | BPT2011 | B1.2.1.3.22011 | 1.2.1.3.2 | Insertion Test Bed | [5 empty] | 2011 | 12 | 80 | 16 | 120 | 0 | 640 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Low Mass Cart Prototype | [10 empty] | Sum | 118596 | Sum
Design Effort Contributed | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 160 | 0 | hours | 24000 | 1 | 24000 | B | PT | BPT2010 | B1.2.1.3.32010 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2010 | 0 | 0 | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Prototype Fabrication (1/2 Detector) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 6000 | 1 | 6000 | B | PT | BPT2011 | B1.2.1.3.32011 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Rail Rider Fabrication | Aluminum | 15 | lb | 8 | 120 | 24 | 0 | 0 | 40 | 0 | hours | 9024 | 1 | 9144 | B | PT | BPT2011 | B1.2.1.3.32011 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2011 | 24 | 0 | 0 | 40 | 0 | 120 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Card Cage Fabrication | Aluminum | 20 | lb | 8 | 160 | 24 | 0 | 0 | 64 | 0 | hours | 12624 | 1 | 12784 | B | PT | BPT2011 | B1.2.1.3.32011 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2011 | 24 | 0 | 0 | 64 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Internediate Support Fabrication | Contract | 1 | Order | 300 | 300 | 0 | 24 | 0 | 24 | 0 | hours | 6408 | 1 | 6708 | B | PT | BPT2011 | B1.2.1.3.32011 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2011 | 0 | 24 | 0 | 24 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bond Tooling Design/Fabrication | Aluminum | 70 | lb | 8 | 560 | 8 | 24 | 0 | 60 | 0 | hours | 12816 | 1 | 13376 | B | PT | BPT2011 | B1.2.1.3.32011 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2011 | 8 | 24 | 0 | 60 | 0 | 560 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly of 1/2 cart | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 6144 | 1 | 6144 | B | PT | BPT2011 | B1.2.1.3.32011 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2011 | 0 | 32 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Fabrication (Engineering Run) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2012 | B1.2.1.3.32012 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2012 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Rail Rider Fabrication | Aluminum | 15 | lb | 8 | 120 | 8 | 0 | 0 | 4 | 0 | hours | 2604.96 | 2 | 2844.96 | B | PD | BPD2012 | B1.2.1.3.32012 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2012 | 16 | 0 | 0 | 8 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Card Cage Fabrication | Aluminum | 20 | lb | 8 | 160 | 24 | 0 | 0 | 4 | 0 | hours | 5870.88 | 2 | 6190.88 | B | PD | BPD2012 | B1.2.1.3.32012 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2012 | 48 | 0 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Internediate Support Fabrication | Contract | 1 | Order | 300 | 300 | 0 | 24 | 0 | 4 | 0 | hours | 5520.96 | 2 | 6120.96 | B | PD | BPD2012 | B1.2.1.3.32012 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2012 | 0 | 48 | 0 | 8 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly of 1/2 cart | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 4 | 0 | hours | 7037.28 | 2 | 7037.28 | B | PD | BPD2012 | B1.2.1.3.32012 | 1.2.1.3.3 | Prototype Insertion Mechanism | [5 empty] | 2012 | 0 | 64 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Fabrication (Production) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2013 | B1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Rail Rider Fabrication | Aluminum | 15 | lb | 8 | 120 | 8 | 0 | 0 | 4 | 0 | hours | 2604.96 | 2 | 2844.96 | B | PD | BPD2013 | B1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 16 | 0 | 0 | 8 | 0 | 240 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Card Cage Fabrication | Aluminum | 20 | lb | 8 | 160 | 24 | 0 | 0 | 4 | 0 | hours | 5870.88 | 2 | 6190.88 | B | PD | BPD2013 | B1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 48 | 0 | 0 | 8 | 0 | 320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Internediate Support Fabrication | Contract | 1 | Order | 300 | 300 | 0 | 24 | 0 | 4 | 0 | hours | 5520.96 | 2 | 6120.96 | B | PD | BPD2013 | B1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 48 | 0 | 8 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bonded Assembly of 1/2 cart | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 4 | 0 | hours | 7037.28 | 2 | 7037.28 | B | PD | BPD2013 | B1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 64 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Cart Fabrication (Production Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 9720 | 2 | 9720 | C | PD | CPD2013 | C1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 80 | 0 | 0
Cart Rail Rider Fabrication | Aluminum | 15 | lb | 8 | 120 | 24 | 0 | 0 | 4 | 0 | hours | 5870.88 | 2 | 6110.88 | C | PD | CPD2013 | C1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 48 | 0 | 0 | 8 | 0 | 240
Card Cage Fabrication | Aluminum | 20 | lb | 8 | 160 | 24 | 0 | 0 | 4 | 0 | hours | 5870.88 | 2 | 6190.88 | C | PD | CPD2013 | C1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 48 | 0 | 0 | 8 | 0 | 320
Internediate Support Fabrication | Contract | 1 | Order | 300 | 300 | 0 | 24 | 0 | 4 | 0 | hours | 5520.96 | 2 | 6120.96 | C | PD | CPD2013 | C1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 8 | 0 | 600
Bonded Assembly of 1/2 cart | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 4 | 0 | hours | 7037.28 | 2 | 7037.28 | C | PD | CPD2013 | C1.2.1.3.42013 | 1.2.1.3.4 | Production Insertion Mechanism | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 64 | 0 | 8 | 0 | 0
Prototype Patch Panel Bulkhead | [10 empty] | Sum | 128804.16 | Sum
Design Effort Required for Cart "Integration" | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 48 | 0 | hours | 7200 | 1 | 7200 | B | PT | BPT2010 | B1.2.1.3.52010 | 1.2.1.3.5 | Prototype Patch Panel Bulkhead | [5 empty] | 2010 | 0 | 0 | 0 | 48 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Effort Required for Fabrication | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 9720 | 1 | 9720 | B | PD | BPD2012 | B1.2.1.3.52012 | 1.2.1.3.5 | Prototype Patch Panel Bulkhead | [5 empty] | 2012 | 0 | 0 | 0 | 80 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Insertion Kinematic Mockup | Aluminum | 80 | lb | 8 | 640 | 8 | 60 | 0 | 8 | 0 | hours | 7474.68 | 1 | 8114.68 | B | PD | BPD2012 | B1.2.1.3.52012 | 1.2.1.3.5 | Prototype Patch Panel Bulkhead | [5 empty] | 2012 | 8 | 60 | 0 | 8 | 0 | 640 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware (Bearings, Fasteners et-al) | Contract | 1 | Order | 2000 | 2000 | 0 | 8 | 0 | 0 | 8 | hours | 1568.16 | 1 | 3568.16 | B | PD | BPD2012 | B1.2.1.3.52012 | 1.2.1.3.5 | Prototype Patch Panel Bulkhead | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 8 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Prototype Fabrication (Engineering Run) | Aluminum | 40 | lb | 8 | 320 | 24 | 24 | 0 | 8 | 0 | hours | 11391.84 | 2 | 12031.84 | B | PD | BPD2012 | B1.2.1.3.52012 | 1.2.1.3.5 | Prototype Patch Panel Bulkhead | [5 empty] | 2012 | 48 | 48 | 0 | 16 | 0 | 640 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Patch Panel Bulkhead Production | [10 empty] | Sum | 95286.84 | Sum
Design Effort Required for Fabrication | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 40 | 0 | hours | 4860 | 1 | 4860 | B | PD | BPD2011 | B1.2.1.3.62011 | 1.2.1.3.6 | Production Patch Panel Bulkhead | [5 empty] | 2011 | 0 | 0 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware (Bearings, Fasteners et-al) | Contract | 1 | Order | 2000 | 2000 | 0 | 8 | 0 | 0 | 8 | hours | 1568.16 | 1 | 3568.16 | B | PD | BPD2012 | B1.2.1.3.62012 | 1.2.1.3.6 | Production Patch Panel Bulkhead | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 8 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Fabrication (Production) | Aluminum | 40 | lb | 8 | 320 | 24 | 60 | 0 | 8 | 0 | hours | 36430.56 | 4 | 37710.56 | B | PD | BPD2013 | B1.2.1.3.62013 | 1.2.1.3.6 | Production Patch Panel Bulkhead | [5 empty] | 2013 | 96 | 240 | 0 | 32 | 0 | 1280 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Fabrication (Contingency) | Aluminum | 40 | lb | 8 | 320 | 24 | 60 | 0 | 8 | 0 | hours | 18215.28 | 2 | 18855.28 | C | PD | CPD2013 | C1.2.1.3.62013 | 1.2.1.3.6 | Production Patch Panel Bulkhead | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 48 | 120 | 0 | 16 | 0 | 640
Level Subtotal | [11 empty] | 443077.56 | Base Labor | [13 empty] | 440 | 1396 | 80 | 1610 | 16 |  | 29420 | 412025.12 |  | 77623.44 | 204 | 312 | 16 | 188 | 0 |  | 2760
[11 empty] | Sum | 42858.72 | Sum
Final Assembly and Installation | [12 empty] | .
Detector Half Enclosure (Engineering) | [12 empty] | 1
Rail Assembly Hardware | Contract | 2 | Units | 800 | 1600 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 8176.64 | B | PD | BPD2011 | B1.2.3.4.12011 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2011 | 0 | 32 | 0 | 16 | 0 | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ITEM 80/20 Hardware | Contract | 2 | Units | 1200 | 2400 | 16 | 16 | 0 | 8 | 0 | hours | 8242.56 | 2 | 13042.56 | B | PD | BPD2011 | B1.2.3.4.12011 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2011 | 32 | 32 | 0 | 16 | 0 | 4800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Covers/Ducting | Acrylic/Lexan | 40 | lb | 20 | 800 | 16 | 32 | 0 | 8 | 0 | hours | 11275.2 | 2 | 12875.2 | B | PD | BPD2011 | B1.2.3.4.12011 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2011 | 32 | 64 | 0 | 16 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Detector Half Enclosure Production | [10 empty] | Sum | 24494.4 | Sum
Rail Assembly Hardware | Contract | 2 | Units | 800 | 1600 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 8176.64 | B | PD | BPD2013 | B1.2.3.4.12013 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2013 | 0 | 32 | 0 | 16 | 0 | 3200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
ITEM 80/20 Hardware | Contract | 2 | Units | 1200 | 2400 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 9776.64 | B | PD | BPD2013 | B1.2.3.4.12013 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2013 | 0 | 32 | 0 | 16 | 0 | 4800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Covers/Ducting | Acrylic/Lexan | 40 | lb | 20 | 800 | 0 | 32 | 0 | 8 | 0 | hours | 8009.28 | 2 | 9609.28 | B | PD | BPD2013 | B1.2.3.4.12013 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2013 | 0 | 64 | 0 | 16 | 0 | 1600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Rail Assembly Hardware Contingency | Contract | 2 | Units | 800 | 1600 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 8176.64 | C | PD | CPD2013 | C1.2.3.4.12013 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 32 | 0 | 16 | 0 | 3200
ITEM 80/20 Hardware Contingency | Contract | 2 | Units | 1200 | 2400 | 16 | 16 | 0 | 8 | 0 | hours | 8242.56 | 2 | 13042.56 | C | PD | CPD2013 | C1.2.3.4.12013 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 32 | 32 | 0 | 16 | 0 | 4800
Covers/Ducting Contingency | Acrylic/Lexan | 40 | lb | 20 | 800 | 16 | 32 | 0 | 8 | 0 | hours | 11275.2 | 2 | 12875.2 | C | PD | CPD2013 | C1.2.3.4.12013 | 1.2.3.4.1 | Detector Half Enclosure | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 32 | 64 | 0 | 16 | 0 | 1600
Detector Assembly (Engineering) | [10 empty] | Sum | 17962.56 | Sum
Engineering Oversight | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 80 | 0 | hours | 19440 | 2 | 19440 | B | PD | BPD2012 | B1.2.3.4.22012 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2012 | 0 | 0 | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Handling Fixtures | Aluminum | 150 | lb | 8 | 1200 | 40 | 160 | 0 | 60 | 0 | hours | 26535.6 | 1 | 27735.6 | B | PD | BPD2012 | B1.2.3.4.22012 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2012 | 40 | 160 | 0 | 60 | 0 | 1200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware (Bearings, Fasteners et-al) | Contract | 1 | Order | 1000 | 1000 | 0 | 8 | 0 | 0 | 0 | hours | 758.16 | 1 | 1758.16 | B | PD | BPD2012 | B1.2.3.4.22012 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2012 | 0 | 8 | 0 | 0 | 0 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
D-Tube (W/Sectors) Mount on Hinges | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 9953.28 | 2 | 9953.28 | B | PD | BPD2012 | B1.2.3.4.22012 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2012 | 0 | 64 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Card Cage Assembly (and Termination) | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 9953.28 | 2 | 9953.28 | B | PD | BPD2012 | B1.2.3.4.22012 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2012 | 0 | 64 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 4976.64 | B | PD | BPD2012 | B1.2.3.4.22012 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2012 | 0 | 32 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Detector Assembly (Production) | [10 empty] | Sum | 71616.96 | Sum
D-Tube (W/Sectors) Mount on Hinges | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 9953.28 | 2 | 9953.28 | B | PD | BPD2013 | B1.2.3.4.22013 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2013 | 0 | 64 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Card Cage Assembly (and Termination) | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 9953.28 | 2 | 9953.28 | B | PD | BPD2013 | B1.2.3.4.22013 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2013 | 0 | 64 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Assembly | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 4976.64 | B | PD | BPD2013 | B1.2.3.4.22013 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2013 | 0 | 32 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
D-Tube (W/Sectors) Mount on Hinges Spare | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 9953.28 | 2 | 9953.28 | B | PD | BPD2014 | B1.2.3.4.22014 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2014 | 0 | 64 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Card Cage Assembly (and Termination) Spare | Labor | 0 | N/A | 0 | 0 | 0 | 32 | 0 | 16 | 0 | hours | 9953.28 | 2 | 9953.28 | B | PD | BPD2014 | B1.2.3.4.22014 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2014 | 0 | 64 | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Assembly Spare | Labor | 0 | N/A | 0 | 0 | 0 | 16 | 0 | 8 | 0 | hours | 4976.64 | 2 | 4976.64 | B | PD | BPD2014 | B1.2.3.4.22014 | 1.2.3.4.2 | Half Detector Assembly | [5 empty] | 2014 | 0 | 32 | 0 | 16 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation Platforms (In-Situ) | [10 empty] | Sum | 49766.4 | Sum
Integration into STAR | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | B | PD | BPDSTAR | B1.2.5.1.1STAR | 1.2.5.1.1 | Work Platform | [5 empty] | STAR | 0 | 0 | 0 | 120 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Effort Required for Fabrication | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 160 | 0 | hours | 19440 | 1 | 19440 | B | PD | BPD2012 | B1.2.5.1.12012 | 1.2.5.1.1 | Work Platform | [5 empty] | 2012 | 0 | 0 | 0 | 160 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Integration into STAR (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 120 | 0 | hours | 14580 | 1 | 14580 | C | PD | CPDSTAR | C1.2.5.1.1STAR | 1.2.5.1.1 | Work Platform | [5 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 120 | 0 | 0
Design Effort Required for Fabrication (Contingency) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 160 | 0 | hours | 19440 | 1 | 19440 | C | PD | CPD2012 | C1.2.5.1.12012 | 1.2.5.1.1 | Work Platform | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 160 | 0 | 0
Fabrication | Aluminum | 2000 | lb | 8 | 16000 | 40 | 80 | 0 | 40 | 0 | hours | 16524 | 1 | 32524 | B | PD | BPD2012 | B1.2.5.1.12012 | 1.2.5.1.1 | Work Platform | [5 empty] | 2012 | 40 | 80 | 0 | 40 | 0 | 16000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation into STAR | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 8650.8 | B | PD | BPDSTAR | B1.2.5.1.1STAR | 1.2.5.1.1 | Work Platform | [5 empty] | STAR | 0 | 40 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware | Contract | 1 | Order | 2000 | 2000 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 4916 | B | PD | BPD2012 | B1.2.5.1.12012 | 1.2.5.1.1 | Work Platform | [5 empty] | 2012 | 0 | 0 | 0 | 24 | 0 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Pixel Insertion (In Situ) | [10 empty] | Sum | 62110.8 | Sum
Installation (Engineering Run) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 8650.8 | B | PD | BPD2013 | B1.2.5.1.22013 | 1.2.5.1.2 | Detector Installation | [5 empty] | 2013 | 0 | 40 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation (Engineering Run) (STAR Contributed) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 8650.8 | B | PD | BPDSTAR | B1.2.5.1.2STAR | 1.2.5.1.2 | Detector Installation | [5 empty] | STAR | 0 | 40 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Modifications | Aluminum | 100 | lb | 8 | 800 | 40 | 60 | 0 | 40 | 0 | hours | 14628.6 | 1 | 15428.6 | B | PD | BPD2013 | B1.2.5.1.22013 | 1.2.5.1.2 | Detector Installation | [5 empty] | 2013 | 40 | 60 | 0 | 40 | 0 | 800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Hardware (Bearings, Fasteners et-al) | Contract | 1 | Order | 2000 | 2000 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 3944 | B | PD | BPD2013 | B1.2.5.1.22013 | 1.2.5.1.2 | Detector Installation | [5 empty] | 2013 | 0 | 0 | 0 | 16 | 0 | 2000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation (2013) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 8650.8 | B | PD | BPD2014 | B1.2.5.1.22014 | 1.2.5.1.2 | Detector Installation | [5 empty] | 2014 | 0 | 40 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Installation (2013) (STAR Contributed) | Labor | 0 | N/A | 0 | 0 | 0 | 40 | 0 | 40 | 0 | hours | 8650.8 | 1 | 8650.8 | B | PD | BPDSTAR | B1.2.5.1.2STAR | 1.2.5.1.2 | Detector Installation | [5 empty] | STAR | 0 | 40 | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Modifications | Aluminum | 100 | lb | 8 | 800 | 40 | 60 | 0 | 40 | 0 | hours | 14628.6 | 1 | 15428.6 | C | PD | CPD2014 | C1.2.5.1.22014 | 1.2.5.1.2 | Detector Installation | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 60 | 0 | 40 | 0 | 800
Hardware (Bearings, Fasteners et-al) | Contract | 1 | Order | 2000 | 2000 | 0 | 0 | 0 | 16 | 0 | hours | 1944 | 1 | 3944 | C | PD | CPD2014 | C1.2.5.1.22014 | 1.2.5.1.2 | Detector Installation | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 16 | 0 | 2000
Service Termination | [10 empty] | Sum | 51175.8 | Sum
Design Effort As-Built Services | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 2916 | B | PD | BPDSTAR | B1.2.5.1.3STAR | 1.2.5.1.3 | Service Termination | [5 empty] | STAR | 0 | 0 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Service Termination (Engineering) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 1730.16 | B | PD | BPD2013 | B1.2.5.1.32013 | 1.2.5.1.3 | Service Termination | [5 empty] | 2013 | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Service Termination (Engineering) (STAR Contributed) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 1730.16 | B | PD | BPDSTAR | B1.2.5.1.3STAR | 1.2.5.1.3 | Service Termination | [5 empty] | STAR | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Design Effort As-Built Services (Final) | Labor | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 24 | 0 | hours | 2916 | 1 | 2916 | B | PD | BPDSTAR | B1.2.5.1.3STAR | 1.2.5.1.3 | Service Termination | [5 empty] | STAR | 0 | 0 | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Service Termination (2013) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 1730.16 | B | PD | BPD2014 | B1.2.5.1.32014 | 1.2.5.1.3 | Service Termination | [5 empty] | 2014 | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Service Termination (2013) (STAR Contributed) | Labor | 0 | N/A | 0 | 0 | 0 | 8 | 0 | 8 | 0 | hours | 1730.16 | 1 | 1730.16 | B | PD | BPDSTAR | B1.2.5.1.3STAR | 1.2.5.1.3 | Service Termination | [5 empty] | STAR | 0 | 8 | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Fabrication (Production) | Aluminum | 40 | lb | 8 | 320 | 24 | 24 | 0 | 8 | 0 | hours | 22783.68 | 4 | 24063.68 | B | PD | BPD2013 | B1.2.5.1.32013 | 1.2.5.1.3 | Service Termination | [5 empty] | 2013 | 96 | 96 | 0 | 32 | 0 | 1280 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Bulkhead Fabrication (Contingency) | Aluminum | 40 | lb | 8 | 320 | 24 | 24 | 0 | 8 | 0 | hours | 11391.84 | 2 | 12031.84 | C | PD | CPD2014 | C1.2.5.1.32014 | 1.2.5.1.3 | Service Termination | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 48 | 48 | 0 | 16 | 0 | 640
Level Subtotal | [11 empty] | 312663.24 | Base Labor | [13 empty] | 280 | 1372 | 0 | 1268 | 0 |  | 43480 | 356143.24 |  | 99518.84 | 152 | 236 | 0 | 400 | 0 |  | 13040
[11 empty] | Sum | 35536.32 | Sum
Shipping (Engineering Run)
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 80 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 80 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 200 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 30 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 947.7 | 2 | 1247.7 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 10 | 0 | 0 | 0 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 816.48 | 2 | 916.48 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 8 | 0 | 0 | 0 | 0 | 100 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 1516.32 | 2 | 1516.32 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 16 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 2 | 3000 | B | PD | BPD2012 | B1.2.12012 | 1.2.1 | Pixel Mechanics | [5 empty] | 2012 | 0 | 0 | 0 | 0 | 0 | 3000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping (Final Production) | [10 empty] | Sum | 3280.5 | Sum
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 160 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 400 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 60 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 60 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 1895.4 | 4 | 2495.4 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 0 | 20 | 0 | 0 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 1632.96 | 4 | 1832.96 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 16 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 3032.64 | 4 | 3032.64 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 6000 | B | PD | BPD2013 | B1.2.12013 | 1.2.1 | Pixel Mechanics | [5 empty] | 2013 | 0 | 0 | 0 | 0 | 0 | 6000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping (Final Production) | [10 empty] | Sum | 6561 | Sum
-Handles | Galvanized | 4 | ea. | 10 | 40 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 160 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 160 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Sides | 1" Plywood | 1 | sheets | 100 | 100 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 400 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Fork Truck Skids | Fir 4X4 | 5 | bd/ft | 3 | 15 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 60 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 60 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Box Fab--Carpenters not MT, but cost scaled | 1" Plywood | 1 | sheets | 150 | 150 | 0 | 5 | 0 | 0 | 0 | hours | 1895.4 | 4 | 2495.4 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 0 | 20 | 0 | 0 | 0 | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing Foam (waterjet parts) | Foam | 1 | m^3 | 50 | 50 | 4 | 0 | 0 | 0 | 0 | hours | 1632.96 | 4 | 1832.96 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 16 | 0 | 0 | 0 | 0 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Packing | Labor |  |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | hours | 3032.64 | 4 | 3032.64 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 0 | 32 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
-Shipping Cost | Unit | 1 |  | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | hours | 0 | 4 | 6000 | B | PD | BPD2014 | B1.2.12014 | 1.2.1 | Pixel Mechanics | [5 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 6000 |  | Base |  | Contingency | 0 | 0 | 0 | 0 | 0 | 0
Shipping Subtotal | [11 empty] | 26244 | Base Labor | [13 empty] | 40 | 130 | 0 | 0 | 0 |  | 3710 | 20112.5 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[25 empty] | 0 |  | 1932.25 | 4749 | 620 | 4685 | 16 |  | 144282 |  |  |  | 1311.25 | 1422 | 156 | 1528 | 0 |  | 57757
[27 empty] | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost |  |  |  | Shop Time | MT Time | CMM | Engineering | Design |  | M&S Cost
[26 empty] | Checksum | 1932.25 | 4749 | 620 | 4685 | 16 |  | 144282 |  |  |  | 1311.25 | 1422 | 156 | 1528 | 0 |  | 57757 | Checksum
[32 empty] | Cost With Contingency | 1953594.34 | 1976466.985 |  | Contributed Labor Excluded…
Description | WBS | [12 empty] | 2009 | B |  |  |  | 1.2.1.1.1 | 0 | 0 | 0 | 2009
Pixel Mechanics | 1.2.1 | <-- Copy Down from this Cell both columns A and B to update WBS list | [11 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | BASE | [9 empty] | CONTINGENCY
Module Support (Sector) | 1.2.1.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
Sector Mechanical Prototypes | 1.2.1.1.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0
Production Sectors | 1.2.1.1.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2010 | 234 | 721 | 108 | 1115 | 0 | 31556.5 |  |  |  | 2010 | 48 | 32 | 0 | 12 | 0 | 153
D-Tube and Kinematic Mounts | 1.2.1.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2011 | 224 | 787 | 96 | 1140 | 0 | 22027.5 |  |  |  | 2011 | 215.75 | 124 | 64 | 318 | 0 | 28945
Prototype D-Tube | 1.2.1.2.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 694.75 | 1021 | 124 | 1135 | 16 | 48703.5 |  |  |  | 2012 | 226 | 356 | 60 | 454 | 0 | 1820
Prototype Kinematic Mounts | 1.2.1.2.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2013 | 763.5 | 1804 | 252 | 843 | 0 | 49654.5 |  |  |  | 2013 | 733.5 | 802 | 32 | 552 | 0 | 23639
[26 empty] | 2014 | 16 | 280 | 40 | 148 | 0 | 7420 |  |  |  | 2014 | 88 | 108 | 0 | 72 | 0 | 3440
Production D-Tube and Kinematic Mounts | 1.2.1.2.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | CONT | 0 | 0 | 0 | 0 | 0 | 0
Insertion Mechanism and Internal Service Supports | 1.2.1.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | STAR | 0 | 136 | 0 | 304 | 0 | 0 |  |  |  | STAR | 0 | 0 | 0 | 120 | 0 | 0
Thermal Prototype | 1.2.1.3.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Project Estimated Cost | [9 empty] | Project Estimated Contingency
Insertion Test Bed | 1.2.1.3.2 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
Prototype Insertion Mechanism | 1.2.1.3.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production Insertion Mechanism | 1.2.1.3.4 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2010 | 28526.4 | 82445.22 | 12267.36 | 164029.5 | 0 | 31556.5 | 318824.98 |  |  | 2010 | 6048 | 3744 | 0 | 1800 | 0 | 153 | 11745
Prototype Patch Panel Bulkhead | 1.2.1.3.5 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  |  |  | 2009 |  |  | 2011 | 25925.76 | 83164.77 | 10563.84 | 165300 | 0 | 22027.5 | 306981.87 |  |  | 2011 | 23838.885 | 13707.72 | 6914.88 | 42057 | 0 | 28945 | 115463.485
Production Patch Panel Bulkhead | 1.2.1.3.6 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2012 | 71833.86 | 96804.63 | 12655.44 | 139612.5 | 1620 | 48703.5 | 371229.93 |  |  | 2012 | 23065.56 | 33738.12 | 6123.6 | 56301 | 0 | 1820 | 121048.28
[26 empty] | 2013 | 78305.85 | 171009.54 | 25719.12 | 102424.5 | 0 | 49654.5 | 427113.51 |  |  | 2013 | 75244.05 | 76050 | 3265.92 | 68208 | 0 | 23639 | 246406.97
Detector Assembly | 1.2.3 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 |  |  | 2014 | 1632.96 | 26535.6 | 4082.4 | 17982 | 0 | 7420 | 57652.96 |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sector Assembly | 1.2.3.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [8 empty] | Base Cost | 1481803.25 | [8 empty] | Contingency | 494663.735
Mechanical Sector Assemblies | 1.2.3.1.1 | [12 empty] | 2009 | B |  |  |  | 1.2.1 |  | 0 | 0 | 2009 | [18 empty] | Percent | 33.38%
Electrical Sector Assemblies | 1.2.3.1.2
D-Tube Assembly and Survey Tool | 1.2.3.2 | [25 empty] | Pre-Production Base Cost | [9 empty] | Pre-Production Contingency Cost
Sector Mount And Survey | 1.2.3.3 | [25 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
Final Assembly | 1.2.3.4 | [15 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0
Detector Half Enclosure | 1.2.3.4.1 | [15 empty] | BPT | [8 empty] | 2010 | 194 | 635 | 52 | 1002 | 0 | 21134 |  |  | CPT | 2010 | 48 | 32 | 0 | 12 | 0 | 153
Half Detector Assembly | 1.2.3.4.2 | [15 empty] | BPT | [8 empty] | 2011 | 128 | 386 | 32 | 940 | 0 | 7827.5 |  |  | CPT | 2011 | 76 | 88 | 16 | 120 | 0 | 1080
System Test | 1.2.3.5 | [15 empty] | BPT | [8 empty] | 2012 | 38.75 | 2 | 0 | 60 | 0 | 2285 |  |  | CPT | 2012 | 0 | 0 | 0 | 40 | 0 | 8
Installation | 1.2.5 | [15 empty] | BPT | [8 empty] | 2013 | 16 | 2 | 0 | 0 | 0 | 160 |  |  | CPT | 2013 | 16 | 2 | 0 | 40 | 0 | 160
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
Pixel Installation In-Situ | 1.2.5.1 | [15 empty] | BPT | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | CONT | 0 | 0 | 0 | 0 | 0 | 0
Work Platform | 1.2.5.1.1 | [15 empty] | BPT | [8 empty] | STAR | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPT | STAR | 0 | 0 | 0 | 0 | 0 | 0
Detector Installation | 1.2.5.1.2 | [25 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
Service Termination | 1.2.5.1.3 | [25 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
Pixel Auxiliary Acess | 1.2.5.2 | [15 empty] | BPT | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work Platform | 1.2.5.2.1 | [15 empty] | BPT | [8 empty] | 2010 | 24444 | 74295 | 6552 | 150300 | 0 | 21134 | 276725 |  | CPT | 2010 | 6048 | 3744 | 0 | 1800 | 0 | 153 | 11745
Detector Installation | 1.2.5.2.2 | IF need to copy below this line to contain WBS, need to update Data Validation for cells in column "U" (WBS) AND 'Look Up' vectors for Column "V" (Descriptor) | [14 empty] | BPT | [8 empty] | 2011 | 16128 | 45162 | 4032 | 141000 | 0 | 7827.5 | 214149.5 |  | CPT | 2011 | 9576 | 10296 | 2016 | 18000 | 0 | 1080 | 40968
Service Termination | 1.2.5.2.3 | [15 empty] | BPT | [8 empty] | 2012 | 4882.5 | 234 | 0 | 9000 | 0 | 2285 | 16401.5 |  | CPT | 2012 | 0 | 0 | 0 | 6000 | 0 | 8 | 6008
[17 empty] | BPT | [8 empty] | 2013 | 2016 | 234 | 0 | 0 | 0 | 160 | 2410 |  |  | 2013 | 2016 | 234 | 0 | 6000 | 0 | 160 | 8410
[17 empty] | BPT | [8 empty] | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPT | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 509686 | [8 empty] | Contingency | 67131
[42 empty] | Percent | 13.17%
[27 empty] | Production Base Cost | [9 empty] | Production Contingency Cost
[27 empty] | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost |  |  |  |  | Shop Time | MT Time | CMM | Engineering | Design | M&S Cost
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 40 | 86 | 56 | 113 | 0 | 10422.5 |  |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 96 | 401 | 64 | 200 | 0 | 14200 |  |  | CPD | 2011 | 139.75 | 36 | 48 | 198 | 0 | 27865
[17 empty] | BPD | [8 empty] | 2012 | 656 | 1019 | 124 | 1075 | 16 | 46418.5 |  |  | CPD | 2012 | 226 | 356 | 60 | 414 | 0 | 1812
[17 empty] | BPD | [8 empty] | 2013 | 747.5 | 1802 | 252 | 843 | 0 | 49494.5 |  |  | CPD | 2013 | 717.5 | 800 | 32 | 512 | 0 | 23479
[17 empty] | BPD | [8 empty] | 2014 | 16 | 280 | 40 | 148 | 0 | 7420 |  |  |  | 2014 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | CONT | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CPD | CONT | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | STAR | 0 | 136 | 0 | 304 | 0 | 0 |  |  | CPD | STAR | 0 | 0 | 0 | 120 | 0 | 0
[27 empty] | Project Estimated Cost | [9 empty] | Project Estimated Cost
[27 empty] | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals |  |  |  | Shop Cost | MT Cost | CMM | Engineering | Design | M&S Cost | Totals
[17 empty] | BPD | [8 empty] | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CPD | 2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2010 | 4082.4 | 8150.22 | 5715.36 | 13729.5 | 0 | 10422.5 | 42099.98 |  | CPD | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | BPD | [8 empty] | 2011 | 9797.76 | 38002.77 | 6531.84 | 24300 | 0 | 14200 | 92832.37 |  | CPD | 2011 | 14262.885 | 3411.72 | 4898.88 | 24057 | 0 | 27865 | 74495.485
[17 empty] | BPD | [8 empty] | 2012 | 66951.36 | 96570.63 | 12655.44 | 130612.5 | 1620 | 46418.5 | 354828.43 |  | CPD | 2012 | 23065.56 | 33738.12 | 6123.6 | 50301 | 0 | 1812 | 115040.28
[17 empty] | BPD | [8 empty] | 2013 | 76289.85 | 170775.54 | 25719.12 | 102424.5 | 0 | 49494.5 | 424703.51 |  |  | 2013 | 73228.05 | 75816 | 3265.92 | 62208 | 0 | 23479 | 237996.97
[17 empty] | BPD | [8 empty] | 2014 | 1632.96 | 26535.6 | 4082.4 | 17982 | 0 | 7420 | 57652.96 |  | CPD | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | Base Cost | 972117.25 | [8 empty] | Contingency | 427532.735
[42 empty] | Percent | 43.98%

## Rates
Values below used only for reference--not linked to data in sheet estimate…
| Construction | R&D |  | English | Metric | Quoted |  | Metric
Shop | 102.06 | 126 | Material | lb/in^3 | g/cc | Cost/Unit | Unit | Cost/Unit | Unit
CMM | 102.06 | 126 | Aluminum | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
M_Tech | 94.77 | 117 | MIC-6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
Engineer | 121.5 | 150 | 6061-T6 | 0.098 | 2.7151 | 8 | $/lb | 0.016529 | $/g
Designer | 101.25 | 125 | 7075-T6 | 0.098 | 2.7151 | 10 | $/lb | 0.020661 | $/g
|  |  | Titanium | 0.198 | 5.4855 | 15 | $/lb | 0.030992 | $/g
Construction Rate does not have full Burden--currently ~81% (below) of Full Burden at LBNL (R&D Rate) |  |  | 6Al4V | 0.198 | 5.4855 | 20 | $/lb | 0.041322 | $/g
|  |  | Steel | 0.298 | 8.256 | 3 | $/lb | 0.0061983 | $/g
|  |  | 304SS | 0.298 | 8.256 | 15 | $/lb | 0.030992 | $/g
|  |  | Carbon Fiber | 0.065 | 1.8008 | 100 | $/lb | 0.20661 | $/g
Differential | 81% |  | M55J-UDT | 0.065 | 1.8008 | 800 | $/lb | 1.6529 | $/g
Change This to change burden rate… |  |  | CN60-PW | 0.065 | 1.8008 | 500 | $/lb | 1.0331 | $/g
|  |  | YSH80A-UDT | 0.065 | 1.8008 | 1200 | $/lb | 2.4793 | $/g
|  |  | Adhesive | 0.055 | 1.5238 | 400 | $/qt | 0.42283 | $/cc
|  |  | EA9396 | 0.055 | 1.5238 | 350 | $/qt | 0.36998 | $/cc
|  |  | EA9394 | 0.075 | 2.0779 | 450 | $/qt | 0.47569 | $/cc
|  |  | CF HoneyComb | 0.0017361 | 0.048099 | 600 | $/bdft | 0.25424 | $/cc
|  |  | Al HoneyComb | 0.0017361 | 0.048099 | 75 | $/bdft | 0.03178 | $/cc
|  |  | Nomex HC | 0.0023148 | 0.064131 | 100 | $/bdft | 0.042373 | $/cc
|  |  | PEEK | 0.055 | 1.5238 | 400 | $/lb | 0.82645 | $/g
|  |  | CF PEEK | 0.055 | 1.5238 | 600 | $/lb | 1.2397 | $/g

## Material Estimates
Material Estimates per component |  |  | Values used to estimate Size/Cost of Batch Orders--Does not report to Cost Summary
Item | Material | Descriptor | Quantity | CPT (microns) | Density (g/cc) | Finished Form | % Waste | Length (cm) | Diameter/Width (cm) | Thickness (cm) | Volume (cc) | Mass (g) | Pre-Preg Area (m^2) | Cost Per Unit | Choose Unit | Cost | Prototype Mass | Prototype Area | Prototype Composites
Material Volumes | [19 empty] | /cc | Bulk | 1
D-Tube | [19 empty] | /g | Plate | 2
Tooling | [19 empty] | /m^2 | Round | 3
Mandrel | Steel | Pipe | 1 | n/a | 8.3 | Shell | 0% | 60 | 20 | 1.5 | 5654.8668 | 46935.3942 | #VALUE! | 0.006 | /g | 281.6124 | 0 | 0 | 0 |  | Shell | 4
Mandrel End Plates | Steel | Plate | 1 | n/a | 8.3 | Plate | 0% | 60 | 25 | 3 | 4500 | 37350 | #VALUE! | 0.006 | /g | 224.1 | 0 | 0 | 0
D-Tube Bond Tool
Tooling
Support Beam Tool | Aluminum | Plate | 1 | n/a | 2.7 | Plate | 0% | 100 | 30 | 3 | 9000 | 24300 | #VALUE! | 0.017 | /g | 413.1 | 0 | 0 | 0
Support Beam Machining Tool | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 0% | 30 | 15 | 5 | 4500 | 12150 | #VALUE! | 0.017 | /g | 206.55 | 0 | 0 | 0
Components | [11 empty] | 80.2863
Thick Laminate | CN60 Cloth | Laminate | 5 | 330 | 1.8 | Plate | 30% | 80 | 2.5 | 0.8 | 1040 | 1872 | 3.1515 | 1.033 | /g | 1933.776 | 0 | 0 | 0
Thick Laminate Test | CN60 Cloth | Test | 2 | 330 | 1.8 | Plate | 50% | 20 | 3 | 0.8 | 144 | 259.2 | 0.43636 | 1.033 | /g | 267.7536 | 259.2 | 0.43636 | 267.7536
Insertion Test Bed
Support Components
Item Bars | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 250 | 7.5 | 7.5 | 73125 | 197437.5 | #VALUE! | 0.017 | /g | 3356.4375 | 0 | 0 | 0
Station Plates | Aluminum | Plate | 3 | n/a | 2.7 | Plate | 30% | 50 | 50 | 5 | 48750 | 131625 | #VALUE! | 0.017 | /g | 2237.625 | 0 | 0 | 0
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Iteration | [11 empty] | 840.7764 |  |  |  | 6489.1125
Kinematic Support Bars | Aluminum | Plate | 2 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 6500 | 17550 | #VALUE! | 0.017 | /g | 298.35 | 0 | 0 | 0
Rail Insert Supports | Aluminum | Plate | 4 | n/a | 2.7 | Plate | 30% | 50 | 10 | 5 | 13000 | 35100 | #VALUE! | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Prototype | [11 empty] | 115.9692 |  |  |  | 895.05
Cart Rail Rider prototype | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 50 | 20 | 10 | 13000 | 35100 | 39.3939 | 0.017 | /g | 596.7 | 0 | 0 | 0
Low Mass Cart | [11 empty] | 154.6256 |  |  |  | 1193.4
Cart Rail Rider | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Cart Rail Rider iteration | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 10 | 20 | 10 | 2600 | 7020 | 7.8788 | 0.017 | /g | 119.34 | 0 | 0 | 0
Tooling | Aluminum | Plate | 1 | 330 | 2.7 | Plate | 30% | 60 | 30 | 5 | 11700 | 31590 | 35.4545 | 0.017 | /g | 537.03 | 0 | 0 | 0