## Sheet1
2003-05-21
Mechanics Priority List
Category |  | Priority | Reported by | Status:
Other
| Services FDR preparation | A | All | Interspersed below in other sections.
| Beam test plate fab | Done | Anmol
| Beam test plate cut | In progress | Maurice
Sectors
| Make hardening work | Done | Jon, Tom, Tom
| Bend tubes/harden | In progress | Tom J | 60 tubes hardened and bent, at least 40 "good ones", all but 6 have strain reliefs attached.
| 2nd sector for system test | Done | Tom J, Tom W
| Modify holders for tube welding | Done | Tom J, Tom W
| Modify strain reliefs | In progress | Tom J | Need to re-anodize 1 batch, but this is for the second batch of 40 tubes, and doesn't hold up anything now.
| 3rd sector with prod tube, destruct test | Done
| Welding results/tests | Done for now
| Bond foam to faceplates | A | Tom J | Jon in process of cutting cyanate-ester during meeting. Jon was cutting foam yesterday.
| Order CGL | Done | Jon
| Order cyanate ester | Done | Jon
| Tooling for module mounting | A | Fred | Fred: "…dropping modules; will get better."
| Locations of modules on sector | Done | Maurice, Fred
| Tolerances for module placement | Done | Gil, Maurice |  | For now, 25 microns
| Sector frame | A | Fred | Now part of tooling
| Prepare for laser welding May 2 | Done | Jon, Tom, Neal
| Next shipment to EB for May 21 or so | Done? | Tom J, Neal | Shipment ready, waiting for quote from EB that shows hourly rates so we can make blanket order and send parts with PO. Promised by EB today, but as of writing has not been received.
Frame
| Get endplate tooling to Allcomp | Done | Jon, Tom
| Follow Allcomp work | Done | Gil
| 1st fit-up and dimension check | Done | Jon, Gil
| Fix endplates | Done | Jon
| Sand sections flat | A | Tom J | No status update from Jon. Assumed no progess made.
| Revise pinning scheme | A | Tom J | No status update from Jon. Assumed no progess made.
| Bond tubes barrel to end sections | B | Jon, Gil
| Send Fred drawing of ring locations | Done | Gil
PST and related
| Rapid prototype samples | Done | Eric
| Shear strength samples | A | Neal | In process of bonding specimens together. Should be tested by next week.
| Irradiate samples | Done | Tom W
| Order production material | Done | Neal, Eric
| Heater prototypes | Done | Alexis, Maurice
| Analysis of irradiated samples | Done
| Allied PO | Done | Neal
| Mandrel status | A | Neal | Mandrel is being finished. It looks like we have found a nickel plater in Fremont, so plating will be done there.
| CTE samples/measurements | Done | Neal | Drawing updated and sent to Allied, attached to PO.
| Material Delivery/Freezer |  | Neal | Material is being sent next Tuesday, should arrive Wednesday. Freezer should be running again by end of the week, after electrical work completed.
Beam pipe support/service panels
| Adjustor prototype fabrication drawings | Done | Uken
| Fabricate prototype adjustor | Done | In shops
| Update support model | Done | Uken, Eric, Neal
| Revise service panel model/drawings | Ongoing | Eric | Eric and Alexis integrating models on Friday for meeting with Dave Uken on Tuesday. Eric is looking at hinging service panel in order to make assembly/access easier.
| Trolley design | Ongoing | Alexis | Ibid.
| PP0 prototype | A | Maurice | Done. Waiting for more parts of panel in order to do anything else.
| April FDR documentation | Done | et al
| Simple mockup, cable lengths | A | Maurice | Cable situation is a "wake-up call". Wire bundles too stiff. Maurice has ordered samples of kapton, silicone, and PE tubing to try as alternates to the heatshrink stuff. Eric and Neal favor "ribbonizing" cables with adhesive, manually. Maurice looking at smaller power wires to ease situation, and wants to investigate new PP0 layout that would make cable lengths all equal.
PP1
| Dimensioned drawings for fab | Done | Fred
| Mechanical fabricate prototype | In progress | Fred | PP1 not done, won't be ready for gas testing for a while. Some inserts have been incorporated into plate, but bellows have not been quoted yet.
| Fabricate electrical feedthroughs | Done? | Maurice | 1 set has been done. Looks good (heavy!). Other set being completed. Wires will be sent to CERN for inclusion in Jocelyn's mockup soon.
| Solder wires to feedthroughs | A |  | Ibid.
| Beam pipe attach for services FDR | A | Fred | Has not been tackled yet, if this means the "can" to the beampipe from the PP1 ID.
| Prototype cooling fittings | Done | Fred, Ron
| Test prototype cooling fittings | A | Tom W | All 4 test in 9/10 scale. One sample that cracked was re-welded and performs admirably. Testing regimen has been completed up to the thermal cycling stage. Tom is ready to do this soon.
| Revise material estimate | Done | Ron | 1st pass
| Material options | Ongoing | Ron | Eric/Neal advised Ron of possible addition of stainless filters/pressure drop devices to the PP1 region, as well as of need to include the beampipe adjustors in material estimate. Eric will provide Ron with specifics of mass and volume.
Cooling tubes
| Respond to proposed evap changes | Done | Gil
| Long capillary status | A | Eric, Neal | We are proposing a baseline system with no changes from the original cooling circuit, except that there will be a pressure drop device included with the filter at PP1. This will allow the possibility of dropping system pressure from 16 to 8 bar before the capillary. We need to build and test the parallel heat exchanger, and add loops around exhaust if necessary. We will use the same capillary as proposed before. Fred is going to work on how to incorporate the pressure drop device into the inlet tube fittings at PP1. Ron will include the mass of these devices into the material estimate.
| EB capillary results | Done