## Slide 1
Fabrication Update – The Frame Awakens
Matt Hoff LBNL April 2, 2015

## Slide 2
Water jet cut small pieces
Machining details
Full welds on this half of the frame
No welds this half yet
Photo taken 4/1/2015

## Slide 3
Machining Details
LBNL’s two best welders

## Slide 4
2 of 4 temporary strut mounting blocks
100 Bal Seal canted spring rings for the slug tuners
Parts are being fabricated and off the shelf items are arriving

## Slide 5
All 4 temporary strut supports
Temp strut mounts in model

## Slide 6
End Machining
This picture is Module 4 getting the ends trimmed for a vacuum check
Module 1 and 2 are scheduled for final end machining starting Friday April 3, 2015. This should be fast. This is the final machining step in the copper.
Module 3 will follow after Module 4 is leak tight. Then finally Module 4.

## Slide 7
Summary
Support Frame fabrication is progressing at a good rate. On schedule.
Other pieces needed for assembly are in progress.
Some off the shelf items have started to arrive.
Module end machining starts Friday April 3.
FNAL has a copy of LBNL’s CAD model