## GENERAL INSTRUCTION
This project budget workbook template has been provided to aid you in creating a project cost estimate.
BASELINE ESTIMATE WORKSHEET
In general, the "Baseline Estimate" worksheet tab will in all likelihood be the first worksheet to be used.
This template contains an example of a single WBS level 2 entry with the the recommended way to display the WBS lower levels .
Your estimate will likely contain many level 3 sections and items at levels 3, 4 and 5. You may insert rows, and either copy or AutoFill the formulas as needed to add additional sections.
Check and double check the added row formulas and column sums!
When not using a line to provide detailed cost information, delete the formulas/info on that particular line.
Specific Column Info:
"Cost Basis"- Options: ose = outside shop estimate cp = catalog price se = on-site shop estimate vq = vendor quote eu = estimate undocumented pe = previous experience
"Unit Cost" - This column should have the estimated $ amount listed. (Not in $K)
"Craft Code" - By entering the craft code of the correct labor type required for a task (found on the "FY07 Craft Rates" worksheet column B "Code". This sheet will be updated by the ALS Planning Office as needed.) the appropriate "Labor Rate $/Hr" column will be filled in for you.
"Overhead Total" - The overhead will be calculated automatically based on the current rates on the "Overhead" worksheet. These rates will be updated as needed by the ALS Planning Office.
"Contng %" - The contingency percentage should be filled in for each item. The cells are already formatted as a percentage. The total project contingency percentage will self-calculate.

## Overhead
Expense type | Effective Rate | Procurement Burden | IGPP | LDRD | Fab | General
|  | 10% | 1.15% | 5.4% | 29.2% | 51%
Fab Procurements | 13.11%
Fab Labor | 31.1%
Ops Procurements | 22%
Ops Labor | 58%
Note on A9: SLRossi: Not a calc, backed into
Note on A11: SLRossi: Not a calc, backed into

## LaborRates
Resource |  |  | Labor Rates
| Code | FY08 Base Hourly w/ Payroll Burden (44.8%) | Plus 17.5% EG/ 18.5% FA Bdn | CAD/Shop Charges | Rate Used in Template (Not including Fab or General Rate) | With Fab Rate (29.2%) | With General Rate, LDRD Tax, and IGPP (Effective 54.75%)
Computer Programmer | CP | 85.77 | 100.7798 |  | 100.7798 | 130.2074 | 155.9567
Electronic Coordination | EC | 68.07 | 79.9822 | 3.8 | 83.7823 | 108.2467 | 129.653
Electronic Engineering | EE | 70.69 | 83.0607 | 3.8 | 86.8607 | 112.2241 | 134.417
Senior Electronic Engineering (.5+) | SEE | 95.45 | 112.1538 | 3.8 | 115.9537 | 149.8122 | 179.4384
Electronic Installation | EI | 47.55 | 55.8713 |  | 55.8713 | 72.1857 | 86.4608
Electrician | EL | 55.44 | 65.6964 |  | 65.6964 | 84.8797 | 101.6652
Electronic Maintenance | EM | 47.55 | 55.8713 |  | 55.8713 | 72.1857 | 86.4608
M.E. Liason | LI | 63.74 | 74.8945 |  | 74.8945 | 96.7637 | 115.8992
Bldg. 77 Assembly Shop | MA | 49.9 | 58.6325 | 16.9 | 75.5325 | 97.588 | 116.8865
Mechanical Technician-Brazing | MB | 45.19 | 53.0983 | 16.9 | 69.9982 | 90.4377 | 108.3223
Mechanical Designer/Drafter | MD | 60.43 | 71.0053 | 3.8 | 74.8053 | 96.6484 | 115.7611
Mechanical Engineer | ME | 70.03 | 82.2853 | 3.8 | 86.0853 | 111.2221 | 133.2169
UHV Cleaning & Plating Shop | MP | 53.22 | 62.5335 | 16.9 | 79.4335 | 102.6281 | 122.9233
77 Machine Shops | MS | 53.22 | 62.5335 | 16.9 | 79.4335 | 102.6281 | 122.9233
Mechanical Technician | MU | 45.19 | 53.0983 |  | 53.0983 | 68.6029 | 82.1695
Mech. Tech/Assembly | MUA | 45.19 | 53.0983 |  | 53.0983 | 68.6029 | 82.1695
Mech. Tech./Installation | MUI | 45.19 | 53.0983 |  | 53.0983 | 68.6029 | 82.1695
Mech. Tech./Machine Shop | MUM | 49.68 | 58.374 |  | 58.374 | 75.4192 | 90.3338
Mech. Tech./Survey & Alignment | MUS | 47.83 | 56.2002 |  | 56.2002 | 72.6107 | 86.9699
Sheet Metal/Welding | SM | 52.57 | 61.7698 | 16.9 | 78.6697 | 101.6413 | 121.7414
Student | ST | 18.49 | 21.7258 | 3.8 | 25.5257 | 32.9793 | 39.5011
Post Doc | PD | 49.24 | 57.857 |  | 57.857 | 74.7512 | 89.5337
Carpenter Shop | CS | 48.26 | 57.1881 |  | 57.1881 | 73.887 | 88.4986
Paint Shop | PS | 48.94 | 57.9939 |  | 57.9939 | 74.9281 | 89.7456
Senior Mech Engineer (.5+) | SME | 97.63 | 114.7152 | 3.8 | 118.5152 | 153.1217 | 183.4023
Riggers | RG | 47.97 | 56.8445 |  | 56.8445 | 73.443 | 87.9668
Laborers | LBR | 35.74 | 42.3519 |  | 42.3519 | 54.7187 | 65.5396
Plumbers | PB | 51.35 | 60.8498 |  | 60.8498 | 78.6179 | 94.165
Facilities | FA | 125 | 148.125 |  | 148.125 | 191.3775 | 229.2234
Estimate Codes
previous experience | pe
outside shop estimate | ose
catalog price | cp
on-site shop estimate | se
vendor quote | vq
estimate undocumented | eu

## NEXT COST to BUILD
[6 empty] | MATERIAL |  |  |  |  | LABOR | [8 empty] | TOTALS
[6 empty] | Unit | Material | Cost | Unit | Total | Labor | Labor | Labor | Craft | Labor | Total | Total | Overhead | Sub | Cntng | Cntng | Totals
Description | [5 empty] | Meas | No. | Basis | Cost | Material | No. | Unit | Total | Code | Rate | Labor | Labor + | Total | Total | % | K$ | K$
[7 empty] | Units |  |  | K$ | Units | Hours | Hours |  | $/Hr. | K$ | Material
| 1 | NEXT Cost to build | [7 empty] | 337.26 |  |  | 7912 |  |  | 505.9194 | 848.3194 | 202.2296 | 1050.549 | 51.99% | 546.1558 | 1647.7512
|  | 1.1 |  |  | EDI |  |  |  |  | 0 |  |  | 1460 |  |  | 124.634 | 124.634 | 38.7612 | 163.3952 | 73.75% | 120.5105 | 283.9057
|  |  | 1.1.1 |  | Project Management |  |  | pe |  | 0 | 1 | 200 | 200 | ME | 86.0853 | 17.2171 | 17.2171 | 5.3545 | 22.5716 | 100% | 22.5716 | 45.1431
|  |  | 1.1.2 |  | WLS Tube Design |  |  | pe |  | 0 | 1 | 200 | 200 | ME | 86.0853 | 17.2171 | 17.2171 | 5.3545 | 22.5716 | 100% | 22.5716 | 45.1431
|  |  | 1.1.3 |  | Xenon Vessel Design |  |  | pe |  | 0 | 1 | 200 | 200 | ME | 86.0853 | 17.2171 | 17.2171 | 5.3545 | 22.5716 | 100% | 22.5716 | 45.1431
|  |  | 1.1.4 |  | Pressure Vessel Design |  |  | pe |  | 0 | 1 | 200 | 200 | ME | 86.0853 | 17.2171 | 17.2171 | 5.3545 | 22.5716 | 40% | 9.0286 | 31.6002
|  |  | 1.1.5 |  | Gas System Design |  |  | pe |  | 0 | 1 | 200 | 200 | ME | 86.0853 | 17.2171 | 17.2171 | 5.3545 | 22.5716 | 40% | 9.0286 | 31.6002
|  |  | 1.1.6 |  | Field Cage Design |  |  | pe |  | 0 | 1 | 100 | 100 | MD | 74.8053 | 7.4805 | 7.4805 | 2.3264 | 9.807 | 50% | 4.9035 | 14.7105
|  |  | 1.1.7 |  | Si PMT design |  |  | pe |  | 0 | 1 | 100 | 100 | EE | 86.8607 | 8.6861 | 8.6861 | 2.7014 | 11.3874 | 40% | 4.555 | 15.9424
|  |  | 1.1.8 |  | Shield Design |  |  | pe |  | 0 | 1 | 60 | 60 | ME | 86.0853 | 5.1651 | 5.1651 | 1.6064 | 6.7715 | 40% | 2.7086 | 9.4801
|  |  | 1.1.8 |  | Installation Planning and Design |  |  | pe |  | 0 | 1 | 200 | 200 | ME | 86.0853 | 17.2171 | 17.2171 | 5.3545 | 22.5716 | 100% | 22.5716 | 45.1431
|  | 1.2 |  |  | WLS Tube Assemblies |  |  |  |  | 196.24 |  |  | 1216 |  |  | 70.1002 | 266.3402 | 47.5282 | 313.8684 | 25.58% | 80.277 | 394.1454
1.2.1 Procurements
|  |  |  | 1.2.1.1 | Suprasil 310 tubes | lot | 100 | vq | 270 | 27 | [6 empty] | 27 | 3.5397 | 30.5397 | 15% | 4.581 | 35.1207
|  |  |  | 1.2.1.2 | WLS Bars | ea | 100 | eu | 400 | 40 | [6 empty] | 40 | 5.244 | 45.244 | 15% | 6.7866 | 52.0306
|  |  |  | 1.2.1.3 | PMTs | ea | 100 | eu | 500 | 50 | [6 empty] | 50 | 6.555 | 56.555 | 15% | 8.4832 | 65.0383
|  |  |  | 1.2.1.4 | Optical Transitions | ea | 100 | eu | 150 | 15 | [6 empty] | 15 | 1.9665 | 16.9665 | 15% | 2.545 | 19.5115
|  |  |  | 1.2.1.5 | lower end cap | lot | 100 | eu | 30 | 3 | [6 empty] | 3 | 0.3933 | 3.3933 | 20% | 0.67866 | 4.072
|  |  |  | 1.2.1.6 | upper plug | ea | 100 | eu | 30 | 3 | [6 empty] | 3 | 0.3933 | 3.3933 | 15% | 0.50899 | 3.9023
|  |  |  | 1.2.1.7 | grade ring | ea | 5700 | eu | 1 | 5.7 | [6 empty] | 5.7 | 0.74727 | 6.4473 | 15% | 0.96709 | 7.4144
|  |  |  | 1.2.1.7 | resistive stripe, monofilament WLS insertion guide, adhesive, etc. | ea | 100 | eu | 1 | 0.1 | [6 empty] | 0.1 | 0.01311 | 0.11311 | 15% | 0.016966 | 0.13008
|  |  |  | 1.2.1.8 | bellows tube | ea | 100 | eu | 20 | 2 | [6 empty] | 2 | 0.2622 | 2.2622 | 15% | 0.33933 | 2.6015
|  |  |  | 1.2.1.9 | instrument fitting | ea | 100 | eu | 20 | 2 | 80 | 0.25 | 20 | SM | 78.6697 | 1.5734 | 3.5734 | 0.75153 | 4.3249 | 15% | 0.64874 | 4.9737
|  |  |  | 1.2.1.10 | instrument fitting mate flange and clamp | ea | 100 | eu | 20 | 2 | [6 empty] | 2 | 0.2622 | 2.2622 | 15% | 0.33933 | 2.6015
|  |  |  | 1.2.1.11 | vacuum valve, pneumatic act. (swagelok SS-8BK-1C) | ea | 80 | eu | 273 | 21.84 | [6 empty] | 21.84 | 2.8632 | 24.7032 | 15% | 3.7055 | 28.4087
|  |  |  | 1.2.1.12 | feedthrough (ceramtec 6 pin 1kV p/n 161212-02-W) | ea | 80 | eu | 190 | 15.2 | [6 empty] | 15.2 | 1.9927 | 17.1927 | 15% | 2.5789 | 19.7716
|  |  |  | 1.2.1.13 | compression and VCR fittings | ea | 100 | eu | 50 | 5 | [6 empty] | 5 | 0.6555 | 5.6555 | 15% | 0.84832 | 6.5038
|  |  |  | 1.2.1.14 | TPH | gm | 100 | eu | 2 | 0.2 | [6 empty] | 0.2 | 0.02622 | 0.22622 | 15% | 0.033933 | 0.26015
|  |  |  | 1.2.1.15 | Optical adhesive | gm | 100 | eu | 2 | 0.2 | [6 empty] | 0.2 | 0.02622 | 0.22622 | 15% | 0.033933 | 0.26015
1.2.2 Fabrications
|  |  |  | 1.2.2.1 | Tube/WLS bar insertion tooling | lot | 1 | se | 2000 | 2 | 1 | 80 | 80 | MS | 79.4335 | 6.3547 | 8.3547 | 2.2385 | 10.5932 | 50% | 5.2966 | 15.8898
|  |  |  | 1.2.2.1 | TPH coating equipment | lot | 1 | se | 2000 | 2 | 1 | 80 | 80 | MS | 79.4335 | 6.3547 | 8.3547 | 2.2385 | 10.5932 | 50% | 5.2966 | 15.8898
|  |  |  | 1.2.2.2 | Insertion guide bonding | lot | 100 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.2.2 | TPH coating | lot | 100 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.2.3 | resistive stripe and grade ring install | lot | 100 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.2.4 | End cap bonding | lot | 100 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
1.2.3 Assembly
|  |  |  | 1.2.3.1 | Test and Calibrate PMTs | ea | 0 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.3.2 | Pot bases to PMTs | ea | 0 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.3.3 | Cement WLS bars to optical transitions | ea | 0 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.3.4 | Cement PMTs to optical transitions | ea | 0 | se | 0 | 0 | 100 | 1 | 100 | MU | 53.0983 | 5.3098 | 5.3098 | 1.6514 | 6.9612 | 50% | 3.4806 | 10.4418
|  |  |  | 1.2.3.5 | Assemble WLS Tube assemblies | ea | 0 | se | 0 | 0 | 100 | 2 | 200 | MU | 53.0983 | 10.6197 | 10.6197 | 3.3027 | 13.9224 | 50% | 6.9612 | 20.8835
|  |  |  | 1.2.3.6 | Assemble WLS Tube assemblies to Xenon Vessel | ea | 0 | se | 0 | 0 | 72 | 0.5 | 36 | MA | 75.5325 | 2.7192 | 2.7192 | 0.84566 | 3.5648 | 50% | 1.7824 | 5.3472
|  | 1.3 |  |  | Xenon Vessel |  |  |  |  | 5.13 |  |  | 452 |  |  | 35.7791 | 40.9091 | 11.7998 | 52.709 | 26.28% | 13.851 | 66.56
1.3.1 Procurements
|  |  |  | 1.3.1.1 | Vessel Body (PMMA) | lb | 200 | eu | 2 | 0.4 | 1 | 80 | 80 | MS | 79.4335 | 6.3547 | 6.7547 | 2.0287 | 8.7834 | 15% | 1.3175 | 10.1009
|  |  |  | 1.3.1.2 | Feedthrough Ring (Al) | lb | 200 | eu | 2 | 0.4 | 1 | 80 | 80 | MS | 79.4335 | 6.3547 | 6.7547 | 2.0287 | 8.7834 | 15% | 1.3175 | 10.1009
|  |  |  | 1.3.1.3 | Bottom plate (PMMA) | lb | 100 | eu | 2 | 0.2 | 1 | 40 | 40 | MS | 79.4335 | 3.1773 | 3.3773 | 1.0144 | 4.3917 | 40% | 1.7567 | 6.1484
|  |  |  | 1.3.1.3 | Shield Ring (Cu) | lb | 560 | eu | 4 | 2.24 | 1 | 120 | 120 | MS | 79.4335 | 9.532 | 11.772 | 3.2581 | 15.0301 | 40% | 6.0121 | 21.0422
|  |  |  | 1.3.1.4 | Top plate | lb | 120 | cp | 2 | 0.24 | [6 empty] | 0.24 | 0.031464 | 0.27146 | 40% | 0.10859 | 0.38005
|  |  |  | 1.3.1.5 | Valve Plates | ea | 2 | cp | 200 | 0.4 | [6 empty] | 0.4 | 0.05244 | 0.45244 | 40% | 0.18098 | 0.63342
|  |  |  | 1.3.1.6 | Bolts, Springs and Misc. Parts | lot | 1 | pe | 150 | 0.15 | [6 empty] | 0.15 | 0.019665 | 0.16967 | 20% | 0.033933 | 0.2036
1.3.2 Fabrications
|  |  |  | 1.3.2.1 | Foil Frame Carrier | lot | 1 | se | 100 | 0.1 | 1 | 16 | 16 | MS | 79.4335 | 1.2709 | 1.3709 | 0.40837 | 1.7793 | 20% | 0.35586 | 2.1352
|  |  |  | 1.3.2.2 | Hinge Pin adapter | lot | 1 | se | 100 | 0.1 | 1 | 8 | 8 | MS | 79.4335 | 0.63547 | 0.73547 | 0.21074 | 0.94621 | 20% | 0.18924 | 1.1355
|  |  |  | 1.3.2.3 | Backplate | lot | 1 | se | 100 | 0.1 | 1 | 8 | 8 | MS | 79.4335 | 0.63547 | 0.73547 | 0.21074 | 0.94621 | 20% | 0.18924 | 1.1355
|  |  |  | 1.3.2.4 | Front plate | lot | 1 | se | 100 | 0.1 | 1 | 8 | 8 | MS | 79.4335 | 0.63547 | 0.73547 | 0.21074 | 0.94621 | 20% | 0.18924 | 1.1355
|  |  |  | 1.3.2.5 | Vacuum Box | lot | 1 | se | 400 | 0.4 | 1 | 32 | 32 | MS | 79.4335 | 2.5419 | 2.9419 | 0.84296 | 3.7848 | 20% | 0.75697 | 4.5418
|  |  |  | 1.3.2.6 | Vacuum Box top plate | lot | 1 | se | 100 | 0.1 | 1 | 4 | 4 | MS | 79.4335 | 0.31773 | 0.41773 | 0.11193 | 0.52966 | 20% | 0.10593 | 0.63559
|  |  |  | 1.3.2.7 | Support Stand | lot | 1 | se | 200 | 0.2 | 1 | 24 | 24 | MS | 79.4335 | 1.9064 | 2.1064 | 0.61911 | 2.7255 | 20% | 0.5451 | 3.2706
1.3.4 Assembly
|  |  |  | 1.3.4.1 | Assemble and survey vacuum box | lot | 1 | pe | 0 | 0 | 1 | 32 | 32 | MA | 75.5325 | 2.417 | 2.417 | 0.7517 | 3.1687 | 25% | 0.79218 | 3.9609
|  | 1.4 |  |  | Pressure Vessel |  |  |  |  | 135.89 |  |  | 4088 |  |  | 235.8506 | 371.7406 | 91.1647 | 462.9053 | 71.62% | 331.5173 | 794.4225
1.4.1 Procurements
|  |  |  | 1.4.1.1 | Pressure Vessel, titanium CP-1, with heads and feedthrough flange | ea | 1 | cp | 50000 | 50 | [6 empty] | 50 | 6.555 | 56.555 | 15% | 8.4832 | 65.0383
|  |  |  | 1.4.1.1 | Electrical Standoffs, PEEK | ea | 4 | cp | 1000 | 4 | [6 empty] | 4 | 0.5244 | 4.5244 | 15% | 0.67866 | 5.2031
1.4.2 Fabrications
|  |  |  | 1.4.2.1 | Triplet to Foil Beamtube | lot | 1 | pe | 50 | 0.05 | 1 | 4 | 4 | MS | 79.4335 | 0.31773 | 0.36773 | 0.10537 | 0.4731 | 20% | 0.094621 | 0.56773
[5 empty] | " | lot | 1 | pe | 50 | 0.05 | 1 | 16 | 16 | SM | 78.6697 | 1.2587 | 1.3087 | 0.39802 | 1.7067 | 20% | 0.34135 | 2.0481
[5 empty] | " | lot | 1 | pe | 0 | 0 | 1 | 4 | 4 | MP | 79.4335 | 0.31773 | 0.31773 | 0.098815 | 0.41655 | 20% | 0.08331 | 0.49986
|  |  |  | 1.4.2.2 | Foil to Quartersphere Beamtube | lot | 1 | pe | 50 | 0.05 | 1 | 6 | 6 | MS | 79.4335 | 0.4766 | 0.5266 | 0.15478 | 0.68138 | 20% | 0.13628 | 0.81765
[5 empty] | " | lot | 1 | pe | 50 | 0.05 | 1 | 6 | 6 | SM | 78.6697 | 0.47202 | 0.52202 | 0.15335 | 0.67537 | 20% | 0.13507 | 0.81045
[5 empty] | " | lot | 1 | pe | 0 | 0 | 1 | 4 | 4 | MP | 79.4335 | 0.31773 | 0.31773 | 0.098815 | 0.41655 | 20% | 0.08331 | 0.49986
|  |  |  | 1.4.2.3 | Quartersphere to Target Chamber Beamtube | lot | 1 | pe | 200 | 0.2 | 1 | 40 | 40 | MS | 79.4335 | 3.1773 | 3.3773 | 1.0144 | 4.3917 | 20% | 0.87834 | 5.2701
[5 empty] | " | lot | 1 | pe | 50 | 0.05 | 1 | 20 | 20 | SM | 78.6697 | 1.5734 | 1.6234 | 0.49588 | 2.1193 | 20% | 0.42386 | 2.5431
[5 empty] | " | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MP | 79.4335 | 0.63547 | 0.63547 | 0.19763 | 0.8331 | 20% | 0.16662 | 0.99972
|  |  |  | 1.4.2.4 | Target Chamber to Q24 Valve Beamtube | lot | 1 | pe | 200 | 0.2 | 1 | 12 | 12 | MS | 79.4335 | 0.9532 | 1.1532 | 0.32267 | 1.4759 | 20% | 0.29517 | 1.771
[5 empty] | " | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MP | 79.4335 | 0.63547 | 0.63547 | 0.19763 | 0.8331 | 20% | 0.16662 | 0.99972
|  | 1.5 |  |  | Gas Handling System |  |  |  |  | 45.76 |  |  | 2600 |  |  | 148.3032 | 194.0632 | 52.1214 | 246.1846 | 83.45% | 205.4337 | 451.6184
1.5.1 Procurements
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  | 1.5 |  |  | Field Cage System |  |  |  |  | 12.08 |  |  | 1360 |  |  | 77.4119 | 89.4919 | 25.6588 | 115.1507 | 87.61% | 100.8832 | 216.034
1.5.1 Procurements
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  | 1.5 |  |  | Installation |  |  |  |  | 5.14 |  |  | 696 |  |  | 39.5555 | 44.6955 | 12.9756 | 57.6712 | 88.51% | 51.0464 | 108.7176
1.5.1 Procurements
|  |  |  | 1.5.1.1 | Survey floor for anchor drilling | ea | 8 | hr | 225 | 1.8 | [6 empty] | 1.8 | 0.23598 | 2.036 | 50% | 1.018 | 3.054
|  |  |  | 1.5.1.2 | Floor bolts and shims, etc. | lot | 12 | vq | 20 | 0.24 | [6 empty] | 0.24 | 0.031464 | 0.27146 | 50% | 0.13573 | 0.4072
1.5.2 Fabrications
|  |  |  | 1.5.2.1 | Support Struts | ea | 6 | pe | 500 | 3 | 1 | 16 | 16 | MS | 79.4335 | 1.2709 | 4.2709 | 0.78856 | 5.0595 | 20% | 1.0119 | 6.0714
|  |  |  | 1.5.2.2 | Gantry Crane Modification | lot | 1 | se | 100 | 0.1 | 1 | 16 | 16 | MS | 79.4335 | 1.2709 | 1.3709 | 0.40837 | 1.7793 | 20% | 0.35586 | 2.1352
|  |  |  | 1.5.2.3 | Drill and tap GRETINA baseplate (mount+foil) | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MU | 53.0983 | 2.5487 | 2.5487 | 0.79265 | 3.3414 | 100% | 3.3414 | 6.6827
1.5.3 GRETINA Disassembly (in Cave 4C)
|  |  |  | 1.5.3.1 | Utility Disconnect | lot | 1 | pe | 0 | 0 | 2 | 16 | 32 | MU | 53.0983 | 1.6991 | 1.6991 | 0.52843 | 2.2276 | 100% | 2.2276 | 4.4552
|  |  |  | 1.5.3.2 | Quad removal and storage | lot | 1 | pe | 0 | 0 | 2 | 16 | 32 | MU | 53.0983 | 1.6991 | 1.6991 | 0.52843 | 2.2276 | 100% | 2.2276 | 4.4552
|  |  |  | 1.5.3.3 | Quartersphere removal and stage | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MU | 53.0983 | 2.5487 | 2.5487 | 0.79265 | 3.3414 | 100% | 3.3414 | 6.6827
|  |  |  | 1.5.3.4 | Gearbox removal and stage | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MU | 53.0983 | 2.5487 | 2.5487 | 0.79265 | 3.3414 | 100% | 3.3414 | 6.6827
|  |  |  | 1.5.3.5 | Axle-Tee removal and stage | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MU | 53.0983 | 2.5487 | 2.5487 | 0.79265 | 3.3414 | 100% | 3.3414 | 6.6827
|  |  |  | 1.5.3.6 | Strut and Baseplate removal | lot | 1 | pe | 0 | 0 | 2 | 8 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
1.5.4 BGS Partial Disassembly and Modification (in Cave 1)
|  |  |  | 1.5.4.1 | Target Chamber, Diagnostic Box and Baffle Removal | lot | 1 | pe | 0 | 0 | 2 | 16 | 32 | MU | 53.0983 | 1.6991 | 1.6991 | 0.52843 | 2.2276 | 100% | 2.2276 | 4.4552
|  |  |  | 1.5.4.2 | Utility Disconnect | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
|  |  |  | 1.5.4.3 | Cable tray removal | lot | 1 | pe | 0 | 0 | 1 | 4 | 4 | MU | 53.0983 | 0.21239 | 0.21239 | 0.066054 | 0.27845 | 100% | 0.27845 | 0.55689
|  |  |  | 1.5.4.4 | Replumb triplet magnets | lot | 1 | pe | 0 | 0 | 1 | 4 | 4 | MU | 53.0983 | 0.21239 | 0.21239 | 0.066054 | 0.27845 | 100% | 0.27845 | 0.55689
|  |  |  | 1.5.4.5 | Modify Q24 cover | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
1.5.5 Assembly
|  |  |  | 1.5.5.1 | Install LN2 feed and exhaust lines | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MU | 53.0983 | 2.5487 | 2.5487 | 0.79265 | 3.3414 | 100% | 3.3414 | 6.6827
[5 empty] | " | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | SM | 78.6697 | 3.7761 | 3.7761 | 1.1744 | 4.9505 | 100% | 4.9505 | 9.9011
|  |  |  | 1.5.5.2 | Drill floor and set anchors | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
|  |  |  | 1.5.5.3 | Inspect anchors | lot | 1 | pe | 0 | 0 | 1 | 4 | 4 | FA | 148.125 | 0.5925 | 0.5925 | 0.18427 | 0.77677 | 100% | 0.77677 | 1.5535
|  |  |  | 1.5.5.4 | Move modified baseplate into cave 1 | lot | 1 | pe | 0 | 0 | 2 | 4 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
|  |  |  | 1.5.5.5 | Mount baseplate to floor | lot | 1 | pe | 0 | 0 | 1 | 4 | 4 | MU | 53.0983 | 0.21239 | 0.21239 | 0.066054 | 0.27845 | 100% | 0.27845 | 0.55689
|  |  |  | 1.5.5.6 | Assemble crane in cave 1 | lot | 1 | pe | 0 | 0 | 2 | 8 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
|  |  |  | 1.5.5.7 | Move axle-tee into cave | lot | 1 | pe | 0 | 0 | 2 | 8 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
|  |  |  | 1.5.5.8 | Mount and assemble axle-tee | lot | 1 | pe | 0 | 0 | 2 | 8 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
|  |  |  | 1.5.5.9 | Move quartersphere into cave 1 | lot | 1 | pe | 0 | 0 | 2 | 8 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
|  |  |  | 1.5.5.10 | Assemble quartersphere | lot | 1 | pe | 0 | 0 | 2 | 8 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
|  |  |  | 1.5.5.11 | Survey and Align quartersphere | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MUS | 56.2002 | 2.6976 | 2.6976 | 0.83896 | 3.5366 | 100% | 3.5366 | 7.0731
|  |  |  | 1.5.5.12 | Install Quads | lot | 1 | pe | 0 | 0 | 2 | 24 | 48 | MU | 53.0983 | 2.5487 | 2.5487 | 0.79265 | 3.3414 | 100% | 3.3414 | 6.6827
|  |  |  | 1.5.5.13 | Install Target Chamber | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
|  |  |  | 1.5.5.14 | Install Foil Vacuum Barrier System | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
|  |  |  | 1.5.5.15 | Install Beamtubes | lot | 1 | pe | 0 | 0 | 1 | 8 | 8 | MU | 53.0983 | 0.42479 | 0.42479 | 0.13211 | 0.55689 | 100% | 0.55689 | 1.1138
|  |  |  | 1.5.5.16 | Install Cabling and LN2 connections | lot | 1 | pe | 0 | 0 | 1 | 16 | 16 | MU | 53.0983 | 0.84957 | 0.84957 | 0.26422 | 1.1138 | 100% | 1.1138 | 2.2276
[5 empty] | LBNL jobs created (FTE) |  |  |  |  | #REF!
[5 empty] | External jobs created (FTE) |  |  |  |  | #REF!
[5 empty] | Total jobs created (FTE) |  |  |  |  | #REF!