Fabrication (LBNL except as noted) (as of 5/6/10)

- Spool  (bid awarded this week)

- Source Insertion tube (add to spool order)

- Mesh planes (in work, TAMU)

- TPC base plate

- PEEK rods

- PEEK spacers

- Field Cage Panels (outside electronics fab, Polyflon)

- Field Cage Support Panels (outside electronics fab, any mfr.)

- Posts for field cage panels

- SiPMT (back reflector) support frame

- Gas feed bulkhead fitting

- Plenum

- Hose or tube connections for plenum

- Anti-Corona balls, rings, cable bend links,  spool cable guides

Pre assembly

- Assemble back reflector to SiPMY hex frame

- Field Cage Panels

  - Trim and bend resistor leads for field cage panels

  - Use resistor solder fixture to hold resistors; solder to field cage panels.

  - Pre-tin post bases

  - Assemble posts to support panels (or fixture, if one)

  - Solder posts to field cage panels; remove support panels

  - Solder end resistors to support panels

  - Assemble support panels to field cage panels

- Mesh Planes

  - Assemble rim reflectors to both EL region mesh planes

  - Check that no mesh wires are protruding on exterior surface; trim with razor blade if necessary

- PMT Assembly

  - Place PMT mount plane with normal vertical, pins up,  perimeter fixture

  - Insert support tubes into holes

  - Assemble PMTs to PMT mount plane

  - Place cover over PMT faces; clamp to PMT mount plane

  - Flip assembly over and place on table

  - Solder cables to PMT pins

  - Assemble PMT back mount plate to support tubes; tighten nuts

  - Assemble plenum to PMT back mount plate

TPC Assembly

- place lid horizontal; spool need not be attached

- insert PEEK base nuts into base pockets

- assemble base to lid

- assemble PEEK rods to base nuts

- assemble spacers #1

- assemble SiPMT frame

- assemble spacers #2

- assemble mesh plane #1; mesh down

- assemble spacers #3

- assemble mesh plane #2 (EL); mesh up

- assemble spacers #4

- assemble gap reflector, if used

- assemble mesh plane #3 (EL); mesh down

- assemble spacers #5

- assemble mesh plane #4

- assemble spacers #6

- assemble mesh plane #5

- assemble PMT Assembly

- assemble PEEK nuts to PEEK rods; do not tighten yet

- use large machinist square to align stack perpendicular to base plate (lid)

- stack may still have torsion; assemble field cage panels, if possible and check flatness. Then remove screws on one edge for each panel

- tighten PEEK nuts progressively to 50 in-lbf.

- finish assembly of field cage panels to mesh frames (minus HV cables)