## Sheet1
Subsystem |  |  | Finish Dates
Subsubsystem
|  | Item | dwg | in fab or proc. | est fin. | received | hr (ea) | rate | cost | est cost | shop
TPC Internal
Support
|  | baseplate | 5/14 | 5/17 | 5/28 | 6/6 | 6 | 100 | 600 |  | rk
|  | tension rods | 5/26 | 5/26 | 5/28 | 6/9 | 2 | 125 | 250 |  | sf
|  | compression spacers | 5/23 | 5/24 | 5/26 | 6/1 | 6 | 125 | 750 |  | sf
|  | PEEK nuts |  |  |  | 5/15 | 40 | 3.34 | 133.6
Grid Assemblies
|  | mesh planes | 4/6 | 4/7 | 7/24 | [5 empty] | ms,tamu
|  | back reflector frame | 5/14 | 5/14 | 5/19 | 5/19 | 6 | 125 | 750 |  | sf
|  | back reflector | 5/21 | 5/22 |  | 6/1 | 2 | 125 | 250 |  | sf
|  | 0-80 screws |  |  |  | 5/15 | 1 | 5.5 | 5.5
|  | rim reflectors | 6/1 | 6/24 | [6 empty] | rk
| Field Cage | [7 empty] | 0
|  | field cage panels | 5/23 | 5/23 | 7/16 |  |  |  | 8500
|  | resistor prep | [8 empty] | phys
|  | f.c. panel assembly |  |  | 8/1 | [5 empty] | phys
|  | resistors, intertrace, Newark |  |  |  | 5/14 | 53 | 6.71 | 355.63
|  | resistors, intertrace, digiKey |  |  |  | 5/25 | 105 | 2.75 | 288.75
|  | resistors, end, various |  |  |  | 5/23 |  |  | 0
|  | HV cable |  |  |  | 5/23 | 125 | 4 | 500
|  | 2-56 screws, SS |  |  |  | 5/15 | 1 | 5.27 | 5.27
|  | 2-56 screws, nylon |  |  |  | 5/15 | 1 | 4.99 | 4.99
|  | support panels | 7/11 | 7/12 | 7/16
|  | cable terminations | 6/5 | 6/10 | 7/16 | [5 empty] | rk
termination bushings
|  | 0-80 x 1 screws (for studs) |  | 7/12 | 7/13
|  | posts | 7/12 | 7/12 | 7/16 | [5 empty] | 71
|  | HV cable ring support |  |  | 7/15
|  | HV cable bend support | 7/12 | 7/13 | 7/23
|  | soldering jig | 7/13 | 7/14 | 7/20 | [5 empty] | 71
PMT array
|  | PMT mount plane | [6 empty] | 0
|  | PMT back plane |  |  |  | 7/1 |  |  | 0
|  | gas plenum | 5/25 | 5/26 | 7/23 |  | 6 |  | 0 |  | ms
|  | PMT support tubes |  |  |  | 7/1 | 6 |  | 0
|  | nuts |  |  |  | 7/1 |  |  | 0
Vessel and Gas system
|  | spool |  |  |  | 5/27 | 1 | 1900 | 1900
|  | source tube |  | 6/8 | 7/15 | 6/30 |  | 1380 | 0
|  | plumbing (see T. Miller) |  |  |  | 7/1
|  | pressure test |  |  | 7/3