## IST Stave Progress
Updated	3/8/2013
STAVE Numbers				Prep			Open Stave				Assembly				Bare Staves				Quality Assurance				Shipping
STAVE Starts	Hybrid Serial Number	Production Database Number	LBNL Serial Number	Received	Pictures	Masking	Co-Cured	Foam Bond	Honey-Comb	Close-Out Bond	Core Ground	Foam Machined	Tube Bonded	Stave Closed	Tube Swaged	Connector Holes	Ground Connection	Plasma Clean	Pressure Cycle Leak Result	In Survey	Survey Result	Finish Date	Boxed	Shipping Number	Comment
1	IST-001	Pre-Prod.					n/a		n/a		n/a	n/a	n/a		x	Delivered	Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
2	IST-002	Pre-Prod.					n/a		n/a		n/a	n/a	n/a		x	Delivered	Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
3	IST-003	Pre-Prod.					n/a		n/a		n/a	n/a	n/a		x	Delivered	Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
4	IST-004	104455					*		*	*	*	*	*	11/12/2012	x	794056251734	Deliver without Swage or Survey
5	IST-005	104456					*		*	*	*	*	*	11/12/2012	x	794056251734	Deliver without Swage or Survey
6	IST-006	104463					*				*	*	*	12/4/2012	x	794214631445	No Swage or Survey. Tube damage from drill. He leak checked 3.0x10-10 Backfill w/Hysol 9394 epoxy
7	IST-007	104467					*				*	*	*	12/4/2012	x	794214631445	No Swage or Survey
8	IST-008	104471					*				*	*	*	12/4/2012	x	794214631445	No Swage or Survey
9	IST-009	104481					*				*	*	*	1/11/2013	x	794498410645
10	IST-010	104485					*				*	*	*	1/11/2013	x	794498410645
11	IST-011	104497					*				*	*	*	1/11/2013	x	794498410645
12	IST-012	104501					*				*	*	*	1/17/2013	x	794545163503
13	IST-013	104505					*				*	*	*	1/17/2013	x	794545163503
14	IST-014	104509					*				*	*	*	1/17/2013	x	794545163503
15	IST-015	104513					*				*	*	*	1/17/2013	x	794545163503
16	IST-016	104517					*				*	*	*	2/12/2013	x	794735773089
17	IST-017	104586					*				*	*	*	2/12/2013	x	794735773089
18	IST-018	104590					*				*	*	*	2/12/2013	x	794735773089
19	IST-019	104596					*				*	*	*	2/12/2013	x	794735773089
20	IST-020	104600					*				*	*	*	2/12/2013	x	794735773089
21	IST-021	104604					*				*	*	*	3/5/2013	x	794894557126
22	IST-022	104608					*				*	*	*	3/5/2013	x	794894557126
23	IST-023	104612					*				*	*	*	3/5/2013	x	794894557126
24	IST-024	104616					*				*	*	*	3/5/2013	x	794894557126
25	IST-025	104620					*				*	*	*	3/5/2013	x	794894557126
26	IST-026	104624					*				*	*	*	3/12/2013	x	799262901878
27	IST-027	104628					*				*	*	*	3/12/2013	x	799262901878
28	IST-028	104632					*				*	*	*	3/12/2013	x	799262901878
29	IST-029	104636					*				*	*	*	3/12/2013	x	799262901878
30	IST-030	104640					*				*	*	*	3/12/2013	x	799262901878
31	IST-031	104644					*				*	*	*	3/21/2013	x	799339372630
32	IST-032	104648					*				*	*	*	3/21/2013	x	799339372630
33	IST-033	104652					*				*	*	*	3/21/2013	x	799339372630
34	IST-034	104656					*				*	*	*	3/21/2013	x	799339372630
35	IST-035	104660					*				*	*	*	3/21/2013	x	799339372630
36	IST-036	104664					*				*	*	*	3/25/2013	x	799362420355
37	IST-037	104668					*				*	*	*	4/23/2013	x	799595542958
38	IST-038	104672					*				*	*	*	4/23/2013	x	799595542958
39	IST-039	104682					*				*	*	*	4/23/2013	x	799595542958
40	IST-040	104686					*				*	*	*	4/23/2013	x	799595542958
41	IST-041	104690					*				*	*	*	5/15/2013	x	799773149275
42	IST-042	104694					*				*	*	*	5/15/2013	x	799773149275
43	IST-043	104700					*				*	*	*	5/15/2013	x	799773149275
44	IST-044	104704					Core Grinding Error
45	IST-045	104708					*				*	*	*	5/15/2013	x	799773149275
46	IST-046	104712					*				*	*	*	5/15/2013	x	799773149275
47	IST-047					*				*	*	*				At LBL for mount Fitting
48	IST-048					*				*	*	*				At LBL for mount Fitting
						0	0			0				0				0		0	0		45	Shipped
						Ready to ship
						45	Total

## IST Ladder Integration
STAVE Numbers			SMT Loading			Shipping		Sensor and ASIC Loading					Shipping		Assembly
STAVE Starts	Hybrid Serial Number	Production Database Number	Received	Location	Components Loaded	Boxed	Shipping Number	Received	Location	Sensors	APV	Wire Bond	Electrical Test	Encapsulate	Boxed	Shipping Number	Assembly Complete	Received At BNL	Electrical Test	Comment
1	IST-001
2	IST-002
3	IST-003
4	IST-004
5	IST-005
6	IST-006
7	IST-007
8	IST-008
9	IST-009
10	IST-010
11	IST-011
12	IST-012
13	IST-013
14	IST-014
15	IST-015
16	IST-016
17	IST-017
18	IST-018
19	IST-019
20	IST-020
21	IST-021
22	IST-022
23	IST-023
24	IST-024
25	IST-025
26	IST-026
27	IST-027
28	IST-028
29	IST-029
30	IST-030
31	IST-031
32	IST-032
33	IST-033
34	IST-034
35	IST-035
36	IST-036
37	IST-037
38	IST-038
39	IST-039
40	IST-040
41	IST-041
42	IST-042
43	IST-043
44
45
			0			0	Shipped	0					0	Shipped			0
				Ready to ship					Ready to ship
				0	Total					0	Total