## IST Stave Progress
Updated | 2013-03-08
STAVE Numbers |  |  |  | Prep |  |  | Open Stave |  |  |  | Assembly |  |  |  | Bare Staves |  |  |  | Quality Assurance |  |  |  | Shipping
STAVE Starts | Hybrid Serial Number | Production Database Number | LBNL Serial Number | Received | Pictures | Masking | Co-Cured | Foam Bond | Honey-Comb | Close-Out Bond | Core Ground | Foam Machined | Tube Bonded | Stave Closed | Tube Swaged | Connector Holes | Ground Connection | Plasma Clean | Pressure Cycle Leak Result | In Survey | Survey Result | Finish Date | Boxed | Shipping Number | Comment
1 | IST-001 | Pre-Prod. | [12 empty] | n/a |  | n/a |  | n/a | n/a | n/a |  | x | Delivered | Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
2 | IST-002 | Pre-Prod. | [12 empty] | n/a |  | n/a |  | n/a | n/a | n/a |  | x | Delivered | Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
3 | IST-003 | Pre-Prod. | [12 empty] | n/a |  | n/a |  | n/a | n/a | n/a |  | x | Delivered | Pre-production unit--no fittings, ground-pin or survey--QC followers not yet developed
4 | IST-004 | 104455 | [12 empty] | * |  | * | * | * | * | * | 2012-11-12 | x | 794056251734 | Deliver without Swage or Survey
5 | IST-005 | 104456 | [12 empty] | * |  | * | * | * | * | * | 2012-11-12 | x | 794056251734 | Deliver without Swage or Survey
6 | IST-006 | 104463 | [12 empty] | * |  |  |  | * | * | * | 2012-12-04 | x | 794214631445 | No Swage or Survey. Tube damage from drill. He leak checked 3.0x10-10 Backfill w/Hysol 9394 epoxy
7 | IST-007 | 104467 | [12 empty] | * |  |  |  | * | * | * | 2012-12-04 | x | 794214631445 | No Swage or Survey
8 | IST-008 | 104471 | [12 empty] | * |  |  |  | * | * | * | 2012-12-04 | x | 794214631445 | No Swage or Survey
9 | IST-009 | 104481 | [12 empty] | * |  |  |  | * | * | * | 2013-01-11 | x | 794498410645
10 | IST-010 | 104485 | [12 empty] | * |  |  |  | * | * | * | 2013-01-11 | x | 794498410645
11 | IST-011 | 104497 | [12 empty] | * |  |  |  | * | * | * | 2013-01-11 | x | 794498410645
12 | IST-012 | 104501 | [12 empty] | * |  |  |  | * | * | * | 2013-01-17 | x | 794545163503
13 | IST-013 | 104505 | [12 empty] | * |  |  |  | * | * | * | 2013-01-17 | x | 794545163503
14 | IST-014 | 104509 | [12 empty] | * |  |  |  | * | * | * | 2013-01-17 | x | 794545163503
15 | IST-015 | 104513 | [12 empty] | * |  |  |  | * | * | * | 2013-01-17 | x | 794545163503
16 | IST-016 | 104517 | [12 empty] | * |  |  |  | * | * | * | 2013-02-12 | x | 794735773089
17 | IST-017 | 104586 | [12 empty] | * |  |  |  | * | * | * | 2013-02-12 | x | 794735773089
18 | IST-018 | 104590 | [12 empty] | * |  |  |  | * | * | * | 2013-02-12 | x | 794735773089
19 | IST-019 | 104596 | [12 empty] | * |  |  |  | * | * | * | 2013-02-12 | x | 794735773089
20 | IST-020 | 104600 | [12 empty] | * |  |  |  | * | * | * | 2013-02-12 | x | 794735773089
21 | IST-021 | 104604 | [12 empty] | * |  |  |  | * | * | * | 2013-03-05 | x | 794894557126
22 | IST-022 | 104608 | [12 empty] | * |  |  |  | * | * | * | 2013-03-05 | x | 794894557126
23 | IST-023 | 104612 | [12 empty] | * |  |  |  | * | * | * | 2013-03-05 | x | 794894557126
24 | IST-024 | 104616 | [12 empty] | * |  |  |  | * | * | * | 2013-03-05 | x | 794894557126
25 | IST-025 | 104620 | [12 empty] | * |  |  |  | * | * | * | 2013-03-05 | x | 794894557126
26 | IST-026 | 104624 | [12 empty] | * |  |  |  | * | * | * | 2013-03-12 | x | 799262901878
27 | IST-027 | 104628 | [12 empty] | * |  |  |  | * | * | * | 2013-03-12 | x | 799262901878
28 | IST-028 | 104632 | [12 empty] | * |  |  |  | * | * | * | 2013-03-12 | x | 799262901878
29 | IST-029 | 104636 | [12 empty] | * |  |  |  | * | * | * | 2013-03-12 | x | 799262901878
30 | IST-030 | 104640 | [12 empty] | * |  |  |  | * | * | * | 2013-03-12 | x | 799262901878
31 | IST-031 | 104644 | [12 empty] | * |  |  |  | * | * | * | 2013-03-21 | x | 799339372630
32 | IST-032 | 104648 | [12 empty] | * |  |  |  | * | * | * | 2013-03-21 | x | 799339372630
33 | IST-033 | 104652 | [12 empty] | * |  |  |  | * | * | * | 2013-03-21 | x | 799339372630
34 | IST-034 | 104656 | [12 empty] | * |  |  |  | * | * | * | 2013-03-21 | x | 799339372630
35 | IST-035 | 104660 | [12 empty] | * |  |  |  | * | * | * | 2013-03-21 | x | 799339372630
36 | IST-036 | 104664 | [12 empty] | * |  |  |  | * | * | * | 2013-03-25 | x | 799362420355
37 | IST-037 | 104668
38 | IST-038 | 104672
39 | IST-039 | 104682
40 | IST-040 | 104686
41 | IST-041 | 104690
42 | IST-042 | 104694
43 | IST-043 | 104700
44 | IST-044 | 104704 | [21 empty] | Core Grinding Error
45 | IST-045 | 104708
46 | IST-046 | 104712
47 | IST-047
48 | IST-048
[6 empty] | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 36 | Shipped
Ready to ship
[23 empty] | 36 | Total

## IST Ladder Integration
STAVE Numbers |  |  | SMT Loading |  |  | Shipping |  | Sensor and ASIC Loading | [6 empty] | Shipping |  | Assembly
STAVE Starts | Hybrid Serial Number | Production Database Number | Received | Location | Components Loaded | Boxed | Shipping Number | Received | Location | Sensors | APV | Wire Bond | Electrical Test | Encapsulate | Boxed | Shipping Number | Assembly Complete | Received At BNL | Electrical Test | Comment
1 | IST-001
2 | IST-002
3 | IST-003
4 | IST-004
5 | IST-005
6 | IST-006
7 | IST-007
8 | IST-008
9 | IST-009
10 | IST-010
11 | IST-011
12 | IST-012
13 | IST-013
14 | IST-014
15 | IST-015
16 | IST-016
17 | IST-017
18 | IST-018
19 | IST-019
20 | IST-020
21 | IST-021
22 | IST-022
23 | IST-023
24 | IST-024
25 | IST-025
26 | IST-026
27 | IST-027
28 | IST-028
29 | IST-029
30 | IST-030
31 | IST-031
32 | IST-032
33 | IST-033
34 | IST-034
35 | IST-035
36 | IST-036
37 | IST-037
38 | IST-038
39 | IST-039
40 | IST-040
41 | IST-041
42 | IST-042
43 | IST-043
44
45
|  |  | 0 |  |  | 0 | Shipped | 0 | [6 empty] | 0 | Shipped |  |  | 0
[7 empty] | Ready to ship | [8 empty] | Ready to ship
[6 empty] | 0 | Total | [7 empty] | 0 | Total